## TOP 2025
SUB 1 | SUB 2 | Task Name | TYPE | kV | Duration | Start | Finish
GORT |  | BUSCOUPLER COMMISSIONING WORKS /WIRING MODIFICATIONS | PROJ | 110 | 1d | 2025-01-06
GORT |  | TRANSFORMER 2 OUTAGE TO REPAIR EM356 sticking and supertapp wiring | PROJ | 110 | 2w | 2025-01-06
HANNAHSTOWN |  | IBTX3 3YR PART MAJOR TC FLUSH AND DOBLE AND MG35 MAINT, inc 275kv CT @ GG18 | MAINT | 275 | 8D | 2025-01-06 | 2025-01-17
TANDRAGEE |  | GB5 MAINT BUS - COUPLER | MAINT | 275 | 1W | 2025-01-06 | 2025-01-10
COLERAINE |  | 7L0 MAINT & leak repairs | MAINT | 110 | 2D | 2025-01-06 | 2025-01-08
GORT |  | TRANSFORMER 2 OUTAGE TO REPAIR EM356 sticking | MAINT | 110 | 2W | 2025-01-06 | 2025-01-17
GORT |  | TX2 supertapp relay replacement . | PROJ | 110 | 2w | 2025-01-06 | 2025-01-17
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS | PROJ | 275 | 6M | 2025-01-06 | 2024-06-30
MAGHERAFELT |  | CIRCUIT BREAKER FAILS SCHEME ( 7 SETS ) | PROJ | 275 | 1M | 2025-01-06 | 2025-03-30
MAGHERAFELT |  | SECTION 'A2' ISOLATORS GH4 | MAINT | 275 | 1W | 2025-01-06 | 2025-01-10
COLERAINE |  | 9L0 replace gas guage and CT removal | MAINT | 110 | 2D | 2025-01-09 | 2025-01-10
BANBRIDGE |  | TX3 OIL TOP UP | MAINT | 110 | 1D | 2025-01-11
HANNAHSTOWN | LISBURN B | POLE REPLACEMENTS WORKS lagmore gardens | OHL | 110 | 1w | 2025-01-13 | 2025-01-17
BALLYVALLAGH |  | ME45 MAINT Bus-coupler | MAINT | 110 |  | 2025-01-13 | 2025-01-17
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - 15H2 | MAINT | 110 | 2D | 2025-01-13 | 2025-01-17
KILROOT |  | GJ65 & GJ70 CBF outage associated with GT3 & GT4 | MAINT | 275 | 2d | 2025-01-13 | 2025-01-14
BANBRIDGE |  | BANBRIDGE BR70 33KV WORKS | PROJ | 110 | 1W | 2025-01-19
COOLKEERAGH |  | COOLKEERAGH GA65 BAY - (Statkraft) concrete struture removal including IBTX2 proximity | MAINT | 275 | 2d | 2025-01-20 | 2025-01-21
LISBURN MAIN |  | 21L0 MAINT | MAINT | 110 | 3D | 2025-01-20 | 2024-01-22
KILROOT | TANDRAGEE | OHL AND TOWER PAINTING | OHL | 275 | 2W | 2025-01-20 | 2025-01-31
KILROOT | TANDRAGEE | VT MAINT AND ISOLATORS | MAINT | 275 | 1W | 2025-01-20 | 2025-02-21
KILROOT |  | 275kv CT BAY TANDRAGEE BAY ( BUS - ZONE SETS ) | PROJ | 275 | 5WKS | 2025-01-20 | 2025-02-21
KILROOT | TANDRAGEE | GJ70/GJ75 BAY PQ MONITOR AND WIRING MODIFCATIONS CVT & CT REPLACEMENT | PROJ | 275 | 5w | 2025-01-20 | 2025-02-21
HANNAHSTOWN |  | IBTX1 MINOR / BAY REMOVAL | MAINT | 275 | 2w | 2025-01-20 | 2025-01-31
KILROOT |  | GJ70 MAINT | MAINT | 275 | 5D | 2025-01-20 | 2025-02-21
KILROOT |  | GJ75 MAINT | MAINT | 275 | 5D | 2025-01-20 | 2025-02-21
HANNAHSTOWN | LISBURN A | POLE REPLACEMENTS WORKS on pole 328 Lagmore gardens | OHL | 110 | 1W | 2025-01-20 | 2025-01-24
CASTLEREAGH |  | MC5 MAINT BUS-COUPLER | MAINT | 110 | 5D | 2025-01-20 | 2025-01-24
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) 1H1 | MAINT | 110 | 2D | 2025-01-20 | 2025-01-21
RASHARKIN |  | MU5 MAINT BUS-COUPLER | MAINT | 110 | 1W | 2025-01-20 | 2025-01-24
HANNAHSTOWN |  | IBTX4 REACTOR COMMISSIONING | PROJ | 110 | TBC | 2025-01-20 | 2025-04-30
BALLYLUMFORD | MAGHERAFELT | TOWER PAINTING AND TROLLEY WORKS | OHL | 275 | 2W | 2025-01-22 | 2025-02-02
BALLYLUMFORD | MAGHERAFELT | GD70 PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 2w | 2025-01-22 | 2025-02-02
BALLYLUMFORD | MAGHERAFELT | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS MAGHERAFELT BAY | PROJ | 275 | 10D | 2025-01-22 | 2025-02-02
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) 7H1 | MAINT | 110 | 2D | 2025-01-22 | 2025-01-23
LISBURN MAIN |  | HAN B CVT | MAINT | 110 | 3D | 2025-01-24
CASTLEREAGH |  | GC55 MAINT | MAINT | 275 | 5d | 2025-01-27 | 2025-01-31
COOLKEERAGH | killymalaght | tower painting AND POLE REPLACEMENTS ON POLE 277 | OHL | 110 | 2W | 2025-01-27 | 2025-02-07
HANNAHSTOWN |  | MG5 BUSCOUPLER '1' | MAINT | 110 | 1W | 2025-01-27 | 2025-01-31
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - 8H8 & 9H2 | MAINT | 110 | 3D | 2025-01-27 | 2025-01-29
GARVAGH |  | SECTION 2 BUSBAR | PROJ | 110 | 1w | 2025-01-27 | 2025-01-31
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - 12H2 | MAINT | 110 | 2D | 2025-01-30 | 2025-01-31
TREMOGE |  | MV5 MAINT BUS-COUPLER | MAINT | 110 | 1W | 2025-02-03 | 2025-02-07
CASTLEREAGH |  | GC65 MAINT | MAINT | 275 | 5D | 2025-02-03 | 2025-02-07
TANDRAGEE | LISBURN A | POLE REPLACEMENTS WORKS | OHL | 110 | 1W | 2025-02-03 | 2025-02-07
TANDRAGEE |  | MB5 MAINT DRU 'A' CCT | MAINT | 110 | 1W | 2025-02-03 | 2025-02-07
DRUMNAKELLY |  | 2K0 MAINT | MAINT | 110 | 2D | 2025-02-03 | 2025-02-07
DRUMNAKELLY |  | 3K0 MAINT | MAINT | 110 | 2D | 2025-02-03 | 2025-02-07
HANNAHSTOWN |  | MG60 MAINT BUS-COUPLER '2' | MAINT | 110 | 1W | 2025-02-03 | 2025-02-07
BELFAST CENTRAL MAIN |  | BCM tx B MAJOR AND MR UPGRADES | MAINT | 110 | 3W | 2025-02-03 | 2025-03-07
CASTLEREAGH | CREGAGH - BELFAST CENTRAL | CAS-CRG-BCM B START | PROJ | 110 | 5wks | 2025-02-03 | 2025-03-07
CASTLEREAGH | CREGAGH - BELFAST CENTRAL 'B' | CAS-CRG-BCM B (PROJECTS) - 3 ENDED PROTECTION | PROJ | 110 | 5wks | 2025-02-03 | 2025-03-07
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - 14H2 | MAINT | 110 | 2D | 2025-02-03 | 2025-02-04
GARVAGH |  | SECTION 1 BUSBAR | PROJ | 110 | 1w | 2025-02-03 | 2025-02-07
COLERAINE |  | LOGUESTOWN B CORNER ISOLATOR 6L8,7L4,CX96 AND EL6. | MAINT | 110 | 3D | 2025-02-05 | 2025-02-07
COLERAINE | LOGUESTOWN 'B' | tower painting | OHL | 110 | 1D | 2025-02-05
CASTLEREAGH |  | GC75 MAINT | MAINT | 275 | 5D | 2025-02-10 | 2025-02-14
TANDRAGEE | LISBURN B | POLE REPLACEMENTS WORKS | OHL | 110 | 1W | 2025-02-10 | 2025-02-14
DRUMNAKELLY | TANDRAGEE 'B' | VT AND ISOLATORS DUE | MAINT | 110 | 2D | 2025-02-10 | 2025-02-13
STRABANE |  | GCB 4S0 MAINT | MAINT | 110 | 1W | 2025-02-10 | 2025-02-14
DRUMNAKELLY |  | 1K0 MAINT | MAINT | 110 | 2D | 2025-02-10 | 2025-02-13
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 37D | 2025-02-16 | 2025-03-24
COOLKEERAGH |  | COOLKEERAGH GA65 BAY - Statkraft catenary removal ( during C30 outage ) | MAINT | 275 | 2d | 2025-02-16 | 2025-03-24
KILROOT |  | GJ95 MAINT | MAINT | 275 | 5D | 2025-02-17 | 2025-02-21
KILROOT |  | SECTION A2 ISOLATOR GJ94 AND ESW EG280 | MAINT | 275 | 5D | 2025-02-17 | 2025-02-21
OMAGH | DROMORE 'A' | 1M4,10M8,CX60 AND DROMORE 'A' CVT | MAINT | 110 | 4D | 2025-02-17 | 2025-02-20
COOLKEERAGH | MAGHERAFELT A | CVT replacement for PQ monitors - New CVTs faulty K Kelly to give new dates | PROJ | 275 | 3w | 2025-02-17 | 2025-03-20
COOLKEERAGH | MAGHERAFELT A | GA35 MAINT | MAINT | 275 | 2w | 2025-02-17 | 2025-03-20
DRUMNAKELLY | TANDRAGEE 'C' | VT AND ISOLATORS DUE | MAINT | 110 | 2D | 2025-02-17 | 2025-02-21
STRABANE |  | 6S0 MAINT /REPLACEMENT AND OMAGH A CVT | PROJ | 110 | 7WKS | 2025-02-17 | 2025-04-04
STRABANE | omagh A | POLE REPLACEMENT WORKS & TOWER PAINTING | OHL | 110 | 3W | 2025-02-17 | 2025-02-28
DRUMNAKELLY |  | 8K0 MAINT | MAINT | 110 | 2D | 2025-02-17 | 2025-02-21
STRABANE |  | ISOLATOR REFURBS | PROJ | 110 | N/A | 2025-02-17
TANDRAGEE | Drumnakelly 'C' + Warr' A | TOWER PAINTING TOWER 600A | OHL | 110 | 2D | 2025-02-17 | 2025-02-18
TANDRAGEE | DRUMNAKELLY C | POLE REPLACEMENTS WORKS | OHL | 110 | 2D | 2025-02-17 | 2025-02-18
TREMOGE |  | MV10 MAINT TAMNAMORE CIRCUIT | MAINT | 110 | 1W | 2025-02-24 | 2025-02-28
BALLYVALLAGH |  | ME5 MAINT kells A | MAINT | 110 |  | 2025-02-24 | 2025-02-28
DRUMNAKELLY | TAMNAMORE 'A' CIRCUIT | VT DUE | MAINT | 110 | 2D | 2025-02-24 | 2025-02-26
BALLYCRONANMORE | HANNAHSTOWN A | TOWER PAINTING | OHL | 275 | 1D | 2025-02-24
OMAGH | STRABANE A | 9M8,10M4 AND CX59 INC ESW | MAINT | 110 | 2D | 2025-03-01
DROMORE |  | MW20 MAINT OMAGH B | MAINT | 110 | 5d | 2025-03-03 | 2025-03-07
DROMORE |  | DRUMQUIN ISOLATORS ON BAY | MAINT | 110 | 1D | 2025-03-03
TANDRAGEE |  | TANDRAGEE IBTX2 MINOR INC RX2 | MAINT | 275 | 1W | 2025-03-03 | 2025-03-08
BALLYVALLAGH |  | ME15 MAINT Kells B | MAINT | 110 |  | 2025-03-03 | 2025-03-07
KELLS | CREAGH | TOWER PAINTING AND POLE REPLACMENTS | OHL | 110 | 3D | 2025-03-03 | 2025-03-05
LOGUESTOWN |  | LOG TX 1 MAJOR MAINT | MAINT | 110 | 8d | 2025-03-03 | 2025-03-12
COLERAINE | LIMAVADY | 2L0/3L0 BAY PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 110 | 20D | 2025-03-03 | 2025-03-23
BALLYLUMFORD |  | GT2 Sheath | MAINT | 110 | 5D | 2025-03-03 | 2025-05-23
COLERAINE | LIMAVADY | POLE REPLACEMENTS WORKS Pole 381 to be changed & earth replaced, OK required from Kyle Taylor | OHL | 110 | 1w | 2025-03-03 | 2025-03-06
BALLYLUMFORD |  | BGT2 OUTAGE | GEN | GEN | 88D | 2025-03-03 | 2025-05-30
MAGHERAFELT |  | (CONTROL PANEL REFURBISHMENT) - CBF AND MIMIC BOARD WORKS | PROJ | 275 | 3M | 2025-03-04 | 2025-06-04
BALLYLUMFORD |  | GD30 MAINT & CVT CHANGE | MAINT | 275 | 5D | 2025-03-09
BALLYLUMFORD | HANNAHSTOWN B | CVT REPLACEMENT | PROJ | 275 | 4WK | 2025-03-09
HANNAHSTOWN |  | 275KV ISOLATORS 3 SETS BPS GG4,GG21,GG22 AND BPS MESH CORNER PROTECTION / DISCONNECT IBTX1 | PROJ | 275 | 15WKS | 2025-03-09 | 2025-06-22
BALLYLUMFORD | HANNAHSTOWN B | OHL WORK AND TOWER PAINTING | OHL | 275 | 1D | 2025-03-09
BALLYLUMFORD |  | GD20 MAINT | MAINT | 275 | 5D | 2025-03-09
HANNAHSTOWN |  | GG5 MAINT | MAINT | 275 | 1W | 2025-03-09
HANNAHSTOWN |  | GG20 MAINT | MAINT | 275 | 1W | 2025-03-09 | 2025-06-22
HANNAHSTOWN | BALLYLUMFORD B | line characteristics | MAINT | 275 | 1d | 2025-03-09 | 2025-06-22
HANNAHSTOWN | BALLYLUMFORD B | OHL AND TOWER PAINTING | OHL | 275 | 1w | 2025-03-09 | 2025-06-22
HANNAHSTOWN |  | MG40 MAINT | MAINT | 110 | 1W | 2025-03-10 | 2025-03-14
COLERAINE |  | LOGUESTOWN A CVT MAINT ISOLATOR 5L8,6L4,CX95 AND EL5. | MAINT | 110 | 3D | 2025-03-12 | 2025-03-14
COLERAINE | LOGUESTOWN 'A' | conductor sampling requested by Assets | OHL | 110 | 1W | 2025-03-12
BALLYLUMFORD |  | GD60 maintenance | MAINT | 275 | 5d | 2025-03-16
ENNISKILLEN |  | 4P0 MAINT | MAINT | 110 | 2D | 2025-03-18
ENNISKILLEN |  | TX2 FIRST MAJOR MAINT | MAINT | 110 | 2W | 2025-03-18 | 2025-05-09
ENNISKILLEN |  | 110KV CABLE REPLACEMENT TRANSFORMER 2, INSTALL DISCONNECTOR requries dromore B and mesh open at dromore | PROJ | 110 | 8wks | 2025-03-18 | 2025-05-09
ENNISKILLEN |  | T2 cable alterations and new disconnector | PROJ | 110 | 8WKS | 2025-03-18 | 2025-05-09
ENNISKILLEN |  | T2 REMOVE DOWNDROPPER 1P4/6P8 START OF JOB | PROJ | 110 | 1D | 2025-03-18
NEWRY MAIN |  | TX1 MAJOR inc MR upgrade by BTRAC | MAINT | 110 | 8D | 2025-03-18 | 2025-04-25
ENNISKILLEN |  | ISOALTORS CX123, 4P4, 3P8, EP3 AND DROMORE 'B' VT MAINT | MAINT | 110 | 2D | 2025-03-18 | 2025-04-30
ENNISKILLEN |  | ENN - DRO 'B' CROSSLEAD, GANTRY REMOVAL AT TX2 AND MOVE CX126 POSITION ERECT NEW GANTRYS AND MESH OPEN AT 4P8/3P4. EXCAVATE CABLES UNDER MESH BETWEEN 3P0/4P0, REMOVE DOWNDROPPER FROM ENN - DROMORE TO 4P4/3P8. | PROJ | 110 | 2W | 2025-03-19 | 2025-03-31
COOLKEERAGH | COLERAINE | OHL Pole changes AND TOWER PAINTING | OHL | 110 | 1W | 2025-03-24 | 2025-04-04
BALLYLUMFORD | B21 | GD90 MULTICORE INSTALLATION | PROJ | 275 | 3D | 2025-03-28 | 2025-03-31
BALLYLUMFORD | B31 | B21 OUTAGE | GEN | GEN | 3D | 2025-03-28 | 2025-03-31
TANDRAGEE |  | MB50 MAINT / C/B REPLACEMENT .NEWRY A | PROJ | 110 | 8WKS | 2025-03-31 | 2025-05-23
TANDRAGEE |  | Newry A SHEATH TESTS ( MB50) - cancelled CB MB50 unreliable | MAINT | 110 | 1D | 2025-03-31
TANDRAGEE |  | TANDRAGEE MBXX CIRCUIT BREAKER AND CT REPLACEMENT | PROJ | 110 | 6WKS | 2025-03-31
TANDRAGEE | NEWRY A | TOWER PAINTING 1 ARM OVER HOUSE, ARCING HORN DEFECT REPAIRS | OHL | 110 | 1D | 2025-03-31
TANDRAGEE |  | Earth switch installation mutliple bays | PROJ | 110 |  | 2025-03-31
BALLYLUMFORD |  | IBTX2 MAJOR, GD45 & MD20 | MAINT | 275 | 3W | 2025-03-31 | 2025-04-18
COOLKEERAGH |  | IBTX2 MINOR | MAINT | 275 | 5D | 2025-03-31 | 2025-04-04
ENNISKILLEN |  | TX2 REPLACE CABLE SEALING ENDS AND COMPLETE SEALING END TERMS AT TX2 AND BETWEEN 1P0/6P0, PRESSURE TEST CABLES AND REINSTATE S/S | PROJ | 110 | 6WKS | 2025-03-31 | 2025-04-30
COOLKEERAGH |  | IBTX1 MINOR AND GA25 MAINT,11H0 & ETx1 CONNECTION TO SYSTEM | MAINT | 275 | 2W | 2025-04-07 | 2025-04-18
STRABANE |  | PST REPAIRS NEW PARTS DUE FROM ELIN | MAINT | 110 | 3W | 2025-04-07 | TBC
STRABANE |  | 8S0 MAINT / REPLACEMENT | PROJ | 110 | 5WKS | 2025-04-07 | 2025-05-09
RASHARKIN |  | EARTHING COURSE. | MAINT | 110 | 2d | 2025-04-07
DUNGANNON |  | 3J0 MAINT | MAINT | 110 | 2D | 2025-04-09 | 2025-04-10
BALLYLUMFORD | B32 | B22 OUTAGE | GEN | GEN | 3D | 2025-04-11 | 2025-04-14
BALLYLUMFORD | B22 | GD80 MULTICORE INSTALLATION | PROJ | 275 | 3D | 2025-04-11 | 2025-04-14
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT G1, G3, G5, G6 | PROJ | 275 | 5W | 2025-04-13 | 2025-05-17
DUNGANNON |  | 6J0 MAINT | MAINT | 110 | 2D | 2025-04-14 | 2025-04-15
STRABANE |  | TX2 MAJOR INC SFRA | MAINT | 110 | 8D | 2025-04-14 | 2025-04-20
BALLYVALLAGH |  | ME25 MAINT Larne A | MAINT | 110 |  | 2025-04-14 | 2025-04-18
RASHARKIN |  | EARTHING COURSE. | MAINT | 110 | 2d | 2025-04-14
DUNGANNON |  | 7J0 MAINT | MAINT | 110 | 2D | 2025-04-16 | 2025-04-17
DUNGANNON | TAMNAMORE 'B' | CABLE SHEATH TESTS | MAINT | 110 | 1D | 2025-04-18 | 2025-04-19
DUNGANNON |  | CVT MAINT TAMNAMORE 'C' CIRCUIT | MAINT | 110 | 2D | 2025-04-18
BALLYLUMFORD | B10 | B10 GENERATOR OUTAGE | GEN | GEN | 4D | 2025-04-25 | 2025-04-29
KELLS |  | MF60 MAINT ANTRIM B CIRCUIT | MAINT | 110 | 1WK | 2025-04-28 | 2025-05-09
BALLYLUMFORD |  | IBTX1 MAJOR, GD35 & MD15 | MAINT | 275 | 3w | 2025-04-28 | 2025-05-16
COLERAINE |  | TX1 MAJOR MAINT Inc MR tapchanger BTRAC | MAINT | 110 | 3W | 2025-04-28 | 2025-05-16
ANTRIM MAIN |  | TX1 MAJOR INC MR UPGRADE | maint | 110 | 8D | 2025-04-28 | 2025-05-09
ENNISKILLEN |  | REINSTALL DROMORE B DOWNLEADS TO 4P4/3P8 | PROJ | 110 | 1D | 2025-04-30
ENNISKILLEN |  | T2 REPLACE DOWNDROPPER 1P4/6P8 END OF JOB AND PHASE OUT PLUS TECHNICAL WORKS | PROJ | 110 | 2W | 2025-04-30 | 2025-05-09
GARVAGH |  | MZ30 MAINT BUS-COUPLER | MAINT | 110 | 1W | 2025-05-01
GARVAGH |  | NEW TRANSFORMER INSTALLATION | PROJ | 110 | 2M | 2025-05-01 | 2025-06-30
OMAGH | STRABANE 'B' | 7M8, 8M4 AND CX57 MAINT INC ESW | MAINT | 110 | 2D | 2025-05-12 | 2025-05-13
AGHYOULE |  | TX1 Major inc MR upgrade by BTRAC | MAINT | 110 | 8D | 2025-05-12 | 2025-05-23
ENNISKILLEN |  | Aghyoule cable sealing end MAINT AND MESH ISOLATORS | MAINT | 110 | 3d | 2025-05-12 | 2025-05-15
ENNISKILLEN |  | 2P0 MAINT | MAINT | 110 | 2D | 2025-05-12 | 2025-05-15
STRABANE |  | 7S0 REPLACEMENT AND OMAGH B CVT | PROJ | 110 | 7WKS | 2025-05-12 | 2025-06-27
DUNGANNON |  | replace old TX 1 | PROJ | 110 | 9wks | 2025-05-12 | 2025-07-10
TANDRAGEE |  | MB45 MAINT WAR 'B' CCT | MAINT | 110 | 1W | 2025-05-12 | 2025-05-23
WARINGSTOWN |  | TX2 MAJOR AND MR UPGRADES | MAINT | 110 | 8d | 2025-05-12 | 2025-05-23
STRABANE | OMAGH B | POLE REPLACEMENT WORKS & TOWER PAINTING | OHL | 110 | 3W | 2025-05-12 | 2025-06-27
CASTLEREAGH |  | MC30 MAINT LISNABREENY CCT | MAINT | 110 | 5D | 2025-05-12 | 2025-05-16
COOLKEERAGH |  | GT8 OUTAGE - | GEN | GEN | 5D | 2025-05-19 | 2025-05-24
COOLKEERAGH |  | 10H0 MAINT GT8 BAY | MAINT | 110 | 6D | 2025-05-19 | 2025-05-24
COOLKEERAGH |  | GT8 OUTAGE - | GEN | GEN | tbc | 2025-05-19 | 2025-05-24
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) 10H1 | MAINT | 110 | 5D | 2025-05-19 | 2025-05-24
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - 10H2 | MAINT | 110 | 2D | 2025-05-19 | 2025-05-19
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS BUSCOUPLER 1 GD20 | PROJ | 275 | 12D | 2025-05-19 | 2025-06-01
TANDRAGEE |  | TANDRAGEE IBTX3 MAJOR INC MB80 AND GB95AND REPLACE RX3 BUCHOLZ & PRD'S | MAINT | 275 | 3W | 2025-05-26 | 2025-07-04
TANDRAGEE |  | MB80 C/B REPLACEMENT IBTX3 | PROJ | 110 | 6WKS | 2025-05-26 | 2025-07-04
MAGHERAFELT |  | GH55 MAINT | MAINT | 275 | 1W | 2025-05-27 | 2025-05-31
KELLS |  | Kells IBTX1 MAJOR | MAINT | 275 | 3W | 2025-05-27 | 2025-06-13
TANDRAGEE |  | MB35 MAINT WAR 'A' CCT | MAINT | 110 | 1W | 2025-05-27 | 2025-06-06
WARINGSTOWN |  | TX1 MINOR inc bushigns and tapchanger flush | MAINT | 110 | 5d | 2025-05-27 | 2025-06-06
MAGHERAFELT | TAMNAMORE 'A' | GH55 BAY PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 3WKS | 2025-05-27 | 2025-06-13
CREGAGH |  | Cregagh EC1 AND EC3 AND XC3 | MAINT | 110 | 2d | 2025-06-01
KILROOT |  | GT1 OUTAGE | GEN | GEN | 2D | 2025-06-01 | 2025-06-03
KILROOT |  | NIK GT2 | GEN | GEN | 2D | 2025-06-01 | 2025-06-03
BALLYLUMFORD |  | MD40 MAINT ( GT1 CIRCUIT) | MAINT | 110 | 5D | 2025-06-01
CREGAGH |  | Cregagh Tx A MAJOR | MAINT | 110 | 1w | 2025-06-01
CREGAGH |  | Cregagh Txa spigots | MAINT | 110 | 2d | 2025-06-01
KILROOT |  | NIK GT3 | GEN | GEN | 30D | 2025-06-01 | 2025-07-01
KILROOT |  | NIKGT4 | GEN | GEN | 30D | 2025-06-01 | 2025-07-01
TAMNAMORE |  | DERRYMEEN BESS CONNECTION AND BAY CONSTRUCTION MP45 | PROJ | 110 | TBC | 2025-06-01 | 2026-10-01
KELLS |  | MF50 MAINT ANTRIM A CIRCUIT | MAINT | 110 | 1WK | 2025-06-02 | 2025-06-07
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS BUS COUPLER 2 GD60 | PROJ | 275 | 13D | 2025-06-02 | 2025-06-15
KILROOT |  | GT1 OUTAGE | GEN | GEN | 6D | 2025-06-02 | 2025-06-08
KILROOT |  | GT2 OUTAGE | GEN | GEN | 6D | 2025-06-02 | 2025-06-08
COLERAINE |  | TX2 MAJOR MAINT Inc MR Tapchangers BTRAC | MAINT | 110 | 3W | 2025-06-02 | 2025-06-20
COOLKEERAGH | MAGHERAFELT B | B CIRCUIT OUTAGE CLEANING CONDUCTORS and Conductor covering 20 SPANS | OHL | 275 | 2W | 2025-06-02
ANTRIM MAIN |  | TX2 MAJOR INC MR UPGRADE | maint | 110 | 8D | 2025-06-02 | 2025-06-11
BALLYLUMFORD |  | MD50 MAINT (BUS-COUPLER ) | MAINT | 110 | 5D | 2025-06-02
COOLKEERAGH |  | GA65 BAY MULTIPLE PROXIMITYS ON SECTION A1/A2/MAG AND IBTX2 FOR CIVIL WORKS FOR GANTRYS/A FRAMES | PROJ | 275 | 1M | 2025-06-02 | 2025-06-30
DRUMNAKELLY |  | TX3 MAJOR MAINT | MAINT | 110 | 8D | 2025-06-09 | 2026-06-20
BANBRIDGE |  | TX1 & TX3 MAJOR | MAINT | 110 | 2W | 2025-06-09
CASTLEREAGH |  | MC45 MAINT ( NAR A ) | MAINT | 110 | 1w | 2025-06-09 | 2025-06-13
KELLS |  | 110KV GROUP ALARMS T602M | PROJ | 110 | 3D | 2025-06-11 | 2025-06-13
KELLS |  | IBTX2 MAJOR | MAINT | 110 | 3W | 2025-06-16 | 2025-07-04
CASTLEREAGH |  | MC55 MAINT ( NAR B ) | MAINT | 110 | 1w | 2025-06-16 | 2025-06-20
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS BUS SECTION BREAKER GD40 | PROJ | 275 | 13D | 2025-06-16 | 2025-06-29
COOLKEERAGH | MAGHERAFELT A | A CIRCUIT OUTAGE CLEANING CONDUCTORS and Conductor covering 20 SPANS | OHL | 275 | 2W | 2025-06-16
RASHARKIN |  | MU20 MAINT | MAINT | 110 | 1W | 2025-06-23
DRUMNAKELLY |  | TX1 MAJOR MAINT | MAINT | 110 | 8D | 2025-06-23 | 2025-07-07
CASTLEREAGH |  | MC90 MAINT cregagh A cct | MAINT | 110 | 5D | 2025-06-23 | 2025-06-27
BELFAST CENTRAL MAIN |  | BCM tx A MAJOR AND MR UPGRADES | MAINT | 110 | 3W | 2025-06-23 | 2025-07-10
BELFAST CENTRAL MAIN |  | BCM tx A ETX LV ENCLOSURE | PROJ | 110 | 1W | 2025-06-23 | 2025-07-10
CASTLEREAGH |  | MC75 MAINT RATHGAEL B | MAINT | 110 | 5D | 2025-06-23 | 2025-06-27
RATHGAEL |  | TX2 MAJOR MAINT INC SFRA AND MR UPGRADE | MAINT | 110 | 2W | 2025-06-23 | 2025-07-04
GARVAGH |  | MZ20 MAINT RASHARKIN CIRCUIT | MAINT | 110 | 1W | 2025-06-23
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 1D | 2025-06-24 | 2025-06-25
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 3D | 2025-06-25 | 2025-06-28
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment | PROJ | 275 | 7D | 2025-06-29 | 2025-07-06
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS BALLYCRONANMORE BAY | PROJ | 275 | 13D | 2025-06-30 | 2025-07-11
KILROOT |  | GT1 OUTAGE | GEN | GEN | 1D | 2025-06-30 | 2025-07-01
KILROOT |  | GT2 OUTAGE | GEN | GEN | 1D | 2025-06-30 | 2025-07-01
MOYLE |  | SINGLE POLE OUTAGE | GEN | GEN | 4D | 2025-06-30 | 2025-07-04
COOLKEERAGH |  | INTERBUS TRANSFORMER 1 (INSTALL BUND WALL) - BUND WALL AND BLAST WALL & ETX installation | PROJ | 275 | 25d | 2025-07-01
COOLKEERAGH |  | STATKRAFT CONNECTION | PROJ | 275 | 2Y | 2025-07-01 | 2027-06-01
KELLS |  | NEW CLUSTER CONNECTION build isolators | PROJ | 110 | 5WKS | 2025-07-01 | 2025-11-01
MOYLE |  | SINGLE POLE OUTAGE | GEN | GEN | 5D | 2025-07-03 | 2025-07-08
DRUMQUIN |  | ISOLATOR MX11, EM435 AND EM435B ASSOCIATED WITH TX1 | MAINT | 110 | 1D | 2025-07-04
CASTLEREAGH |  | MC65 MAINT RATHGAEL 'A' | PROJ | 275 | 1W | 2025-07-07 | 2025-07-11
MOYLE |  | 7day outage as per SONI outage plan | GEN | GEN | 5D | 2025-07-07 | 2025-07-12
KILROOT |  | surge arrestor unit 1 | MAINT | 275 | 5d | 2025-07-14 | 2025-09-12
KILROOT |  | KILROOT GENERATOR T1 (LINES) - PLANT MAINT. GJ23,GJ26,GJ31, CVT & CSE's | MAINT | 275 | 5D | 2025-07-14 | 2025-09-12
KILROOT |  | GT1 OUTAGE | GEN | GEN | 60D | 2025-07-14 | 2025-09-12
LISNABREENY BATT |  | CABLE CHARACTERISTICS TESTS AND CT/CVT MAINT | MAINT | 110 | 4D | 2025-07-15
LISNABREENY BATTERY STORAGE |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | tbc | 2025-07-15
TAMNAMORE |  | REACTOR 2 remove earthing tx busbars and change to flexibles | PROJ | 110 | 2d | 2025-07-15 | 2025-07-16
SLIEVEKIRK | KILLYMALAGHT | SSE OUTAGE | MAINT | 110 | 2D | 2025-07-16
SLIEVEKIRK WINDFARM |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | tbc | 2025-07-16
HANNAHSTOWN |  | IBTX2 MINOR | MAINT | 275 | 3W | 2025-07-16 | 2025-08-01
STRABANE |  | 5S0 REPLACEMENT AND CPS B CVT | PROJ | 110 | 7WKS | 2025-07-16 | 2025-08-30
STRABANE | COOLKEERAGH 'B' | OHL WORKS | OHL | 110 | 1wk | 2025-07-16 | 2025-07-25
TANDRAGEE |  | MB75 C/B REPLACEMENT BANBRIDGE 'A' | PROJ | 110 | 6WKS | 2025-07-17 | 2025-08-15
TANDRAGEE | BANBRIDGE A | OHL WORKS | OHL | 110 | 1D | 2025-07-17
CASTLEREAGH |  | IBTX1 MINOR AND ASSOC WORKS | MAINT | 275 | 5D | 2025-07-20 | 2025-07-30
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 | MAINT | 275 | 1W | 2025-07-20
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar bolts and refurbishment ( INC IBTX1) | PROJ | 275 | 10D | 2025-07-20 | 2025-07-30
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS IBTX1 BAY | PROJ | 275 | 11D | 2025-07-21 | 2025-08-03
BANBRIDGE |  | TX2 & TX4 MAJOR | MAINT | 110 | 2W | 2025-07-21
ROSEBANK |  | TX2 MINOR MAINT | MAINT | 110 | 8D | 2025-07-28 | 2025-08-08
CASTLEREAGH |  | IBTX2 MINOR | MAINT | 275 | 1W | 2025-07-30 | 2025-08-10
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar bolts and refurbishment ( INC IBTX2 ) | PROJ | 275 | 10D | 2025-07-30 | 2025-08-10
COLERAINE |  | STATCOM CONNECTION AT CAP BANK CORNER | PROJ | 110 | 2Y | 2025-08-01 | 2026-12-25
KELLS | Glengormley 'A' | cable sheath tests | MAINT | 110 | 2D | 2025-08-03
KELLS | Glengormley 'B' | cable sheath tests | MAINT | 110 | 2D | 2025-08-03
RASHARKIN |  | MU15 MAINT AN TX2 MAJOR | MAINT | 110 | 1W | 2025-08-04 | 2025-08-08
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS IBTX2 BAY | PROJ | 275 | 13D | 2025-08-04 | 2025-08-17
HANNAHSTOWN |  | GG15 MAINT | MAINT | 275 | 1W | 2025-08-04 | 2025-08-08
ENNISKILLEN |  | ISOLATORS 5P4 , 4P8 AND CX124 | MAINT | 110 | 2D | 2025-08-04 | 2025-08-08
KELLS | Glengormley 'A' | earth wire restringing | MAINT | 110 | 5wks | 2025-08-04
KELLS | Glengormley 'B' | earth wire restringing | MAINT | 110 | 5wks | 2025-08-04
KELLS |  | MF75 GLENGORMLEY B | MAINT | 110 | 1W | 2025-08-04
TAMNAMORE |  | MP15 MAINT ( DRUMKEE) | MAINT | 110 | 1W | 2025-08-04
CASTLEREAGH |  | IBTX3 MAJOR ( faulty test tap - bushing not to be changed ) | MAINT | 110 | 2w | 2025-08-10 | 2025-08-31
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar bolts and refurbishment ( INC IBTX3) | PROJ | 275 | 10D | 2025-08-10 | 2025-08-20
CASTLEREAGH |  | MC10 MAINT ROSEBANK 'A' | MAINT | 110 | 5D | 2025-08-11 | 2025-08-22
ROSEBANK |  | TX1 MAJOR MAINT | MAINT | 110 | 8D | 2025-08-11 | 2025-08-22
ENNISKILLEN |  | ISOLATORS CX121, 1P8, 2P4, EP1 AND DROMORE 'A' VT | MAINT | 110 | 1W | 2025-08-11
ENNISKILLEN | DROMORE 'A' | conductor sampling requested by Assets | OHL | 110 | 2d | 2025-08-11
TANDRAGEE |  | MB85 C/B REPLACEMENT BANBRIDGE 'B' | PROJ | 110 | 6WKS | 2025-08-18 | 2025-09-26
TANDRAGEE | BANBRIDGE B | conductor sampling requested by Assets | OHL | 110 | 1d | 2025-08-18
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar bolts and refurbishment | PROJ | 275 | 4D | 2025-08-20 | 2025-08-24
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 | MAINT | 275 | 1W | 2025-08-24
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment ( INC HAN A ) | PROJ | 275 | 7d | 2025-08-24 | 2025-08-31
HANNAHSTOWN | CASTLEREAGH A | OHL AND TOWER PAINTING | OHL | 275 | 7D | 2025-08-24 | 2025-08-31
HANNAHSTOWN | CASTLEREAGH A & B | earth wire conductor sampling dual circuit outage | OHL | 275 | 1d | 2025-08-24
BALLYLUMFORD |  | GD10 MAINT | MAINT | 275 | 5D | 2025-08-25
HANNAHSTOWN | CASTLEREAGH B | VT AND CVT MAINT | MAINT | 275 | 4D | 2025-08-31 | 2025-09-07
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment ( INC HAN B ) | PROJ | 275 | 7D | 2025-08-31 | 2025-09-07
HANNAHSTOWN | CASTLEREAGH B | OHL AND TOWER PAINTING | OHL | 275 | 7D | 2025-08-31 | 2025-09-07
COOLKEERAGH |  | 110KV CABLE REPLACMEMENT IBTX1 CABLE | PROJ | 275 | TBC | 2025-09-01
TREMOGE |  | MV40 MAINT OMAGH CIRCUIT | MAINT | 110 | 1W | 2025-09-01
TREMOGE |  | TX2 MAJOR INC SFRA AND MV15 MAINT | MAINT | 110 | 1W | 2025-09-01 | 2025-09-05
CONNOR BATT |  | PLANT MAINT | MAINT | 110 | 2D | 2025-09-01
CONNOR BATTERY STORAGE |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | TBC | 2025-09-01
KELLS | CONNOR | MF80 MAINT CONNOR CIRCUIT | MAINT | 110 | 1W | 2025-09-01 | 2025-09-05
TANDRAGEE |  | TANDRAGEE IBTX1 MINOR INC RX1 | MAINT | 275 | 1W | 2025-09-01
TANDRAGEE |  | MB40 C/B/REPLACEMENT IBTX1 CIVILS LINKED TO THIS | PROJ | 110 | 6WKS | 2025-09-01 | 2026-09-01
TANDRAGEE |  | Reactor 1 replacement | PROJ | 275 | 12M | 2025-09-01 | 2026-09-30
BALLYLUMFORD | KELLS | TOWER PAINTING & OHL WORKS | OHL | 275 | 2W | 2025-09-01 | 2025-09-14
TANDRAGEE |  | INTERBUS TRANSFORMER '1' BUND AND REMOVAL | PROJ | 275 | 12M | 2025-09-01 | 2025-09-30
BALLYMENA |  | TX2 MINOR INC BUSHING REPLACEMENT AND BUSBAR COVER REPLACEMENT | MAINT | 110 | 2W | 2025-09-01
BALLYMENA |  | TX4 MAJOR 1ST MAINTENANCE AND COOLER OIL LEAK REPAIRS | MAINT | 110 | 2W | 2025-09-01
BROCKAGHBOY WINDFARM |  | MU99 AND CT AND EM407 DUE | MAINT | 110 | 1W | 2025-09-01
BROCKAGHBOY WINDFARM |  | WINDFARM ANNUAL MAINT for Statkraft | GEN | GEN | tbc | 2025-09-01
GARVAGH |  | MZ10 MAINT BROCKAGHBOY CIRCUIT | MAINT | 110 | 1W | 2025-09-01
KELLS | BALLYMENA 'B' | POLE REPLACEMENTS WORKS | OHL | 110 | 1W | 2025-09-01
TREMOGE | OMAGH B | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION/ EARTH WIRE COMPLETION LAST SPAN OVER UNDERCOSSING | OHL | 110 | 2w | 2025-09-01
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment ( INC HAN B &KPS ) | PROJ | 275 | 10D | 2025-09-07 | 2025-09-17
BALLYCRONANMORE |  | LINE TRAP REPLACE tuning UNITS AT BYC END OF HAN CIRCUIT | PROJ | 275 | 3w | 2025-09-08 | 2025-09-26
HANNAHSTOWN |  | 275KV ISOLATORS BYC CORNER INSTALL BUSBARS FINISH CVT AND LINE TRAPS | PROJ | 275 | 2w | 2025-09-08 | 2025-09-26
EDEN |  | TX1 MAJOR AND NOISE ENCLOSURE | MAINT | 110 | 8d | 2025-09-08
EDEN |  | TX2 MAJOR AND NOISE ENCLOSURE | MAINT | 110 | 8d | 2025-09-08
STRABANE |  | 1S0 MAINT / REPLACEMENT | PROJ | 110 | 5WKS | 2025-09-08 | 2025-10-10
STRABANE |  | 2S0 raise circuit breaker and PST Line trap repair | PROJ | 110 | 8wks | 2025-09-08 | 2025-10-31
GARVAGH |  | MZ15 AND TRANSFOMER 1 MAJOR | MAINT | 110 | 1W | 2025-09-08
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 1D | 2025-09-09 | 2025-09-10
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 3D | 2025-09-10 | 2025-09-13
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS B22 BAY | PROJ | 275 | 5D | 2025-09-16 | 2025-09-23
BALLYLUMFORD | B31 | B21 OUTAGE | GEN | GEN | 4D | 2025-09-16 | 2025-09-20
BALLYLUMFORD | B32 | B22 OUTAGE | GEN | GEN | 7D | 2025-09-16 | 2025-09-23
KILROOT |  | CAS CVT AND WALL BUSHING TO BE RETESTED INCLUDE ISOLATORS | MAINT | 275 | 1W | 2025-09-17
KILROOT |  | 275kv CT BAY CASTLEREAGH ( BUS - ZONE SETS ) | PROJ | 275 | 4wks | 2025-09-17
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment ( INC KPS ) | PROJ | 275 | 11D | 2025-09-17 | 2025-09-28
KILROOT | CASTLEREAGH | OHL AND TOWER PAINTING | OHL | 275 | 2W | 2025-09-17 | 2025-09-28
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS B21 BAY | PROJ | 275 | 2W | 2025-09-20 | 2025-09-30
BALLYLUMFORD | B31 | B21 OUTAGE | GEN | GEN | 10D | 2025-09-20 | 2025-09-30
KILROOT |  | surge arrestor unit 2 | MAINT | 275 | 5d | 2025-09-22 | 2025-11-21
KILROOT |  | KILROOT GENERATOR T2 (LINES) - PLANT MAINT. CVT & CSE's maint | MAINT | 275 | 5D | 2025-09-22 | 2025-11-21
KILROOT |  | GT2 OUTAGE | GEN | GEN | 60D | 2025-09-22 | 2025-11-21
KILROOT |  | sheath test cvt unit tx unit. | MAINT | 275 | 5D | 2025-09-22 | 2025-11-21
BALLYLUMFORD | B32 | B32 OUTAGE | GEN | GEN | 4D | 2025-09-23 | 2025-09-27
BALLYLUMFORD | B32 | B32 OUTAGE | GEN | GEN | 3D | 2025-09-27 | 2025-09-30
TANDRAGEE |  | GB105 MAINT | MAINT | 275 | 1W | 2025-09-28 | 2025-10-05
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment ( INC TAN ) | PROJ | 275 | 10D | 2025-09-28 | 2025-10-05
CASTLEREAGH | TANDRAGEE | OHL AND TOWER PAINTING | OHL | 275 | 10d | 2025-09-28 | 2025-10-05
TANDRAGEE |  | MB45 C/B REPLACEMENT WAR 'B' CCT | PROJ | 110 | 6WKS | 2025-09-29 | 2025-11-07
OMAGH | TREMOGE | TREMOGE CVT 4M8,5M4,CX54 AND SHEATH TEST | MAINT | 110 | 4D | 2025-10-01
CASTLEREAGH |  | IBTX4 MINOR | MAINT | 275 | 1w | 2025-10-01
CREGAGH |  | TX A TAP CHANGE CONTROL AND TX PROTECTION move existing protection | PROJ | 110 | 2wks | 2025-10-01
CREGAGH |  | TX B TAP CHANGE CONTROL AND TX PROTECTION move existing protection | PROJ | 110 | 2wks | 2025-10-01
CASTLEREAGH | KNOCK B | MOVE KNOCK B BAY MC70 TO MC40 FACILITATE IBTX4 | PROJ | 110 | 6WKS | 2025-10-01
TREMOGE | OMAGH B | prep works and measurements for diversion | OHL | 110 | 2d | 2025-10-01
CASTLEREAGH |  | CASTLEREAGH MCXX CIRCUIT BREAKER complete REPLACEMENT | PROJ | 110 | 6WKS | 2025-10-01
CASTLEREAGH |  | Earth switch installation mutliple bays | PROJ | 110 |  | 2025-10-01
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - BUS SECTION ISOLATORS A1 -A3 | PROJ | 275 | 5D | 2025-10-01 | 2025-10-07
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar bolts and refurbishment. | PROJ | 275 | 7D | 2025-10-05 | 2025-10-12
CASTLEREAGH | TANDRAGEE | GC70/GC75 PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 1w | 2025-10-06 | 2025-10-10
TAMNAMORE |  | INTERBUS 1 MAJOR AND GP15 & Reactor | MAINT | 275 | 3W | 2025-10-06
BALLYLUMFORD |  | BGT1 OUTAGE | GEN | GEN | 6D | 2025-10-07 | 2025-10-13
BALLYLUMFORD | KELLS | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS KELLS BAY | PROJ | 275 | 13D | 2025-10-13 | 2025-10-24
TAMNAMORE |  | INTERBUS 2 MINOR | MAINT | 275 | 1W | 2025-10-13
TAMNAMORE |  | REACTOR 2 INSTALLATION offline | PROJ | 110 | 3M | 2025-10-13 | 2026-01-30
BALLYLUMFORD | B10 | B10 GENERATOR OUTAGE | GEN | GEN | 4D | 2025-10-24 | 2025-04-28
KELLS |  | NEW CLUSTER CONNECTION ( KELLS EAST MAIN HVC ?????) | PROJ | 110 | 5WKS | 2025-11-01 | 2025-12-24
STRABANE | killymalaght | POLE REPLACEMENTS WORKS | OHL | 110 | 1D | 2025-11-24
DONEGALL |  | TX 'B' REPLACEMENT WITH NEW 33BOARD (PROJECTS ) - INSTALL TX B FROM POWERSTATION WEST?? | PROJ | 110 | 10WKS | 2025-12-01
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 2D | 2025-12-16 | 2025-12-18