## TOP 2026
SUB 1 | SUB 2 | Task Name | TYPE | kV | Duration | Start | Finish
BALLYLUMFORD |  | GD20 CONTROL PANEL WORKS | PROJ | 275 | 1w | 2026-01-05 | 2026-01-09
AGHYOULE |  | FLOOD REPAIRS WORKS | MAINT | 110 | TBC | 2026-01-06
TAMNAMORE |  | REACTOR 2 INSTALLATION offline | PROJ | 110 | 3M | 2026-01-06 | 2026-03-30
DUNGANNON | TAMNAMORE 'C' | D/C TOWER T614 CSE cleaning | OHL | 110 | 1D | 2026-01-07
LIMAVADY |  | 53v0 ct checks AOR 2024/28 | maint | 110 | 1d | 2026-01-07
COOLKEERAGH | MAGHERAFELT A | line characteristics tests | MAINT | 275 | 1d | 2026-01-07
COOLKEERAGH | MAGHERAFELT B | line characteristics tests | MAINT | 275 | 1d | 2026-01-07
BALLYLUMFORD |  | BGT2 OUTAGE | GEN | GEN | 1D | 2026-01-08
BALLYLUMFORD |  | repair water washing equipment | PROJ | 275 | TBC | 2026-01-08
LIMAVADY |  | 54v0 ct checks AOR 2024/28 | maint | 110 | 1d | 2026-01-08
KELLS | Glengormley 'B' | remove spare bay isolator beside Glen B MF70. MF71 | PROJ | 110 | 1d | 2026-01-08
LIMAVADY |  | 52v0 ct checks AOR 2024/28 | maint | 110 | 1d | 2026-01-09
KELLS | Glengormley 'B' | remove spare bay isolator beside Glen B MF70. MF68 | PROJ | 110 | 1d | 2026-01-09
BALLYLUMFORD | magherafelt | repair lights above the Mag circuit at Ballylumford | MAINT | 275 | 3D | 2026-01-10
BALLYLUMFORD | MAGHERAFELT | ISOL GD66, GD68 MTCE + proximity outage for station lighting | PROJ | 275 | 4D | 2026-01-10 | 2025-12-23
MAGHERAFELT |  | GH13 - SECTION 'A1' ISOLATOR refurb | MAINT | 275 | 4D | 2026-01-10 | 2025-12-23
LIMAVADY |  | 51v0 ct checks AOR 2024/28 | maint | 110 | 1d | 2026-01-10
CASTLEREAGH | KNOCK A | SECTION 1L ISOLATOR PLUS NEWTOWNARDS A CCT, MC41 | PROJ | 110 | 3D | 2026-01-11 | 2026-01-14
BALLYLUMFORD |  | GD70 MAINT pipe work for water washing, and lighting | MAINT | 110 | 4d | 2026-01-12
OMAGH | DUNGANNON A | CVT MAINT | MAINT | 110 | 2D | 2026-01-12 | 2026-01-13
STRABANE |  | TX1 MAJOR INC SFRA | MAINT | 110 | 8D | 2026-01-12 | 2026-03-06
STRABANE |  | 1S0 busbar removal to 1s4 | PROJ | 110 | 1d | 2026-01-12
STRABANE |  | 1S0 MAINT / REPLACEMENT | PROJ | 110 | 5WKS | 2026-01-12 | 2026-03-06
STRABANE |  | PST BAY MAINTENANCE WORKS , RAISE CTS AND 2S0 | MAINT | 110 | 8WKS | 2026-01-12 | 2026-03-06
STRABANE |  | 2S0 AND CT RAISE WORKS PST | PROJ | 110 | 8WKS | 2026-01-12 | 2026-03-06
STRABANE | LETTERKENNY | TOWER PAINTING | OHL | 110 | 5D | 2026-01-12
BALLYLUMFORD |  | MD35 MAINT GT2 Sheath | MAINT | 110 | 7D | 2026-01-12 | 2026-01-18
LARNE |  | TOWER WORKS TO BUILD NEW CABLE PLATFORM OFFLINE | OHL | 110 | N/A | 2026-01-12 | 2026-02-27
LETTERKENNY | STRABANE | ESB WORKS AT LETTERKENNY | ESB | 110 | 2WKS | 2026-01-12 | 2026-02-15
KELLS | MAGHERAFELT | T928 BROKEN DISHES AND TOWER PAINTING | OHL | 275 | 3D | 2026-01-14
CASTLEREAGH | KNOCK A | SECTION 2L ISOLATOR, PLUS NEWTOWNARDS A CCT. MC38 | PROJ | 110 | 3D | 2026-01-14 | 2026-01-16
DUNGANNON |  | CVT MAINT MESH CORNER 7 | MAINT | 110 | 2D | 2026-01-19 | 2026-01-20
OMAGH |  | 2M0 MAINT | MAINT | 110 | 2D | 2026-01-19 | 2026-01-20
BANBRIDGE |  | TX2 & 4 TCHANGER INDICAITION BOX AND LNER, ISOLATORS | MAINT | 110 | 1D | 2026-01-19
TAMNAMORE |  | GP45 MAINT BUS-COUPLER | MAINT | 275 | 1W | 2026-01-19
BANBRIDGE |  | TX1 & 3 TCHANGER INDICATION BOX AND LNER ISOLATORS | MAINT | 110 | 1D | 2026-01-21
BALLYLUMFORD | B32 | B32 OUTAGE | GEN | GEN | 5D | 2026-01-21 | 2026-01-25
BALLYLUMFORD | BALLYCRONANMORE | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS GD10 | PROJ | 275 | 2w | 2026-01-26 | 2026-02-06
CARNMONEY |  | CAS B CVT AND ISOLATORS | MAINT | 110 | 5D | 2026-01-26 | 2026-01-30
CASTLEREAGH |  | MC15 MAINT CARNMONEY 'B' | MAINT | 110 | 5D | 2026-01-26 | 2026-01-30
OMAGH |  | 6M0 SF6 leak investigation | MAINT | 110 | 1D | 2026-01-26 | 2026-01-27
OMAGH |  | 6MO MAINT | MAINT | 110 | 2D | 2026-01-26 | 2026-01-27
DRUMNAKELLY |  | CVT MAINT | MAINT | 110 | 2D | 2026-01-26 | 2026-01-27
COOLKEERAGH |  | GA65 bay stage 1 | PROJ |  | 20d | 2026-01-26 | 2026-02-20
DRUMNAKELLY |  | 5K8,6K4,CX44, AND EK5 | MAINT | 110 | 2D | 2026-01-28 | 2026-01-30
KELLS |  | NEW CLUSTER CONNECTION isolators | PROJ | 110 | 1WK | 2026-01-28
KELLS |  | MF20, Ballymena 'B', Sect 2L busbar - proximity for NEW CLUSTER CONNECTION ( KELLS EAST MAIN HVC ?????) | PROJ | 110 | 1WK | 2026-01-28
CASTLEREAGH | KNOCK A | NEW KNOCK A??? MC40 BAY SO KNOCK A CAN BE USED FOR IBTX4 | PROJ | 110 | 6WKS | 2026-01-29 | 2026-02-28
CASTLEREAGH | KNOCK A | MOVE KNOCK A? BAY MC80 TO MC40 FACILITATE IBTX4 | PROJ | 110 | 6WKS | 2026-01-29 | 2026-02-27
CASTLEREAGH |  | MC80 MAINT KNOCK 'A' | MAINT | 110 | 5D | 2026-01-30
CASTLEREAGH |  | HANNAHSTOWN A CVT MAINT | MAINT | 275 | 3D | 2026-02-02 | 2026-02-04
OMAGH | GORT | OHL NOISE COMPLAINT Arcing of bottom insulator on middle phase on pole MDH15- all insulators are intact | OHL | 110 | 1D | 2026-02-02
COLERAINE |  | 3L0 MAINT AND SF6 CHECK | MAINT | 110 | 1w | 2026-02-02 | 2026-02-03
DUNGANNON |  | 4J0 MAINT | MAINT | 110 | 2D | 2026-02-02 | 2026-02-03
MAGHERAFELT |  | CIRCUIT BREAKER FAILS SCHEME ( 7 SETS ) | PROJ | 275 | 1M | 2026-02-02 | 2026-03-30
ROSEBANK |  | DOUBLE CIRCUIT OUTAGE TO ALLOW FOR 33KV BELFAST EAST MAIN | PROJ | 110 | 1W | 2026-02-02
CASTLEREAGH |  | TANDRAGEE VT | MAINT | 275 | 3D | 2026-02-04 | 2026-02-06
COLERAINE |  | 4L0 MAINT sf6 investigation | MAINT | 110 | 1d | 2026-02-04 | 2026-02-05
BALLYLUMFORD |  | GD40 MAINT | MAINT | 275 | 5d | 2026-02-09 | 2026-02-13
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS GD40 | PROJ | 275 | 6M | 2026-02-09 | 2026-02-13
ENNISKILLEN |  | 6P0 MAINT | MAINT | 110 | 2D | 2026-02-09
COLERAINE |  | 5L0 MAINT | MAINT | 110 | 2d | 2026-02-09 | 2026-02-10
DUNGANNON |  | 2J0 MAINT | MAINT | 110 | 2D | 2026-02-09 | 2026-02-10
CASTLEREAGH | NEWTOWNARDS 'A' | REPLACE POLE 271 DUE TO DAMAGE BY HEDGECUTTER | OHL | 110 | 2D | 2026-02-09
ENNISKILLEN |  | 5P0 MAINT | MAINT | 110 | 2D | 2026-02-11
CASTLEREAGH |  | GC15 MAINT | MAINT | 275 | 4D | 2026-02-16 | 2026-02-19
ENNISKILLEN |  | 3P0 MAINT | MAINT | 110 | 2D | 2026-02-16
COLERAINE | RASHARKIN | POLE REPLACEMENTS WORKS | OHL | 110 | 3D | 2026-02-16
BALLYVALLAGH |  | ME30 BAY MAINT BPS B CIRCUIT | MAINT | 110 | 5D | 2026-02-16 | 2026-02-20
DUNGANNON |  | 1J0 MAINT | MAINT | 110 | 2D | 2026-02-16 | 2026-02-17
BALLYVALLAGH |  | SECTION 1 BUSBAR | MAINT | 110 | 1W | 2026-02-16
BALLYVALLAGH |  | SECTION 2 BUSBAR | MAINT | 110 | 1W | 2026-02-16
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT G4 | PROJ | 275 | 1w | 2026-02-16 | 2026-02-20
DRUMNAKELLY |  | 1K4, 8K8 AND CX47 | MAINT | 110 | 2D | 2026-02-17 | 2026-02-19
COOLKEERAGH | MAGHERAFELT A | GA35 MAINT + GA33 ( Section A1 Busbar ) | MAINT | 275 | 1w | 2026-02-23 | 2026-02-27
MAGHERAFELT | COOLKEERAGH A | GH35 MAINT | MAINT | 275 | 1W | 2026-02-23 | 2026-02-27
BALLYLUMFORD |  | IBTX1 MINOR | MAINT | 275 | 2w | 2026-02-23 | 2026-03-06
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS IBTX1 | PROJ | 275 | 2w | 2026-02-23 | 2026-03-06
BALLYVALLAGH |  | ME40 BAY MAINT BPS A CIRCUIT | MAINT | 110 | 5D | 2026-02-23 | 2026-02-27
DRUMNAKELLY |  | 3K8,4K4,CX42 AND EK3 | MAINT | 110 | 2D | 2026-02-24 | 2026-02-25
KILROOT |  | GT1 OUTAGE | GEN | GEN | 1d | 2026-02-26
CASTLEREAGH |  | IBTX 4 INSTALLATION INC 275KV DIAGONAL AND 110KV CABLES | PROJ | 275 | 6M | 2026-03-01 | 2026-08-28
CASTLEREAGH |  | IBTX4 MINOR | MAINT | 275 | 1w | 2026-03-01
KILROOT |  | KILROOT GENERATOR T1 (LINES) - PLANT MAINT. GJ23,GJ26,GJ31, CVT & CSE's | MAINT | 275 | 5 days | 2026-03-01
KILROOT |  | GT1 OUTAGE TO REPLACE SURGE ARRESTOR | GEN | GEN | 2W | 2026-03-01
KILROOT |  | GT1 OUTAGE | GEN | GEN | 28d | 2026-03-01 | 2026-03-28
KILROOT |  | KILROOT GENERATOR T1 (LINES) - PLANT MAINT. GJ23,GJ26,GJ31, CVT & CSE's | MAINT | 275 | 5d | 2026-03-01
CASTLEREAGH |  | NEW MC80 BAY TO FACILITATE BUILD IBTX4 | PROJ | 110 | 5WKS | 2026-03-01
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar CIVIL WORKS | PROJ | 275 | 2W | 2026-03-02 | 2026-03-13
HANNAHSTOWN | LISBURN B | tower painting | OHL | 110 | 3d | 2026-03-02 | 2026-03-06
HANNAHSTOWN |  | MG45 BAY MAINT | MAINT | 110 | 5D | 2026-03-02 | 2026-03-08
LISBURN MAIN | HANNAHSTOWN B | CVT MAINT | MAINT | 110 | 2D | 2026-03-02
DUNGANNON |  | 5J0 MAINT | MAINT | 110 | 2D | 2026-03-02 | 2026-02-03
MAGHERAFELT |  | (CONTROL PANEL REFURBISHMENT) - CBF AND MIMIC BOARD WORKS | PROJ | 275 | 6M | 2026-03-02
HANNAHSTOWN | LISBURN A | POLE REPLACEMENTS WORKS | OHL | 110 | 1W | 2026-03-09
HANNAHSTOWN | LISBURN A | tower painting | OHL | 110 | 1W | 2026-03-09 | 2026-03-13
HANNAHSTOWN | LISBURN A | MG25 MAINT | MAINT | 110 | 1W | 2026-03-09 | 2026-03-15
LISBURN MAIN | HANNAHSTOWN A | CVT MAINT | MAINT | 110 | 2D | 2026-03-09
DUNGANNON |  | 8J0 MAINT | MAINT | 110 | 2D | 2026-03-09 | 2026-03-10
GORT | TAMNAMORE | MT10 MAINT TAM CCT | MAINT | 110 | 5D | 2026-03-09 | 2026-03-13
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS G3 | PROJ | 275 | 1W | 2026-03-09 | 2026-03-13
LIMAVADY | COLERAINE | CVT MAINT AND MESH CORNER ISOLATORS | MAINT | 110 | 3d | 2026-03-11 | 2026-03-13
CREAGH |  | MAINT WORKS em170 | MAINT | 110 | 2d | 2026-03-11 | 2026-03-12
TAMNAMORE |  | REACTOR 2 MATCHING SHOTS AND ETX BUSBAR REINSTALL | PROJ | 110 | 2W | 2026-03-12 | 2026-03-30
HANNAHSTOWN | BALLYLUMFORD B | line characteristics AND CORONA RINGS TO BE FITTED OLD IBTX1 BUSBAR SUPPORT | PROJ | 275 | 2D | 2026-03-17
COOLKEERAGH |  | LOADSHEDDING (RUNBACK SCHEME) - 3 LOADSHEDDING RELAYS | PROJ | 275 | 1d | 2026-03-17
MAGHERAFELT |  | RUNBACK SCHEME TESTING AND COMMISSIONING | PROJ | 275 | 1D | 2026-03-17
LISBURN MAIN |  | HAN B CVT | MAINT | 110 | 2D | 2026-03-17 | 2025-12-12
DRUMNAKELLY | TAMNAMORE 'A' CIRCUIT | VT DUE | MAINT | 110 | 2D | 2026-03-17 | 2025-12-16
LISBURN MAIN |  | HAN A CVT | MAINT | 110 | 2D | 2026-03-17 | 2025-12-19
KELLS |  | GF114 & maintenance earth sw refurb ( Kilroot A circuit ) | MAINT | 275 | 4D | 2026-03-17
OMAGH | STRABANE A | 9M8,10M4 AND CX59 INC ESW | MAINT | 110 | 2D | 2026-03-18 | 2026-03-19
COOLKEERAGH | MAGHERAFELT b | GA55 MAINT | MAINT | 275 | 1w | 2026-03-18 | 2026-03-28
COOLKEERAGH | MAGHERAFELT B | B CIRCUIT OUTAGE NOISE SUPPRESSION | OHL | 275 | 2W | 2026-03-18
COOLKEERAGH | MAGHERAFELT B | STATKRAFT CONNECTION REQUIRES IBTX2 AND MAG B CIRCUIT OUT FOR DURATION | PROJ | 275 | 6M | 2026-03-18 | 2026-09-18
MAGHERAFELT | COOLKEERAGH B | GH45 MAINT | MAINT | 275 | 1WK | 2026-03-18
KILROOT |  | GT6 OUTAGE | GEN | 275 | 3D | 2026-03-18 | 2026-03-20
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar CIVIL WORKS | PROJ | 275 | 2W | 2026-03-18 | 2026-04-03
STRABANE |  | 7S0 TRAVEL CURVE / CHECK CIRCUIT BREAKER | PROJ | 110 | 2D | 2026-03-18 | 2026-03-19
CREAGH |  | MAINT WORKS MN16,MN19,MN24,EM185 | MAINT | 110 | 2d | 2026-03-18 | 2026-03-19
COOLKEERAGH | Magherafelt B | GA65 bay stage 2 | PROJ |  | 9d | 2026-03-18 | 2026-03-28
OMAGH | STRABANE 'B' | 7M8, 8M4 AND CX57 MAINT INC ESW | MAINT | 110 | 2D | 2026-03-19 | 2026-03-21
STRABANE |  | 8S0 TRAVEL CURVE / CHECK CIRCUIT BREAKER | PROJ | 110 | 2D | 2026-03-19 | 2026-03-20
NEWRY |  | CX191 AND EN1 MAINT | MAINT | 110 | 2D | 2026-03-19 | 2026-03-20
CREAGH |  | MN5 ISOLATORS MN6,EM173 | maint | 110 | 2d | 2026-03-19 | 2026-03-20
COOLKEERAGH |  | COOLKEERAGH GA65 BAY - (Statkraft) concrete struture removal including MAG B & IBTX2 proximity | MAINT | 275 | 6M | 2026-03-19
COOLKEERAGH | killymalaght | POLE REPLACEMENTS ON POLE 277 | OHL | 110 | tbc | 2026-03-23
COOLKEERAGH | killymalaght | tower painting | OHL | 110 | 1w | 2026-03-23 | 2026-03-27
LISBURN MAIN | TANDRAGEE B | CVT AND ISOLATORS | MAINT | 110 | 3D | 2026-03-23
TANDRAGEE | LISBURN B | TOWER PAINTING | OHL | 110 | 1W | 2026-03-23
TANDRAGEE |  | MB55 LISBURN B CIRCUIT BREAKER REPALCEMENT | PROJ | 110 | 6WKS | 2026-03-23 | 2026-05-01
DONEGALL |  | transformer D oil level guage | MAINT | 110 | 2D | 2026-03-23
DONEGALL |  | TX D MAJOR MAINT | MAINT | 110 | 2W | 2026-03-23
FINAGHY | DONEGALL B | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1D | 2026-03-23
FINAGHY | DONEGALL B | Castell repairs on Power isolators | MAINT | 110 | 1D | 2026-03-23 | 2026-04-03
FINAGHY |  | TX2 MAJOR & isol defects | MAINT |  | 2w | 2026-03-23 | 2026-04-03
HANNAHSTOWN | FINAGHY A | MG15 MAINT | MAINT | 110 | 5D | 2026-03-23 | 2026-04-03
GORT |  | TX2 & TX1 protection works to allow energising both. | PROJ | 110 | 2D | 2026-03-23
GORT |  | TX2 MAJOR AND SFRA AND MT15 | MAINT | 110 | 2W | 2026-03-23 | 2026-04-03
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS G6 | PROJ | 275 | 1W | 2026-03-23 | 2026-03-27
KILROOT |  | GT7 OUTAGE | GEN | 275 | 3D | 2026-03-23 | 2026-03-25
OMAGH | DROMORE 'A' | TOWER PLATFORM REPAIRS | MAINT | 110 | 1D | 2026-03-24
OMAGH | DROMORE 'B' | CVT MAINT | MAINT | 110 | 2D | 2026-03-26
RASHARKIN |  | EARTHING COURSE. | MAINT | 110 | 2d | 2026-03-27
COOLKEERAGH |  | GA65 bay stage 3 | PROJ |  | 15d | 2026-03-30 | 2026-04-17
BALLYLUMFORD |  | IBTX2 MINOR ( Major complete 2024) | MAINT | 275 | 1w | 2026-03-30 | 2026-04-03
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS IBTX 2 | PROJ | 275 | 1W | 2026-03-30 | 2026-04-03
CASTLEREAGH | KNOCK A | MOVE KNOCK A BUILD NEW BAY MC80 OFFLINE DURING MARCH AND CONNECTION WORKS END MARCH | PROJ | 110 | 6WKS | 2026-03-30 | 2026-04-30
ENNISKILLEN |  | tower '3' weeding | MAINT | 110 | 1d | 2026-03-30
KELLS |  | NEW CLUSTER CONNECTION ( KELLS EAST MAIN HVC ?????) | PROJ | 110 | 1WK | 2026-04-01
KELLS |  | 110KV GROUP ALARMS T602M | PROJ | 110 | 3D | 2026-04-01 | 2026-04-03
BALLYVALLAGH | LARNE | A & B CIRCUIT DUALT OUTAGE FOR CABLE ON TERMINAL TOWER | PROJ | 110 | TBC | 2026-04-06 | 2026-05-29
CASTLEREAGH |  | IBTX1 MAJOR AND ASSOC WORKS | MAINT | 275 | 5D | 2026-04-08 | 2026-04-19
HANNAHSTOWN |  | IBTX2 MAJOR & MG55 BAY | MAINT | 275 | 13D | 2026-04-08 | 2026-04-24
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar STRUCTURES IBTX1 | PROJ | 275 | 11D | 2026-04-08 | 2026-04-19
CREAGH |  | TX1 MINOR INC TC FLUSH AND MN10 | MAINT | 110 | 2W | 2026-04-08 | 2026-04-19
CASTLEREAGH |  | MC65 MAINT RATHGAEL 'A' breaker replacements | PROJ | 110 | 5wks | 2026-04-08 | 2026-05-22
RATHGAEL |  | TX1 33KV CABLES REPLACEMENT WORKS | PROJ | 110 | 6WKS | 2026-04-08 | 2026-05-22
RATHGAEL |  | TX 1 MAJOR MAINT INC SFRA, COOLER REPLACEMENTS AND CONTROL GEAR | PROJ | 110 | 6WKS | 2026-04-08 | 2025-05-22
DUNGANNON |  | CVT MAINT TAMNAMORE 'A' | MAINT | 110 | 2D | 2026-04-08 | 2026-04-10
BALLYLUMFORD |  | BALLYLUMFORD 110KV ISOLATORS OPERATION CHECKS | MAINT | 110 | TBC | 2026-04-08
CASTLEREAGH |  | NEW 275KV busbars section A1 | PROJ | 275 | 2M | 2026-04-08 | 2026-05-29
BALLYLUMFORD | B31 | B21 OUTAGE | GEN | GEN | 15D | 2026-04-11 | 2026-04-26
COOLKEERAGH | strabane | tower painting | OHL | 110 | 1D | 2026-04-13
COOLKEERAGH | STRABANE B | 4H0 MAINT | MAINT | 110 | 4D | 2026-04-13
STRABANE | COOLKEERAGH 'B' | OHL WORKS | OHL | 110 | 2D | 2026-04-13
STRABANE | killymalaght | tower painting | OHL | 110 | 3d | 2026-04-13
KELLS | ANTIRM A | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1D | 2026-04-13
KELLS |  | MF50 MAINT ANTRIM A CIRCUIT | MAINT | 110 | 1WK | 2026-04-13 | 2026-04-17
DONEGALL |  | TX A MAINT INC TC FLUSH | MAINT | 110 | 2W | 2026-04-13
FINAGHY | DONEGALL A | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1D | 2026-04-13
FINAGHY | DONEGALL A | Castell repairs on Power isolators | MAINT | 110 | 1D | 2026-04-13 | 2026-04-24
FINAGHY |  | TX1 MAJOR & isol defects | MAINT |  | 2w | 2026-04-13 | 2026-04-24
HANNAHSTOWN | FINAGHY B | MG39, EM159 AND EM159B MAINT | MAINT | 110 | 2D | 2026-04-13
CASTLEREAGH |  | MC30 MAINT LISNABREENY CCT AOR CLEARANCE WORKS | MAINT | 110 | 5D | 2026-04-13 | 2026-04-17
LISNABREENY BATTERY STORAGE |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | 1d | 2026-04-13
BALLYLUMFORD |  | B20 outage requested on 3/3/25 | GEN | 275 | TBC | 2026-04-13
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS B20, B21 & B22 | PROJ | 275 | 1W | 2026-04-13 | 2026-04-24
BALLYLUMFORD | B32 | B22 OUTAGE | GEN | GEN | 13D | 2026-04-13 | 2026-04-26
CASTLEREAGH |  | IBTX2 MAJOR + MC75 + 275kV isolator REFURB GC51, GC46, GC43 | MAINT | 275 | 3W | 2026-04-19
CASTLEREAGH |  | IBTX2 MINOR ( MAJOR COMPLETE 2025 MAYBE???) | MAINT | 275 | 2W | 2026-04-19 | 2026-05-06
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar STRUCTURES IBTX2 | PROJ | 275 | 18D | 2026-04-19 | 2026-05-06
COOLKEERAGH |  | GA65 bay stage 4 | PROJ |  | 19d | 2026-04-20 | 2026-05-14
CREAGH |  | TX2 MINOR INC TX FLUSH AND MN20 | MAINT | 110 | 2W | 2026-04-20 | 2026-05-01
HANNAHSTOWN |  | Reactor 3 wti measurements AND REPAIRS | MAINT | 275 | 5D | 2026-04-27
HANNAHSTOWN |  | IBTX3 MINOR | MAINT | 275 | 4d | 2026-04-27 | 2026-05-01
CASTLEREAGH |  | GC35 MAINT | MAINT | 275 | 4D | 2026-04-27 | 2026-05-01
BALLYLUMFORD |  | MD50 MAINT | MAINT | 110 | 5D | 2026-04-27 | 2026-05-01
KILROOT |  | NIK GT3 | GEN | GEN | 1D | 2026-04-28
DUNGANNON |  | CVT MAINT TAMNAMORE ''B' | MAINT | 110 | 2D | 2026-04-30 | 2026-05-01
KILROOT |  | kilroot fire alarm tests | MAINT | 275 | 5D | 2026-05-01
HANNAHSTOWN |  | IBTX3 PAINTING | PROJ | 275 | 3W | 2026-05-01 | 2026-05-22
KILROOT |  | NIK GT3 | GEN | GEN | 1D | 2026-05-01
KILROOT |  | NIKGT4 | GEN | GEN | 1D | 2026-05-02
KILROOT |  | NIK GT3 | GEN | GEN | 30D | 2026-05-03 | 2026-05-30
KILROOT |  | NIKGT4 | GEN | GEN | 30D | 2026-05-03 | 2026-05-30
KILROOT |  | GT1 OUTAGE | GEN | GEN | 6d | 2026-05-04 | 2026-05-09
KILROOT |  | KILROOT GENERATOR T2 (LINES) - PLANT MAINT. CVT & CSE's maint | MAINT | 275 | 5 days | 2026-05-04
KILROOT |  | GT2 OUTAGE | GEN | GEN | 6D | 2026-05-04 | 2026-05-09
ENNISKILLEN | Corraclassy | ESB works at corraclassy and on OHL | ESB | 110 | TBC | 2026-05-05
ENNISKILLEN |  | PST MAINTENANCE AND 7P0 CIRCUIT BREAKER LEAK REPAIRS | MAINT | 110 | TBC | 2026-05-05 | 2026-05-29
ENNISKILLEN |  | PST overhaul , bay maint & RAISE CVT / SURGE ARRESTOR STANDS | PROJ | 110 | 4w | 2026-05-05 | 2026-05-29
ENNISKILLEN | Corraclassy | POLE REPLACEMENTS | OHL | 110 | 2W | 2026-05-05 | 2026-05-15
COOLKEERAGH | COLERAINE | OHL Pole changes ( including TOWER PAINTING ) | OHL | 110 | 4W | 2026-05-05 | 2026-05-29
LISBURN MAIN | TANDRAGEE A | CVT AND ISOLATORS | MAINT | 110 | 3D | 2026-05-05
TANDRAGEE | LISBURN A | TOWER PAINTING | OHL | 110 | 1W | 2026-05-05
TANDRAGEE |  | MB65 LISBURN A CIRCUIT BREAKER REPALCEMENT | PROJ | 110 | 6WKS | 2026-05-05 | 2026-06-12
OMAGH |  | TX1 MINOR INC T/C FLUSH AND PAINTING | PROJ | 110 | 3W | 2026-05-05 | 2026-05-22
CASTLEREAGH |  | IBTX3 MINOR ( faulty test tap - bushing not to be changed ) | MAINT | 110 | 4D | 2026-05-06 | 2026-05-13
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar STRUCTURES IBTX3 | PROJ | 275 | 8D | 2026-05-06 | 2026-05-13
EDEN |  | TX1 NOISE ENCLOSURE & gcb SF6 LEAK DETECTION, 33KV CABLING TO NEW BOARD | MAINT | 110 | TBC | 2026-05-06
COLERAINE | COOLKEERAGH | 4L8, 5L4, CX94 AND CABLE SEALING ENDS AND CVT | MAINT | 110 | 3D | 2026-05-11 | 2026-05-15
KILLYMALAGHT |  | MR20 AND TX1 MAJOR ( FLUSH) | MAINT | 110 | 5d | 2026-05-11 | 2026-05-15
BALLYLUMFORD | B10 | B10 GENERATOR OUTAGE | GEN | GEN | 13D | 2026-05-11 | 2026-05-24
TREMOGE |  | SECTION 1 BUSBAR | MAINT | 110 | 1W | 2026-05-12
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 B/Bar STRUCTURES FINISHING WORKS | PROJ | 275 | 2M | 2026-05-13 | 2026-05-29
TREMOGE |  | SECTION 2 BUSBAR | MAINT | 110 | 1W | 2026-05-13
COOLKEERAGH | magherafelt B | GA65 bay stage 5 | PROJ |  | 7d | 2026-05-15 | 2026-05-24
KILLYMALAGHT |  | MR5 MAINT | MAINT | 110 | 4d | 2026-05-18 | 2026-05-22
KILLYMALAGHT |  | MR25 MAINT BUS-SECTION | MAINT | 110 | 4d | 2026-05-18 | 2026-05-22
SLIEVEKIRK | KILLYMALAGHT | SSE OUTAGE | MAINT | 110 | 2D | 2026-05-18
SLIEVEKIRK WINDFARM |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | 1w | 2026-05-18
COOLKEERAGH |  | 10H0 MAINT GT8 BAY | MAINT | 110 | 5D | 2026-05-18
COOLKEERAGH |  | GT8 OUTAGE - break bars at TX | GEN | GEN | 5D | 2026-05-18 | 2026-05-23
DRUMNAKELLY |  | 6K8,7K4 AND CX45 | MAINT | 110 | 3D | 2026-05-19 | 2026-05-22
DRUMNAKELLY |  | 6K0 MAINT ( NEEDS TX PROXIMITY) | MAINT | 110 | 4D | 2026-05-19 | 2026-05-22
RASHARKIN |  | MU5 MAINT BUS-COUPLER | MAINT | 110 | 1W | 2026-05-23 | 2026-03-27
COOLKEERAGH |  | GA65 bay stage 6 | PROJ |  | 18d | 2026-05-25 | 2026-06-17
COOLKEERAGH | COLERAINE | 2H0 MAINT | MAINT | 110 | 4D | 2026-05-25 | 2026-05-29
CASTLEREAGH |  | MC75 MAINT RATHGAEL B breaker replacement | PROJ | 110 | 5WKS | 2026-05-25 | 2026-06-26
CASTLEREAGH | RATHGAEL 'B' | RESTRING OF OHL CONDUCTORS | OHL | 110 | 3W | 2026-05-25 | 2026-06-12
RATHGAEL |  | TX2 33KV CABLES REPLACEMENT WORKS | PROJ | 110 | 6WKS | 2026-05-25 | 2026-06-26
HANNAHSTOWN |  | IBTX4 MINOR & REACTOR works | MAINT | 110 | 1w | 2026-05-26 | 2026-05-29
COLERAINE | LIMAVADY | CVT MAINT AND MESH ISOLATORS | MAINT | 110 | 3D | 2026-05-26 | 2026-06-29
OMAGH |  | TX2 MAJOR INC SFRA AND PAINTING | PROJ | 110 | 3W | 2026-05-26 | 2026-06-12
BALLYLUMFORD |  | BGT2 OUTAGE | GEN | GEN | 1D | 2026-05-29
HANNAHSTOWN | CASTLEREAGH A | CT AND CVT MAINT | MAINT | 275 | 4D | 2026-05-31
HANNAHSTOWN |  | interbus 2 MINOR | MAINT | 275 | 4D | 2026-05-31
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar STRUCTURES HAN A | PROJ | 275 | 10D | 2026-05-31 | 2026-06-09
CASTLEREAGH |  | GC33 AND EG44 | MAINT | 275 | 4D | 2026-06-01
HANNAHSTOWN |  | GG10 MAINT | MAINT | 275 | 1W | 2026-06-01 | 2026-06-05
KILROOT |  | GJ90 MAINT | MAINT | 275 | 4d | 2026-06-01 | 2026-06-05
CASTLEREAGH |  | 275KV ISOLATORS SECTION A1 | MAINT | 275 | TBC | 2026-06-01 | 2026-07-31
CASTLEREAGH | TANDRAGEE | OHL AND TOWER PAINTING | OHL | 275 | 2W | 2026-06-01 | 2026-06-12
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 | PROJ | 275 | 2M | 2026-06-01 | 2026-07-30
BALLYLUMFORD |  | BGT2 OUTAGE | GEN | GEN | 30D | 2026-06-01 | 2026-06-30
BALLYLUMFORD |  | GIS cable works GT2 M Atcheson & Gavin Spence , Includes CT replacements on the both circuits | PROJ | 110 | 7WKS | 2026-06-01
CASTLEREAGH |  | NEW 275KV busbar section A2 | PROJ | 275 | 2M | 2026-06-01 | 2026-07-31
KILROOT |  | GT6 OUTAGE | GEN | 275 | 8D | 2026-06-01 | 2026-06-08
BALLYLUMFORD |  | BGT1 OUTAGE | GEN | GEN | 1D | 2026-06-06
EDEN |  | TX2 NOISE ENCLOSURE AND GCB SF6 REPAIRS, 33KV CABLING TO NEW BOARD | MAINT | 110 | 4D | 2026-06-06
TANDRAGEE | TAMNAMORE 'B' | GB15 MAINT AND ISOLATORS | MAINT | 275 | 1W | 2026-06-08 | 2026-06-12
COOLKEERAGH | LIMAVADY | tower painting AND POLE REPLACEMENTS | OHL | 110 | 1D | 2026-06-08
COOLKEERAGH | LIMAVADY | 6H0 MAINT | MAINT | 110 | 4D | 2026-06-08 | 2026-06-12
RASHARKIN | KELLS | MU10 MAINT | MAINT | 110 | 5D | 2026-06-08 | 2026-06-12
DUNGANNON |  | TX2 MAJOR | MAINT | 110 | 2W | 2026-06-08 | 2026-06-19
KNOCK |  | TX B MAJOR AND SFRA | MAINT | 110 | 3W | 2026-06-08 | 2026-06-26
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar STRUCTURES HAN B | PROJ | 275 | 8D | 2026-06-09 | 2026-06-17
BALLYLUMFORD |  | BGT1 OUTAGE | GEN | GEN | 1D | 2026-06-09
BALLYLUMFORD |  | BGT1 OUTAGE | GEN | GEN | 6D | 2026-06-11 | 2026-06-16
BALLYLUMFORD |  | MD40 MAINT GT1 | MAINT | 275 | 5D | 2026-06-11
BALLYLUMFORD |  | GIS cable works GT1 M Atcheson & Gavin Spence , Includes CT replacements on the both circuits | PROJ | 110 | 7WKS | 2026-06-11
KILROOT | CASTLEREAGH | TOWER PAINTING AND TROLLEY WORKS | OHL | 275 | 2W | 2026-06-15 | 2026-06-26
KELLS |  | GF105 MAINT | MAINT | 275 | 5D | 2026-06-15 | 2026-06-19
COOLKEERAGH | SPRINGTOWN 'A' | 13H0 maint | MAINT | 110 | 5d | 2026-06-15
SPRINGTOWN |  | TX1 MAJOR T/C FLUSH | MAINT | 110 | 2W | 2026-06-15
COOLKEERAGH | KILLYMALAGHT | 8H0 MAINT | MAINT | 110 | 4D | 2026-06-15 | 2026-06-19
STRABANE | omagh B | OHL WORKS | OHL | 110 | TBC | 2026-06-15
STRABANE | OMAGH B | POLE REPLACEMENT WORKS & TOWER PAINTING | OHL | 110 | 2W | 2026-06-15 | 2026-06-26
TANDRAGEE |  | MB45 C/B REPLACEMENT WAR 'B' CCT | PROJ | 110 | 6WKS | 2026-06-15 | 2026-07-24
WARINGSTOWN |  | TX2 MAJOR AND MR UPGRADES | MAINT | 110 | 8d | 2026-06-15 | 2026-06-26
LARNE |  | LARNE TX1 REPLACEMENT (PROJECTS) | PROJ | 110 | 7WKS | 2026-06-15 | 2026-07-31
CASTLEREAGH | RATHGAEL 'A' | RESTRING OF OHL CONDUCTORS | OHL | 110 | 3W | 2026-06-15
BALLYLUMFORD | BALLYCRONANMORE | GD7, EG64 AND EG65 MAINT | MAINT | 110 | 3D | 2026-06-16
BALLYLUMFORD | BALLYCRONANMORE | Filter bank permanent removal and OHL downleads after test stage | PROJ | 275 | 3D | 2026-06-16
HANNAHSTOWN | BALLYCRONANMORE | OHL AND TOWER PAINTING | OHL | 275 | 1W | 2026-06-16
MOYLE |  | SINGLE POLE OUTAGE | GEN | GEN | 3D | 2026-06-16 | 2026-06-18
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar STRUCTURES HAN B AND KPS | PROJ | 275 | 11D | 2026-06-17 | 2026-06-28
KELLS |  | GF45 MAINT | MAINT | 110 | 1W | 2026-06-22 | 2026-06-26
COOLKEERAGH |  | C30 OUTAGE | GEN | GEN | 4D | 2026-06-23 | 2026-06-27
COOLKEERAGH | magherafelt B | GA65 bay stage 7 | PROJ |  | 11d | 2026-06-26 | 2026-07-10
BELFAST CENTRAL MAIN |  | BCM TX A PAINTING | PROJ | 110 | 2W | 2026-06-28
BALLYLUMFORD | HANNAHSTOWN B | GD30 MAINT | MAINT | 275 | 5D | 2026-06-29
KILROOT | TANDRAGEE | OHL AND TOWER PAINTING | OHL | 275 | 2W | 2026-06-29 | 2026-07-10
TANDRAGEE |  | TANDRAGEE IBTX2 MAJOR INC RX2 | MAINT | 275 | 3W | 2026-06-29 | 2026-07-17
COOLKEERAGH |  | INTERBUS TRANSFORMER 1 MINOR INC (INSTALL BUND WALL) - BUND WALL AND BLAST WALL & ETX installation | MAINT | 275 | 5d | 2026-06-29
COLERAINE |  | STATKRAFT CONNECTION potential outage | PROJ | 110 | 2M | 2026-06-29 | 2026-08-30
COLERAINE |  | 9L0 and STATKRAFT Connection | PROJ | 110 | 2M | 2026-06-29 | 2026-08-30
LISBURN MAIN |  | TX1 MAJOR INC SFRA AND 22L0 | MAINT | 110 | 8D | 2026-06-29 | 2026-07-10
BROCKAGHBOY WINDFARM |  | Plant MAINT | MAINT | 110 | 3d | 2026-06-29
RASHARKIN | Garvagh | MAINT WORKS | MAINT | 110 | TBC | 2026-06-29
BROCKAGHBOY WINDFARM |  | MU99 AND CT AND EM407 DUE | MAINT | 110 | 1W | 2026-06-29
GARVAGH |  | MZ10 MAINT BROCKAGHBOY CIRCUIT , repair leaks | MAINT | 110 | 1W | 2026-06-29
KILROOT |  | GT7 OUTAGE | GEN | 275 | 8D | 2026-07-01 | 2026-07-08
DONEGALL |  | TX A & TX D ISOLATION FOR BONFIRE ADJACENT TO SITE. | MAINT | 110 | 2w | 2026-07-02 | 2026-07-15
BALLYCRONANMORE |  | LINE TRAP REPLACE tuning UNITS AT BYC END OF HAN CIRCUIT | PROJ | 275 | 3w | 2026-07-04
BALLYCRONANMORE | HANNAHSTOWN A | OHL WORKS | OHL | 275 | 1W | 2026-07-04
MOYLE |  | SINGLE POLE OUTAGE | GEN | GEN | 5D | 2026-07-04
CASTLEREAGH |  | MC25 MAINT CARNMONEY 'A' | MAINT | 110 | 5D | 2026-07-06 | 2026-07-10
GORT |  | GORT MT5 MAINT AND BUSBAR ISOLATOR REPAIRS MT3 | MAINT | 110 | 5D | 2026-07-06 | 2026-07-10
LISAGHMORE |  | TX1 PAINTING | PROJ | 110 | 2w | 2026-07-14 | 2026-07-24
KELLS |  | IBTX2 MINOR | MAINT | 110 | 4D | 2026-07-15 | 2026-07-18
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar STRUCTURES TAN CCT | PROJ | 275 | 9D | 2026-07-15 | 2026-07-24
COLERAINE | LOGUESTOWN 'B' | tower painting and OHL defect repairs | OHL | 110 | 1D | 2026-07-15
COLERAINE | LOGUESTOWN 'B' | CVT MAINT | MAINT | 110 | 2D | 2026-07-15
LOGUESTOWN |  | LOG TX 2 MAJOR AND SFRA | MAINT | 110 | 8D | 2026-07-15 | 2026-07-24
COOLKEERAGH |  | 15H0 MAINT AND CAP BANK Maintenance too( weeding only ) | MAINT | 110 | 5d | 2026-07-15 | 2026-07-24
TANDRAGEE | LOUTH 1 | TOWER PAINTING AND OHL WORKS | OHL | 275 | 2w | 2026-07-20 | 2026-07-31
TANDRAGEE | LOUTH 1 | GB35 MAINT AND ISOLATORS | MAINT | 275 | 1W | 2026-07-20 | 2026-07-31
KELLS | BALLYVALLAGH 'B' | POLE REPLACEMENTS WORKS AND TOWER PAINTING | OHL | 110 | 1W | 2026-07-20 | 2026-07-31
KELLS | BALLYVALLAGH 'B' | MF100 BAY MAINT | MAINT | 110 | 1W | 2026-07-20 | 2026-07-31
LISBURN MAIN |  | TX2 MAJOR INC SFRA AND 25L0 | MAINT | 110 | 8D | 2026-07-20 | 2026-07-31
TAMNAMORE | TANDRAGEE A | GP65 MAINT | MAINT | 275 | 1W | 2026-07-20 | 2026-07-26
TANDRAGEE | TAMNAMORE 'A' | GB25 MAINT | MAINT | 275 | 5D | 2026-07-20 | 2026-07-24
CASTLEREAGH |  | 275KV ISOLATORS SECTION A2 B/Bar STRUCTURES BBAR ONLY | PROJ | 275 | 7D | 2026-07-24 | 2026-07-31
COOLKEERAGH | Magheraflet B | GA65 bay stage 8 | PROJ |  | 4d | 2026-07-27 | 2026-07-30
BALLYLUMFORD | EDEN A | MD60 MAINT | MAINT | 110 | 5D | 2026-07-27 | 2026-07-31
LISAGHMORE |  | TX2 PAINTING | PROJ | 110 | 2w | 2026-07-27 | 2026-08-07
TANDRAGEE |  | MB35 C/B REPALCEMENT WAR A CCT | PROJ | 110 | 6WKS | 2026-07-27 | 2026-09-04
LISNABREENY BATTERY STORAGE |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | 1d | 2026-07-27
KILLYMALAGHT |  | MR15 MAINT | MAINT | 110 | 4d | 2026-08-01 | 2026-03-24
STRABANE | killymalaght | CVT MAINT AND CX235 | MAINT | 110 | 3d | 2026-08-01 | 2026-03-19
KELLS |  | MAG CVT MAINT AND GF43,GF46 AND GF56 MAINT | MAINT | 275 | 1W | 2026-08-03
KELLS |  | KILROOT 'A' CVT MAINT AND GF103, GF106 AND GF116 MAINT | MAINT | 275 | 1W | 2026-08-03
KILROOT | KELLS 'A' | OHL WORKS | OHL | 275 | TBC | 2026-08-03
KILROOT | KELLS A | CVT & CT REPLACEMENT AND WALL BUSHING MAINT | PROJ | 275 | 5WKS | 2026-08-03 | 2026-09-04
KILROOT | KELLS 'A' | TOWER PAINTING AND TROLLEY WORKS | OHL | 275 | 2W | 2026-08-03 | 2026-08-14
TANDRAGEE |  | TANDRAGEE IBTX3 MINOR | MAINT | 275 | 4D | 2026-08-03 | 2026-08-07
KILROOT |  | GJ45 MAINT | MAINT | 275 | 5D | 2026-08-03 | 2026-09-04
KILROOT |  | GJ50 CT REPLACEMENTS | PROJ | 275 | 5D | 2026-08-03 | 2026-09-04
KILROOT |  | GJ55 MAINT | MAINT | 275 | 5D | 2026-08-03 | 2026-09-04
MAGHERAKEEL | OMAGH | MS20 MAINT | MAINT | 110 | 5D | 2026-08-03
OMAGH | MAGHERAKEEL | OHL CONDUCTOR SAMPLES and DLR equipment addition, CVT MAINT @M'Keel | OHL | 110 | 12D | 2026-08-03 | 2026-08-19
OMAGH | MAGHERAKEEL | REPLACE AP1 POLES | OHL | 110 | 12D | 2026-08-03 | 2026-08-19
OMAGH | MAGHERAKEEL | CVT AND MESH ISOLATORS | MAINT | 110 | 3D | 2026-08-03 | 2026-08-06
EDEN |  | 1T2,3T2,CX101,ET1 AND BPS A CVT | MAINT | 110 | 3D | 2026-08-03
GLENGORMLEY |  | 110KV CABLE CLEAT REPLACEMENT ON TX B AT TOWERS | PROJ | 110 | 2W | 2026-08-03 | 2026-08-14
NEWTOWNARDS |  | TX1 PAINTING | PROJ | 110 | 2w | 2026-08-04 | 2026-08-14
KELLS |  | Kells IBTX1 MINOR | MAINT | 275 | 1W | 2026-08-10 | 2026-08-14
TAMNAMORE |  | INTERBUS 1 MINOR | MAINT | 110 | 4D | 2026-08-10 | 2026-08-14
TAMNAMORE |  | INTERBUS 1 MINOR AND GP15 & Reactor | MAINT | 275 | 4D | 2026-08-10 | 2026-08-14
BALLYLUMFORD | EDEN B | MD55 MAINT | MAINT | 110 | 5D | 2026-08-10
EDEN |  | 2T0 MAINT, ISOLS AND BPS B CVT | MAINT | 110 | 5D | 2026-08-10
DROMORE | DRUMQUIN | PQ MONITIOR REWIRING AND COMMISSIONING | PROJ | 110 | 5D | 2026-08-10
KELLS | RASHARKIN | TOWER PAINTING AND OHL WORKS | OHL | 110 | 2W | 2026-08-17 | 2026-08-28
KELLS | RASHARKIN | TOWER PAINTING AND POLE REPLACEMENTS | OHL | 110 | 1D | 2026-08-17 | 2026-08-28
KELLS | RASHARKIN | MF30 BAY MAINT | MAINT | 110 | 1w | 2026-08-17 | 2026-08-28
BALLYVALLAGH |  | ME35 BAY MAINT LARNE B | MAINT | 110 | 5D | 2026-08-17
LARNE |  | LARNE TX2 REPLACEMENT (PROJECTS) | PROJ | 110 | 7WKS | 2026-08-17 | 2026-10-02
NEWTOWNARDS |  | TX2 MAJOR FLUSH ONLY AND PAINTING | PROJ | 110 | 3W | 2026-08-17 | 2026-09-04
KILROOT |  | GT2 OUTAGE | GEN | GEN | 1d | 2026-08-27
GLENGORMLEY |  | TRANSFORMER TX A replacement | PROJ | 110 | 3M | 2026-08-31 | 2026-11-27
GLENGORMLEY |  | TRANSFORMER 'A' CABLE WORKS | PROJ | 110 | 3M | 2026-08-31 | 2026-11-27
GLENGORMLEY |  | 110KV CABLE CLEAT REPLACEMENT ON TX A AT TOWERS | PROJ | 110 | 2W | 2026-08-31 | 2026-11-27
KELLS | Glengormley 'A' | KELLS BAY CONSTRUCTION OF BREAKER AND NEW EARTH SWITCHES | PROJ | 110 | 3M | 2026-08-31 | 2026-11-27
KELLS | Glengormley 'A' | cable sheath tests | MAINT | 110 | 1/2d | 2026-08-31
TANDRAGEE | LOUTH 2 | TOWER PAINTING AND OHL WORKS | OHL | 275 | 2w | 2026-09-01 | 2026-09-11
TANDRAGEE | LOUTH 2 | GB55 MAINT AND ISOLATORS | MAINT | 275 | 1W | 2026-09-01 | 2026-09-11
TANDRAGEE |  | TAN IBTX1 MINOR | MAINT | 110 | 4D | 2026-09-01
KILROOT |  | GT2 OUTAGE TO REPLACE SURGE ARRESTOR | GEN | GEN | 2W | 2026-09-01
KILROOT |  | GT2 OUTAGE | GEN | GEN | 28d | 2026-09-01 | 2026-09-28
KILROOT |  | KILROOT GENERATOR T2 (LINES) - PLANT MAINT. CVT & CSE's maint | MAINT | 275 | 5D | 2026-09-01
KELLS | CREAGH | MF40 BAY MAINT & PFFIFFNER WIRING MODIFCATIONS | PROJ | 110 | 1D | 2026-09-01 | 2026-09-11
KELLS | CREAGH | TOWER PAINTING AND OHL WORKS | OHL | 110 | 2W | 2026-09-01 | 2026-09-11
KELLS | CREAGH | POLE REPLACMENTS | OHL | 110 | 4D | 2026-09-01 | 2026-09-11
CASTLEREAGH |  | MC100 MAINT CREGAGH B | MAINT | 110 | 5D | 2026-09-01
CREGAGH |  | TX B move existing protection | PROJ | 110 | 2wks | 2026-09-01
CREGAGH |  | TX B 33KV CABLE ALTERATION WORKS | PROJ | 110 | 5wks | 2026-09-01
CREGAGH |  | TX B MAINTENANCE | MAINT | 110 | 2W | 2026-09-01
BELFAST CENTRAL MAIN |  | BCM TX B PAINTING | PROJ | 110 | 2W | 2026-09-01
KILROOT | KELLS B | CVT & CT REPLACEMENT AND WALL BUSHING MAINT | PROJ | 275 | 5WKS | 2026-09-07 | 2026-10-09
KILROOT | KELLS 'B' | TOWER PAINTING AND TROLLEY WORKS | OHL | 275 | 2W | 2026-09-07 | 2026-09-18
TANDRAGEE |  | INTERBUS TRANSFORMER '1' minor mtce | PROJ | 275 | 4d | 2026-09-07
TANDRAGEE |  | MB40 C/B/REPLACEMENT IBTX1 CIVILS LINKED TO THIS | PROJ | 110 | 12M | 2026-09-07
TANDRAGEE |  | Reactor 1 replacement | PROJ | 275 | 12M | 2026-09-07
TANDRAGEE |  | INTERBUS TRANSFORMER '1' BUND AND REMOVAL | PROJ | 275 | 15M | 2026-09-07 | 2027-12-01
KILROOT |  | GJ25 MAINT | MAINT | 275 | 3W | 2026-09-07
KILROOT |  | GJ30 MAINT | MAINT | 275 | 5D | 2026-09-07
KILROOT |  | GJ35 MAINT | MAINT | 275 | 5D | 2026-09-07
TANDRAGEE |  | MB20 NEWRY B CIRCUIT BREAKER REPALCEMENT | PROJ | 110 | 6WKS | 2026-09-07 | 2026-10-16
TAMNAMORE |  | DERRYMEEN BAY AND CONNECTION WORKS | PROJ | 110 | 4m | 2026-09-07 | 2026-12-23
KELLS |  | 275KV ISOLATORS GF44 GF84 & GF104 | MAINT | 110 | 5D | 2026-09-14 | 2026-09-18
KELLS | BALLYVALLAGH 'A' | POLE REPLACEMENTS WORKS AND TOWER PAINTING | OHL | 110 | 2W | 2026-09-14 | 2026-09-25
KELLS | BALLYVALLAGH 'A' | MF90 BAY MAINT | MAINT | 110 | 1W | 2026-09-14 | 2026-09-25
TAMNAMORE |  | INTERBUS 2 MINOR | MAINT | 275 | 1W | 2026-09-14 | 2026-09-18
TAMNAMORE | MAGHERAFELT A | GP25 MAINT | MAINT | 275 | 1W | 2026-09-21 | 2026-09-25
BALLYLUMFORD |  | GD20 MAINT | MAINT | 275 | 5d | 2026-09-28 | 2026-10-02
BALLYMENA |  | TX2 MINOR INC TC FLUSH, BUSHING REPLACEMENT AND BUSBAR COVER REPLACEMENT | MAINT | 110 | 2W | 2026-09-28 | 2026-10-09
BALLYMENA |  | TX4 MAJOR | MAINT | 110 | 1W | 2026-09-28 | 2026-10-09
KELLS | BALLYMENA 'B' | POLE REPLACEMENTS WORKS & TOWER PAINTING | OHL | 110 | 2W | 2026-09-28 | 2026-10-09
MAGHERAFELT | TAMNAMORE 'A' | GH55 BAY CVT REPLACEMENT ,PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 3WKS | 2026-10-01
MAGHERAFELT | TAMNAMORE 'A' | TMN - MAG 'A' (OHL WORK) - SINGLE TENSION TOWER 228 & 253 | OHL | 275 | 1wk | 2026-10-01
OMAGH | TREMOGE | OHL WORKS | MAINT | 110 | 3D | 2026-10-01
OMAGH | TREMOGE | OHL WORKS | OHL | 110 | 5D | 2026-10-01
BANBRIDGE |  | TX2 & TX4 CIVIL WORKS + top up lners | MAINT | 110 | 3W | 2026-10-01
TREMOGE | OMAGH B | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION/ EARTH WIRE COMPLETION LAST SPAN OVER UNDERCOSSING | OHL | 110 | 3W | 2026-10-01
TREMOGE | OMAGH B | prep works and measurements for diversion | OHL | 110 | 1D | 2026-10-01
OMAGH |  | 4M0 & 5M0 timing tests , plus tremoge earth switch | maiNT | 110 | 4d | 2026-10-01
COOLKEERAGH |  | IBTX2 MINOR | MAINT | 275 | 4d | 2026-10-05 | 2026-10-09
GORT | OMAGH | MT40 BAY MAINT AND PQ REPAIR OMAGH CCT | MAINT | 110 | 5D | 2026-10-05 | 2026-10-09
KILROOT | CASTLEREAGH | CVT & CT REPLACEMENT AND WALL BUSHING MAINT | PROJ | 275 | 5WKS | 2026-10-12 | 2026-11-13
BALLYLUMFORD | BALLYVALLAGH A | MD80 MAINT | Maint | 110 | 5D | 2026-10-12
LISNABREENY BATTERY STORAGE |  | ANNUAL MAINT FOR 3RD PARTY | GEN | GEN | 1d | 2026-10-12
BALLYLUMFORD | B32 | B32 OUTAGE | GEN | GEN | 3D | 2026-10-13 | 2026-10-15
COOLKEERAGH |  | IBTX1 MINOR maint and 110KV CABLE REPLACMEMENT trials IBTX1 CABLE | PROJ | 275 | 4d | 2026-10-19 | 2026-10-23
TANDRAGEE |  | MB5 C/B REPLACEMENT DRU 'A' CCT | PROJ | 110 | 6WKS | 2026-10-19 | 2026-12-18
BALLYLUMFORD | BALLYVALLAGH B | MD75 MAINT | MAINT | 110 | 5D | 2026-10-19
TANDRAGEE |  | MB10 C/B REPLACEMENT BUSCOUPELR '1' | PROJ | 110 | 6WKS | 2026-10-19 | 2026-12-18
BALLYLUMFORD | B31 | B21 OUTAGE | GEN | GEN | 4D | 2026-10-20 | 2026-10-22
BALLYLUMFORD | B10 | B10 GENERATOR OUTAGE | GEN | GEN | 3D | 2026-10-27 | 2026-10-29
KILROOT |  | CT REPLACEMENT FINAL SETS | PROJ | 275 | 5WKS | 2026-11-14
CREGAGH |  | Cregagh Tx A measurements for new tx & spigots | PROJ | 110 | 4D | 2026-11-16
CREGAGH |  | TX A move existing protection | PROJ | 110 | 2wks | 2026-11-16
CREGAGH |  | TX A 33KV CABLE ALTERATION WORKS | PROJ | 110 | 5wks | 2026-11-16
COOLKEERAGH | MAGHERAFELT B | STATKRAFT CONNECTION AND COMPLETION OF NEW BAYS | PROJ | 275 | 1M | 2026-12-01 | 2026-12-25
STRABANE |  | TX1 PAINTING AND COOLERS | PROJ | 110 | 2W | 2026-12-01
STRABANE |  | TX2 PAINTING AND COOLERS | PROJ | 110 | 2W | 2026-12-01
MAGHERAFELT |  | AUTO RECLOSE PANEL AND SCHEME | PROJ | 275 | 1M | 2026-12-01
TANDRAGEE |  | 110KV GROUP ALARMS T602M | PROJ | 110 | 1M | 2026-12-01
TANDRAGEE |  | 275KV GROUP ALARMS T602G | PROJ | 110 | 1M | 2026-12-01
VARIOUS |  | TUNING UNITS ON CVTS MULTIPLE LOCATIONS | PROJ |  | 3W | 2026-12-01
CASTLEREAGH |  | repair defective earth switch drives EM57,EM58,EM59 OR EM60 | MAINT | 110 | 4D | 2026-12-04