## Info
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed and elements of the capital works programme and maintenance requirements relevant to each item of plant on the transmission system are detailed in this spreadsheet. Outages are classified as either 'Scheduled', 'Proposed' or 'Planned'. The 'Reference' status refers to an outage of an item of plant which is not under the control of the TSO e.g. a customer transformer.
Outage Classification:
Scheduled - Outage scheduled with specified start and end dates.
Proposed - An outage slot for the work to be completed in, with proposed specific start and end dates.
Planned - A viable outage window identified to complete a particular work item. Works will not be assigned a date until later in the outage season.
Reference - Outage scheduled with specified start and end dates. Plant is not under TSO control e.g. a customer transformer.
Outages several months in the future will initially be classified as 'Planned', as the outage window approaches the outage will move to a 'Proposed'/'Scheduled' state. For maintenance activities, outage dates will be proposed 6 weeks before the start of the month in which the outage is occurring and the outage will be scheduled 4 weeks before the start of the month. For outages relating to capital projects, the proposal and scheduling of outage dates will vary from project to project. Where possible similar timelines to those outlined for maintenance activities will be adhered to.
All planned outages due to start from the Monday following publication date until the end of the year is presented in this spreadsheet. Outages which have already begun and will run into this period are also included. For information on outages which have already taken place in 2018 please refer to the two week outage summary publications at the following link:
http://www.eirgridgroup.com/customer-and-industry/general-customer-information/outage-information/transmission-outages/
The 'All' tab includes all outages while separate tabs are provided which list the outages in the various regions around the country. The specific information provided for each outage is described here;
Outage ID – A unique TOP outage ID showing the outage in which the transmission works belong.
Feeder ID – Full feeder name as per TOP database naming convention of outaged equipment.
Calendar Day Duration – This shows the amount of calendar days proposed or scheduled to complete the works associated with the outage ID in question. If outage windows are indicative without firm schedules the amount of calendar days required is unknown and this field is populated with “Unknown”
Work Days Required - This shows the amount of days ESB Network Operators need to be on site to complete all works planed on or close to the particular piece of electrical equipment. This can be working days only or a combination of working and non-working days in which operators are on site.
Outage Status – This is the outage classification as described above.
Start – This indicates the start date of a proposed or scheduled outage or the start month of an indicative outage. Unscheduled work is given a start field of 25/12/2500 to facilitate further post processing.
Finish – This indicates the end date of a proposed or scheduled outage or the end month of an indicative outage. Unscheduled work is given an end field of 25/12/2500 to facilitate further post processing.
Date of publication: 10 05 2018
Update interval: The first week of each month

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AA-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G2-T102 | 57 |  | Scheduled | 18/03/2018 | 13/05/2018
TO-18-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 67 |  | Scheduled | 20/03/2018 | 25/05/2018
TO-18-AA-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA 110-DRUMLINE 110-1 | 83 | 55 | Scheduled | 20/03/2018 | 10/06/2018
TO-18-FIN-GLA-1-01 | 110kV FEEDER - FINGLAS 110-GLASMORE 110-1 | 53 | 36 | Reference | 20/03/2018 | 11/05/2018
TO-18-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-CBR-110SA1-02 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-CBR-110SA2-02 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 114 | 80 | Scheduled | 03/04/2018 | 25/07/2018
TO-18-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 85 | 59 | Scheduled | 03/04/2018 | 26/06/2018
TO-18-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 114 | 80 | Scheduled | 03/04/2018 | 25/07/2018
TO-18-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 114 |  | Scheduled | 03/04/2018 | 25/07/2018
TO-18-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 114 | 80 | Reference | 03/04/2018 | 25/07/2018
TO-18-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 65 | 45 | Scheduled | 09/04/2018 | 12/06/2018
TO-18-AA-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G3-T103 | 55 | 38 | Scheduled | 15/04/2018 | 08/06/2018
TO-18-AA-110K1-2-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA 110-ARDNACRUSHA 110-110K1-2 | 54 | 38 | Scheduled | 16/04/2018 | 08/06/2018
TO-18-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 12 | 10 | Scheduled | 23/04/2018 | 04/05/2018
TO-18-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-MID-T141-02 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 10 | 8 | Reference | 25/04/2018 | 04/05/2018
TO-18-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 2 | 2 | Scheduled | 30/04/2018 | 01/05/2018
TO-18-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 5 |  | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 |  | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 |  | Reference | 30/04/2018 | 04/05/2018
TO-18-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 10 | 7 | Scheduled | 30/04/2018 | 09/05/2018
TO-18-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 21 | 14 | Scheduled | 30/04/2018 | 20/05/2018
TO-18-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 22 | 15 | Scheduled | 30/04/2018 | 21/05/2018
TO-18-110 kV B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 22 | 15 | Scheduled | 30/04/2018 | 21/05/2018
TO-18-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | Scheduled | 30/04/2018 | 02/05/2018
TO-18-MP GIS-T4201-03 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 2 | 2 | Scheduled | 30/04/2018 | 01/05/2018
TO-18-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BWR-T124-03 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 2 | 2 | Reference | 01/05/2018 | 02/05/2018
TO-18-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-COL-CDU-1-05 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-110K1-2-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-110K1-3-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-PLA-1-04 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-RYB GIS-1-03 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-T2101-03 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 8 | 5 | Scheduled | 02/05/2018 | 09/05/2018
TO-18-KRA-220K1-2-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-RRU-T122-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-INC-220K1-2-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 2 | 2 | Scheduled | 03/05/2018 | 04/05/2018
TO-18-INC-MAY-1-06 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 03/05/2018 | 04/05/2018
TO-18-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 1 | 1 | Scheduled | 03/05/2018 | 03/05/2018
TO-18-KPG-KNR-1-220-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 58 | 40 | Scheduled | 03/05/2018 | 29/06/2018
TO-18-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 4 | Scheduled | 07/05/2018 | 11/05/2018
TO-18-110 kV A1/A2/A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1-A2-A3 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G2-T102 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-BLK-T142-03 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference | 08/05/2018 | 08/05/2018
TO-18-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Scheduled | 08/05/2018 | 08/05/2018
TO-18-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | Scheduled | 08/05/2018 | 08/05/2018
TO-18-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 11 | 9 | Scheduled | 08/05/2018 | 18/05/2018
TO-18-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 2 | 2 | Scheduled | 08/05/2018 | 09/05/2018
TO-18-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 7 | 5 | Reference | 08/05/2018 | 14/05/2018
TO-18-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 3 | 3 | Scheduled | 08/05/2018 | 10/05/2018
TO-18-KRA-MID-1-03 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 10 | 8 | Scheduled | 08/05/2018 | 17/05/2018
TO-18-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | 3 | 3 | Scheduled | 08/05/2018 | 10/05/2018
TO-18-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 2 | 2 | Scheduled | 09/05/2018 | 10/05/2018
TO-18-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 5 | 3 | Scheduled | 09/05/2018 | 13/05/2018
TO-18-FIN-220K1-2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 1 | 1 | Scheduled | 09/05/2018 | 09/05/2018
TO-18-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 3 | 3 | Scheduled | 09/05/2018 | 11/05/2018
TO-18-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 114 | 80 | Scheduled | 10/05/2018 | 31/08/2018
TO-18-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Scheduled | 10/05/2018 | 11/05/2018
TO-18-FIN-GLA-1-02 | 110kV FEEDER - FINGLAS 110-GLASMORE 110-1 | 2 | 2 | Reference | 10/05/2018 | 11/05/2018
TO-18-KNR-TB-1-01 | 110kV FEEDER - KNOCKANURE 110-TARBERT 110-1 | 118 | 82 | Scheduled | 10/05/2018 | 04/09/2018
TO-18-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 3 | 1 | Scheduled | 11/05/2018 | 13/05/2018
TO-18-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 1 | 1 | Scheduled | 11/05/2018 | 11/05/2018
TO-18-AA GIS-SNG-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | 2 | 0 | Reference | 12/05/2018 | 13/05/2018
TO-18-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-CLE-WOO-1-02 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 2 | 1 | Scheduled | 13/05/2018 | 14/05/2018
TO-18-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 2 | 1 | Scheduled | 13/05/2018 | 14/05/2018
TO-18-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 19 | 15 | Scheduled | 14/05/2018 | 01/06/2018
TO-18-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 10 | 8 | Scheduled | 14/05/2018 | 23/05/2018
TO-18-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-110SA2-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 4 | 4 | Scheduled | 14/05/2018 | 17/05/2018
TO-18-FIN-SVN-1-01 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 44 |  | Reference | 14/05/2018 | 26/06/2018
TO-18-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 3 | 3 | Scheduled | 16/05/2018 | 18/05/2018
TO-18-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-DRM-110SA1-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 3 | Scheduled | 16/05/2018 | 20/05/2018
TO-18-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 3 | Scheduled | 16/05/2018 | 20/05/2018
TO-18-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 3 | 3 | Scheduled | 16/05/2018 | 18/05/2018
TO-18-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | Scheduled | 16/05/2018 | 16/05/2018
TO-18-INC-MAY-1-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 22 | 15 | Scheduled | 17/05/2018 | 07/06/2018
TO-18-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 22 | 15 | Scheduled | 17/05/2018 | 07/06/2018
TO-18-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference | 18/05/2018 | 18/05/2018
TO-18-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Scheduled | 18/05/2018 | 18/05/2018
TO-18-BLK,T-MAY-1-04 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | Scheduled | 18/05/2018 | 18/05/2018
TO-18-AA-AA GIS-1-02 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 3 | 3 | Reference (Tentative) | 21/05/2018 | 23/05/2018
TO-18-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-BLK,T-NEW-1-03 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 21/05/2018 | 21/05/2018
TO-18-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 21/05/2018 | 21/05/2018
TO-18-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | 3 | 3 | Reference | 21/05/2018 | 23/05/2018
TO-18-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 5 |  | Tentative | 21/05/2018 | 25/05/2018
TO-18-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 8 | 6 | Scheduled | 21/05/2018 | 28/05/2018
TO-18-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 2 | 2 | Scheduled | 22/05/2018 | 23/05/2018
TO-18-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 2 | 2 | Scheduled | 22/05/2018 | 23/05/2018
TO-18-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 112 |  | Scheduled | 22/05/2018 | 10/09/2018
TO-18-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 10 | 8 | Scheduled | 23/05/2018 | 01/06/2018
TO-18-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 10 | 8 | Scheduled | 23/05/2018 | 01/06/2018
TO-18-KRA-T2103-03 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | 2 | 2 | Scheduled | 23/05/2018 | 24/05/2018
TO-18-CTN-110SA1-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-110SA2-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | 2 | 2 | Reference | 24/05/2018 | 25/05/2018
TO-18-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | 2 | 2 | Reference | 24/05/2018 | 25/05/2018
TO-18-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-110SA1-04 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-CTN-110SA2-04 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 15 | 10 | Scheduled | 28/05/2018 | 11/06/2018
TO-18-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 15 | 10 | Scheduled | 28/05/2018 | 11/06/2018
TO-18-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 65 | 46 | Scheduled | 28/05/2018 | 31/07/2018
TO-18-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 1 | 1 | Scheduled | 28/05/2018 | 28/05/2018
TO-18-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 1 | 1 | Reference | 28/05/2018 | 28/05/2018
TO-18-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 5 | 5 | Scheduled | 28/05/2018 | 01/06/2018
TO-18-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 3 | 3 | Scheduled | 28/05/2018 | 30/05/2018
TO-18-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 13 | 8 | Tentative | 30/05/2018 | 11/06/2018
TO-18-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 22 | 15 | Scheduled | 30/05/2018 | 20/06/2018
TO-18-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-CUS-PLS-1-02 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 29 | 20 | Scheduled | 01/06/2018 | 29/06/2018
TO-18-BIN-LET-1-02 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-BIN-LET-1-03 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 1 | 1 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 4 | Scheduled | 04/06/2018 | 08/06/2018
TO-18-LET-110SA1-2-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-110SA1-2-SA2-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-110SA1-3-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-LET-110SA1-3-SA3-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA3 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 0 | Reference | 04/06/2018 | 04/06/2018
TO-18-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-CLG-110K1-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | Unknown | 4 | Planned | June | June
TO-18-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | Unknown | 1 | Planned | June | June
TO-18-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | Unknown | 1 | Planned | June | June
TO-18-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | Unknown | 1 | Planned | June | June
TO-18-CLG-MCE-1-01 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | Unknown | 20 | Planned | June | July
TO-18-CLG-MCE-1-02 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | 28 | 20 | Scheduled | 05/06/2018 | 02/07/2018
TO-18-CLG-T121-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | Unknown | 4 | Planned | June | June
TO-18-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | 1 | Planned | June | June
TO-18-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 2 | 2 | Scheduled | 05/06/2018 | 06/06/2018
TO-18-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 2 | 2 | Scheduled | 05/06/2018 | 06/06/2018
TO-18-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 3 | 3 | Proposed | 05/06/2018 | 07/06/2018
TO-18-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 3 | 3 | Reference | 05/06/2018 | 07/06/2018
TO-18-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-PB-220K2-3-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | Unknown | 1 | Planned | June | June
TO-18-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 2 | 2 | Scheduled | 06/06/2018 | 07/06/2018
TO-18-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 2 | Scheduled | 07/06/2018 | 08/06/2018
TO-18-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 1 | Scheduled | 08/06/2018 | 08/06/2018
TO-18-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 0 | Scheduled | 09/06/2018 | 10/06/2018
TO-18-DFR-T122-04 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 0 | Reference | 09/06/2018 | 10/06/2018
TO-18-DFR,T-DFR-1-04 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 0 | Proposed | 09/06/2018 | 10/06/2018
TO-18-DFR,T-KIN-1-02 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | Proposed | 09/06/2018 | 10/06/2018
TO-18-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 0 | Scheduled | 09/06/2018 | 10/06/2018
TO-18-BAL-110SA1-02 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-BAL-110SA2-02 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 2 | 2 | Reference | 11/06/2018 | 12/06/2018
TO-18-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 5 |  | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 9 | 7 | Scheduled | 11/06/2018 | 19/06/2018
TO-18-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 1 | 1 | Scheduled | 11/06/2018 | 11/06/2018
TO-18-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-DRU-CAP2-02 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 2 | 2 | Proposed | 11/06/2018 | 12/06/2018
TO-18-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | 2 | Planned | June | June
TO-18-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SA1-3CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-FIN-SVN-1-03 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 2 | 2 | Reference | 11/06/2018 | 12/06/2018
TO-18-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 9 | 7 | Scheduled | 11/06/2018 | 19/06/2018
TO-18-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 5 | 5 | Reference | 11/06/2018 | 15/06/2018
TO-18-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 5 | 5 | Reference | 11/06/2018 | 15/06/2018
TO-18-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-NW-PB-1-04 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 47 | 35 | Proposed | 11/06/2018 | 27/07/2018
TO-18-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-220K3-4-03 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-R223-4-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-SHL-1-03 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-TF4-01 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 12 | 10 | Reference (Proposed) | 11/06/2018 | 22/06/2018
TO-18-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 1 | 1 | Scheduled | 11/06/2018 | 11/06/2018
TO-18-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 4 | 4 | Scheduled | 12/06/2018 | 15/06/2018
TO-18-KRA-MID-1-04 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | 3 | 3 | Scheduled | 12/06/2018 | 14/06/2018
TO-18-MID-110SA1-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MID-110SA2-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MID-T141-03 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 4 | 4 | Reference (Proposed) | 12/06/2018 | 15/06/2018
TO-18-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 3 | 3 | Scheduled | 13/06/2018 | 15/06/2018
TO-18-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 1 | 1 | Scheduled | 13/06/2018 | 13/06/2018
TO-18-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | Scheduled | 13/06/2018 | 15/06/2018
TO-18-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 8 | 6 | Scheduled | 13/06/2018 | 20/06/2018
TO-18-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 3 | 3 | Reference (Proposed) | 13/06/2018 | 15/06/2018
TO-18-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 3 | 3 | Reference (Proposed) | 13/06/2018 | 15/06/2018
TO-18-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-ST101-01 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-ST101-03 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 21 | 15 | Reference | 13/06/2018 | 03/07/2018
TO-18-GI-T2101-04 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 1 | 1 | Scheduled | 14/06/2018 | 14/06/2018
TO-18-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN-SVN-1-04 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 2 | 2 | Reference | 14/06/2018 | 15/06/2018
TO-18-OST-T4202-03 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 2 | 2 | Trip Testing | 14/06/2018 | 15/06/2018
TO-18-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 | Scheduled | 18/06/2018 | 29/06/2018
TO-18-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 1 | Reference (Planned) | June | June
TO-18-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | Scheduled | 18/06/2018 | 19/06/2018
TO-18-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | 1 | Planned | June | June
TO-18-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | Unknown | 1 | Planned | June | June
TO-18-DOO-CAP1-01 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | 5 | Planned | June | June
TO-18-DOO-T141-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-ENN-T102-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | 3 | 3 | Reference | 18/06/2018 | 20/06/2018
TO-18-ENN-T142-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T142 | 3 | 3 | Reference | 18/06/2018 | 20/06/2018
TO-18-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 5 | 5 | Scheduled | 18/06/2018 | 22/06/2018
TO-18-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-KLN-220K1-2-02 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 10 | 8 | Scheduled | 18/06/2018 | 27/06/2018
TO-18-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 3 | 3 | Proposed | 18/06/2018 | 20/06/2018
TO-18-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 3 | 3 | Scheduled | 19/06/2018 | 21/06/2018
TO-18-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 50 | 35 | Proposed | 20/06/2018 | 08/08/2018
TO-18-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 50 | 35 | Scheduled | 20/06/2018 | 08/08/2018
TO-18-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 1 | 1 | Scheduled | 21/06/2018 | 21/06/2018
TO-18-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 21/06/2018 | 22/06/2018
TO-18-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 1 | Reference (Planned) | June | June
TO-18-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 3 | 1 | Scheduled | 22/06/2018 | 24/06/2018
TO-18-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 3 | 1 | Scheduled | 22/06/2018 | 24/06/2018
TO-18-CBR-T141-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 3 | 1 | Reference | 22/06/2018 | 24/06/2018
TO-18-DOO-110SA1-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | 1 | Planned | June | June
TO-18-DOO-110SA2-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | Unknown | 1 | Planned | June | June
TO-18-DOO-T141-02 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 1 | Reference (Planned) | June | June
TO-18-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | 1 | 0 | Scheduled | 23/06/2018 | 23/06/2018
TO-18-CBG-CBR-1-02 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CBG-T142-02 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CSH-SAL-1-02 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-CBR-110SA1-03 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-110SA2-03 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-DLT-1-02 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-CBR-DLT-1-04 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-CBR-T142-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 3 | 3 | Scheduled | 25/06/2018 | 27/06/2018
TO-18-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 5 | 5 | Proposed | 25/06/2018 | 29/06/2018
TO-18-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-FIN GIS-T2106-06 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 4 | 4 | Proposed | 25/06/2018 | 28/06/2018
TO-18-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | Scheduled | 25/06/2018 | 06/07/2018
TO-18-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-MLC-110SA1-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MLC-110SA2-03 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 1 | 1 | Reference (Proposed) | 25/06/2018 | 25/06/2018
TO-18-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 3 | 3 | Proposed | 25/06/2018 | 27/06/2018
TO-18-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 5 | 5 | Proposed | 25/06/2018 | 29/06/2018
TO-18-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 117 | 84 | Proposed | 25/06/2018 | 19/10/2018
TO-18-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 117 | 84 | Proposed | 25/06/2018 | 19/10/2018
TO-18-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-WOH-110SA1-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 3 | 3 | Scheduled | 25/06/2018 | 27/06/2018
TO-18-ART-FIN-1-01 | 110kV FEEDER - ARTANE 110-FINGLAS 110-1 | Unknown | 30 | Reference (Planned) | June | August
TO-18-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 2 | 2 | Proposed | 28/06/2018 | 29/06/2018
TO-18-DRY-PLA-1-02 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 2 | 2 | Scheduled | 28/06/2018 | 29/06/2018
TO-18-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 1 | Planned | June | June
TO-18-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | June | June
TO-18-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | June | June
TO-18-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | 5 | Planned | July | July
TO-18-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | Unknown | 5 | Planned | July | July
TO-18-CSH-CAP1-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | Unknown | 6 | Planned | July | July
TO-18-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | Unknown | 2 | Planned | July | July
TO-18-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | 2 | Planned | July | July
TO-18-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | 2 | Planned | July | July
TO-18-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | 2 | Planned | July | July
TO-18-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | Unknown | 10 | Planned | July | July
TO-18-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | 10 | Planned | July | July
TO-18-DGN-WOH-1-03 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 3 | Planned | July | July
TO-18-DGN-WOH-1-04 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 3 | Planned | July | July
TO-18-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | 15 | Planned | July | July
TO-18-FIN GIS-T2106-07 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 15 | Planned | July | July
TO-18-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | 5 | Planned | July | July
TO-18-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | 10 | Planned | July | July
TO-18-KIN-T102-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | 10 | Planned | July | July
TO-18-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | 15 | Planned | July | July
TO-18-KNR-TRI-2-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | 15 | Planned | July | July
TO-18-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | 5 | Planned | July | July
TO-18-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | Unknown | 2 | Planned | July | July
TO-18-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | 1 | Planned | July | July
TO-18-SHL-T2014-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | 3 | Planned | July | July
TO-18-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | 8 | Planned | July | July
TO-18-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | Unknown | 2 | Planned | July | July
TO-18-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | 4 | Reference (Planned) | July | July
TO-18-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | 4 | Planned | July | July
TO-18-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | 4 | Planned | July | July
TO-18-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | 4 | Planned | July | July
TO-18-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | 3 | Planned | July | July
TO-18-CDU-HN-1-02 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 2 | Planned | July | July
TO-18-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 2 | Planned | July | July
TO-18-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 20 | Planned | July | August
TO-18-CUS-NEW-1-02 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 20 | Planned | July | August
TO-18-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | 2 | Planned | July | July
TO-18-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | 1 | Planned | July | July
TO-18-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | 2 | Planned | July | July
TO-18-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | Unknown | 6 | Planned | July | July
TO-18-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 0 | Planned | July | July
TO-18-CBR-110SA1-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | Unknown | 0 | Planned | July | July
TO-18-CBR-110SA2-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | Unknown | 0 | Planned | July | July
TO-18-CBR-CLN-1-04 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 0 | Planned | July | July
TO-18-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 0 | Planned | July | July
TO-18-CBR-T141-04 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | Unknown | 0 | Reference (Planned) | July | July
TO-18-CBR-CLN-1-11 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-10 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-05 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-09 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-SVC-05 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 24 | Planned | July | August
TO-18-CBR-SVC-07 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 24 | Planned | July | August
TO-18-CBR-T141-05 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | Unknown | 24 | Reference (Planned) | July | August
TO-18-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | 20 | Planned | July | August
TO-18-BDN-DOO-1-03 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 10 | Planned | July | July
TO-18-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | Unknown | 1 | Planned | July | July
TO-18-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | 1 | Planned | July | July
TO-18-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | 1 | Planned | July | July
TO-18-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | 1 | Reference (Planned) | July | July
TO-18-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | Unknown | 1 | Planned | July | July
TO-18-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | 1 | Planned | July | July
TO-18-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | Unknown | 4 | Planned | July | July
TO-18-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | Unknown | 4 | Planned | July | July
TO-18-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | 5 | Planned | July | July
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown |  | Planned | July | November
TO-18-MP-OST-1-02 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-MP-OST-1-04 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 74 | Planned | July | October
TO-18-MP-OST-1-05 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown |  | Planned | July | October
TO-18-OST-400SA1-02 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown | 74 | Planned | July | October
TO-18-OST-400SA2-02 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | 74 | Planned | July | October
TO-18-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown |  | Planned | July | October
TO-18-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown |  | Planned | July | October
TO-18-OST-T4202-04 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | 74 | Planned | July | October
TO-18-OST-TY-1-03 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 74 | Planned | July | October
TO-18-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | Unknown | 3 | Planned | July | July
TO-18-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | 3 | Planned | July | July
TO-18-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | 1 | Planned | July | July
TO-18-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | 1 | Planned | July | July
TO-18-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | 1 | Planned | July | July
TO-18-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | Unknown | 1 | Planned | July | July
TO-18-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | 1 | Planned | July | July
TO-18-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | Unknown | 1 | Planned | July | July
TO-18-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | 40 | Planned | July | September
TO-18-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | 0 | Planned | July | July
TO-18-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | 0 | Planned | July | July
TO-18-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | Unknown | 0 | Planned | July | July
TO-18-CLN-T141-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | Unknown | 0 | Reference (Planned) | July | July
TO-18-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | 3 | Planned | July | July
TO-18-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | 3 | Planned | July | July
TO-18-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | 5 | Planned | July | July
TO-18-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 5 | Planned | July | July
TO-18-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | 6 | Planned | July | July
TO-18-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | Unknown | 1 | Planned | July | July
TO-18-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | Unknown |  | Planned | July | July
TO-18-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | 5 | Planned | July | July
TO-18-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | 5 | Planned | July | July
TO-18-MAY-110K3-4-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | 5 | Planned | July | July
TO-18-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | 10 | Planned | July | July
TO-18-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | 10 | Planned | July | July
TO-18-MAY-T2104-03 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown |  | Planned | July | July
TO-18-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | Unknown | 3 | Planned | July | July
TO-18-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | Unknown | 1 | Planned | July | July
TO-18-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | Unknown | 5 | Planned | July | July
TO-18-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | 3 | Planned | July | July
TO-18-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | 15 | Planned | July | August
TO-18-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | Unknown | 1 | Planned | July | July
TO-18-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 5 | Planned | July | July
TO-18-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | Unknown | 5 | Planned | July | July
TO-18-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | 5 | Planned | July | July
TO-18-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | 5 | Planned | July | July
TO-18-PB-TF4-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | Unknown | 5 | Reference (Planned) | July | July
TO-18-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | 2 | Planned | July | July
TO-18-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | Unknown | 1 | Planned | July | July
TO-18-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | 20 | Planned | July | August
TO-18-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | 20 | Planned | July | August
TO-18-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 61 | Planned | July | October
TO-18-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 61 | Planned | July | October
TO-18-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | Unknown | 1 | Planned | July | July
TO-18-110 kV B4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B4 | Unknown | 5 | Planned | July | July
TO-18-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown |  | Planned | July | July
TO-18-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | 5 | Planned | July | July
TO-18-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | Unknown | 2 | Planned | July | July
TO-18-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 4 | Planned | July | July
TO-18-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | 15 | Planned | July | August
TO-18-FIN GIS-T2106-08 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 15 | Planned | July | August
TO-18-IKE-T141-02 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | 2 | Reference (Planned) | July | July
TO-18-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | 2 | Planned | July | July
TO-18-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | 2 | Planned | July | July
TO-18-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | 2 | Planned | July | July
TO-18-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | Unknown | 3 | Planned | July | July
TO-18-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | 5 | Planned | July | July
TO-18-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown |  | Planned | July | November
TO-18-MP-T4001-02 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown | 83 | Planned | July | November
TO-18-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | Unknown | 3 | Planned | July | July
TO-18-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | 2 | Reference (Planned) | July | July
TO-18-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | 3 | Planned | July | July
TO-18-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | 3 | Planned | July | July
TO-18-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | 3 | Planned | July | July
TO-18-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | 3 | Planned | July | July
TO-18-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | Unknown | 1 | Planned | July | July
TO-18-NW-PB-1-03 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 4 | Planned | July | July
TO-18-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | 3 | Planned | July | July
TO-18-BDN-110SA2-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | 3 | Planned | July | July
TO-18-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | Unknown | 7 | Planned | July | August
TO-18-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | 3 | Planned | July | July
TO-18-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | Unknown | 3 | Reference (Planned) | July | July
TO-18-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | Unknown | 1 | Planned | July | July
TO-18-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | July | July
TO-18-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown |  | Reference (Planned) | July | July
TO-18-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | 1 | Planned | July | July
TO-18-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | 60 | Planned | July | October
TO-18-ARI,T-COS-1-02 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | 60 | Planned | July | October
TO-18-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | July | July
TO-18-ARI,T-CDY-1-03 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 2 | Planned | July | July
TO-18-ARI,T-CDY-1-04 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | July | July
TO-18-CDY-110SA1-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | 2 | Planned | July | July
TO-18-CDY-110SA2-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | 2 | Planned | July | July
TO-18-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | 2 | Planned | July | July
TO-18-CDY-T121-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T121 | Unknown | 2 | Reference (Planned) | July | July
TO-18-110 kV A6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | July | July
TO-18-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | 2 | Planned | July | July
TO-18-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | 2 | Planned | July | July
TO-18-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | 2 | Planned | July | July
TO-18-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 38-T141 | Unknown | 2 | Reference (Planned) | July | July
TO-18-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | Unknown | 7 | Planned | July | August
TO-18-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | Unknown | 1 | Planned | July | July
TO-18-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | Unknown | 1 | Planned | July | July
TO-18-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-GI-WEX-1-07 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | 1 | Planned | July | July
TO-18-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | 5 | Planned | July | August
TO-18-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | 5 | Planned | July | August
TO-18-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | 14 | Planned | July | August
TO-18-400 kV B1 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400B1 | Unknown | 5 | Planned | July | August
TO-18-MP-400K1-2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT 400-MONEYPOINT 400-400K1-2 | Unknown | 8 | Planned | July | August
TO-18-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | 2 | Planned | July | July
TO-18-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | Unknown | 3 | Planned | July | August
TO-18-SRA-110K1-2-01 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | Unknown | 5 | Planned | July | August
TO-18-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | 1 | Planned | July | July
TO-18-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | Unknown |  | Planned | July | August
TO-18-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | 2 | Planned | July | August
TO-18-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 5 | Planned | August | August
TO-18-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | 1 | Planned | August | August
TO-18-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | 2 | Planned | August | August
TO-18-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | 2 | Planned | August | August
TO-18-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | 1 | Reference (Planned) | August | August
TO-18-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | Unknown | 3 | Planned | August | August
TO-18-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | 1 | Planned | August | August
TO-18-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-BOL-T121-02 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | 1 | Planned | August | August
TO-18-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | Unknown | 2 | Planned | August | August
TO-18-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | Unknown | 2 | Planned | August | August
TO-18-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | 2 | Planned | August | August
TO-18-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | 2 | Planned | August | August
TO-18-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | Unknown | 4 | Planned | August | August
TO-18-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | Unknown | 9 | Planned | August | August
TO-18-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 4 | Planned | August | August
TO-18-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | 3 | Planned | August | August
TO-18-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | 7 | Planned | August | August
TO-18-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | Unknown | 3 | Planned | August | August
TO-18-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | 7 | Planned | August | August
TO-18-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | Unknown | 1 | Planned | August | August
TO-18-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | 1 | Planned | August | August
TO-18-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | 2 | Planned | August | August
TO-18-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | 1 | Planned | August | August
TO-18-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | Unknown | 1 | Planned | August | August
TO-18-KNR-110K4-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K4 | Unknown | 1 | Planned | August | August
TO-18-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | 1 | Planned | August | August
TO-18-BK-CBR-1-04 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 0 | Planned | August | August
TO-18-CBR-110SA1-06 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | Unknown | 0 | Planned | August | August
TO-18-CBR-110SA2-06 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | Unknown | 0 | Planned | August | August
TO-18-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 7 | Planned | August | August
TO-18-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | 5 | Planned | August | August
TO-18-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | Unknown | 5 | Planned | August | August
TO-18-220 kV B1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B1 | Unknown | 5 | Planned | August | August
TO-18-220 kV A1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | Unknown | 2 | Planned | August | August
TO-18-220 kV B1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | Unknown | 2 | Planned | August | August
TO-18-CKM-T2101-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2101 | Unknown | 98 | Reference (Planned) | August | December
TO-18-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 4 | Planned | August | August
TO-18-CUL-DGN-1-02 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 4 | Planned | August | August
TO-18-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | 4 | Planned | August | August
TO-18-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | 5 | Planned | August | August
TO-18-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 4 | Planned | August | August
TO-18-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 4 | Planned | August | August
TO-18-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | 4 | Reference (Planned) | August | August
TO-18-110 kV A6 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | August | August
TO-18-FIN GIS-110K6-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | August | August
TO-18-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | August | August
TO-18-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | Unknown | 30 | Reference (Planned) | August | September
TO-18-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | 2 | Planned | August | August
TO-18-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | 2 | Reference (Planned) | August | August
TO-18-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 10 | Planned | August | August
TO-18-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 6 | Planned | August | August
TO-18-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | 10 | Planned | August | August
TO-18-GLR-MOY-1-03 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | 6 | Planned | August | August
TO-18-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | Unknown | 4 | Reference (Planned) | August | August
TO-18-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | 7 | Planned | August | August
TO-18-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | 3 | Planned | August | August
TO-18-KNY-110K2-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | Unknown | 1 | Planned | August | August
TO-18-KNY-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-KUR-NAV-1-02 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 5 | 5 | Reference | 13/08/2018 | 17/08/2018
TO-18-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 5 | 5 | Reference | 13/08/2018 | 17/08/2018
TO-18-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | 5 |  | Reference | 13/08/2018 | 17/08/2018
TO-18-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | Unknown | 3 | Planned | August | August
TO-18-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | 3 | Planned | August | August
TO-18-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | 8 | Planned | August | August
TO-18-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | 8 | Planned | August | August
TO-18-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | Unknown | 1 | Planned | August | August
TO-18-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | Unknown | 1 | Planned | August | August
TO-18-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | Unknown | 1 | Planned | August | August
TO-18-KNY-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K1 | Unknown | 1 | Planned | August | August
TO-18-KNY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-LET-TLK-1-01 | 110kV FEEDER - LETTERKENNY 110-TRILLICK 110-1 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-T122-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T122 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-TLK-1-01 | 110kV FEEDER - SORNE HILL 110-TRILLICK 110-1 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-TLK-T141-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T141 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-TLK-T142-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T142 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | 5 | Planned | August | August
TO-18-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | Unknown | 1 | Planned | August | August
TO-18-GI-ST101-02 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | Unknown |  | Planned | August | December
TO-18-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | Unknown | 5 | Planned | August | August
TO-18-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | 1 | Planned | August | August
TO-18-SKL-M/CAP2-01 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | Unknown | 5 | Planned | August | August
TO-18-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | 1 | Planned | August | August
TO-18-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | Unknown | 3 | Planned | August | August
TO-18-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | 30 | Reference (Planned) | August | October
TO-18-GI-110K1-2-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | 15 | Planned | August | September
TO-18-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | Unknown |  | Planned | August | October
TO-18-GI-KKY-1-04 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-ST101-04 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-T141-02 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | Unknown |  | Reference (Planned) | August | September
TO-18-GI-T141-04 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 63 | 45 | Reference | 21/08/2018 | 22/10/2018
TO-18-GI-T2101-05 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | Unknown |  | Planned | August | September
TO-18-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown |  | Planned | August | September
TO-18-GI-WAT-1-06 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | 1 | Planned | August | August
TO-18-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown |  | Planned | August | August
TO-18-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | Unknown | 2 | Planned | August | August
TO-18-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | Unknown | 7 | Planned | August | August
TO-18-KRA-RAF-1-05 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | 3 | Planned | August | August
TO-18-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | Unknown | 1 | Planned | August | August
TO-18-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | Unknown | 5 | Planned | August | August
TO-18-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown |  | Planned | August | September
TO-18-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | 24 | Planned | August | September
TO-18-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | Unknown | 1 | Planned | August | August
TO-18-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | Unknown | 7 | Planned | August | September
TO-18-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | Unknown | 6 | Planned | August | September
TO-18-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | 8 | Planned | August | September
TO-18-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | 6 | Planned | August | September
TO-18-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | Unknown | 6 | Planned | August | September
TO-18-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | 5 | Planned | August | August
TO-18-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | 5 | Planned | August | August
TO-18-ARK-CKM GIS-1-05 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 2 | Planned | August | August
TO-18-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 2 | 2 | Proposed | 28/08/2018 | 29/08/2018
TO-18-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | Unknown | 1 | Planned | August | August
TO-18-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | 6 | Planned | August | September
TO-18-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | 4 | Planned | August | September
TO-18-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | 1 | Planned | August | August
TO-18-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | 4 | Planned | August | September
TO-18-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | 4 | Planned | August | September
TO-18-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | 4 | Planned | August | September
TO-18-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-3-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-3-SA3-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA3 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-M/CAP1-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-T141-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 0 | Reference | 01/09/2018 | 01/09/2018
TO-18-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | 3 | Planned | September | September
TO-18-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | 3 | Planned | September | September
TO-18-ARK-CKM GIS-1-04 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 7 | Planned | September | September
TO-18-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | 2 | Planned | September | September
TO-18-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | 5 | Planned | September | September
TO-18-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | 3 | Reference (Planned) | September | September
TO-18-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-GI-WEX-1-08 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | 10 | Planned | September | September
TO-18-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | 4 | Planned | September | September
TO-18-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | 5 | Planned | September | September
TO-18-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | 3 | Planned | September | September
TO-18-LET-110SA1-2-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-110SA1-2-SA2-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 3 | 3 | Reference | 03/09/2018 | 05/09/2018
TO-18-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | 3 | Planned | September | September
TO-18-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | 5 | Planned | September | September
TO-18-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | 10 | Planned | September | September
TO-18-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | 10 | Planned | September | September
TO-18-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | Unknown | 10 | Reference (Planned) | September | September
TO-18-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | Unknown | 7 | Planned | September | September
TO-18-110 kV A6 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | September | September
TO-18-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110K6-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110SA4-6CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | 2 | Planned | September | September
TO-18-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 3 | Planned | September | September
TO-18-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | 19 | Planned | September | October
TO-18-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 5 | Planned | September | September
TO-18-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | 5 | Planned | September | September
TO-18-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 3 | 3 | Reference | 10/09/2018 | 12/09/2018
TO-18-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | 10 | Planned | September | September
TO-18-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | 3 | Planned | September | September
TO-18-KRA-T2103-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | Unknown | 3 | Planned | September | September
TO-18-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | 7 | Planned | September | September
TO-18-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | 2 | Planned | September | September
TO-18-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | 5 | Planned | September | September
TO-18-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | Unknown | 4 | Planned | September | September
TO-18-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | 4 | Planned | September | September
TO-18-CF-T104-03 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | 4 | Planned | September | September
TO-18-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | Unknown | 15 | Planned | September | October
TO-18-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | Unknown | 15 | Planned | September | October
TO-18-LOU-MTH-1-02 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | Unknown | 7 | Planned | September | September
TO-18-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | 3 | Planned | September | September
TO-18-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | 2 | Planned | September | September
TO-18-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | 1 | Planned | September | September
TO-18-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | Unknown | 1 | Planned | September | September
TO-18-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | 6 | Planned | September | September
TO-18-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | 5 | Planned | September | September
TO-18-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | 1 | Planned | September | September
TO-18-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | Unknown | 5 | Planned | September | September
TO-18-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | 3 | Planned | September | September
TO-18-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | 1 | Planned | September | September
TO-18-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | Unknown | 2 | Planned | September | September
TO-18-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | 5 | Planned | September | September
TO-18-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | 5 | Planned | September | September
TO-18-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | 5 | Reference (Planned) | September | September
TO-18-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | 5 | Reference (Planned) | September | September
TO-18-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | 5 | Reference (Planned) | September | September
TO-18-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | Unknown | 5 | Planned | September | September
TO-18-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | Unknown | 1 | Planned | September | September
TO-18-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | 3 | Planned | September | September
TO-18-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | Unknown | 5 | Planned | September | September
TO-18-TB-TRL-1-06 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | September | September
TO-18-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | 5 | Planned | September | September
TO-18-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-TRL-CAP2-02 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-TRL-T141-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | Unknown | 3 | Reference (Planned) | September | September
TO-18-FIN-FIN GIS-2-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | 2 | Planned | September | September
TO-18-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 3 | Planned | September | September
TO-18-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | Unknown | 5 | Planned | September | September
TO-18-CSH-GAL-1-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | Unknown | 1 | Planned | September | September
TO-18-COL-FIN GIS-1-03 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | Unknown | 3 | Planned | September | September
TO-18-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | 2 | Planned | September | September
TO-18-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-TRL-T142-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | Unknown | 2 | Reference (Planned) | September | September
TO-18-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | Unknown | 4 | Planned | September | September
TO-18-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | Unknown | 2 | Planned | September | September
TO-18-TBK-T142-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T142 | Unknown | 3 | Reference (Planned) | September | September
TO-18-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-BOL-1-03 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | 3 | Planned | September | September
TO-18-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | 2 | Planned | September | September
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 1 | Planned | October | October
TO-18-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 1 | Planned | October | October
TO-18-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | 1 | Planned | October | October
TO-18-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | 1 | Planned | October | October
TO-18-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | 1 | Reference (Planned) | October | October
TO-18-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | Unknown | 1 | Planned | October | October
TO-18-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | Unknown | 5 | Planned | October | October
TO-18-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 7 | Planned | October | October
TO-18-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown |  | Planned | October | October
TO-18-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | 1 | Planned | October | October
TO-18-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | 30 | Planned | October | November
TO-18-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | 30 | Reference (Planned) | October | November
TO-18-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | Unknown | 1 | Planned | October | October
TO-18-GI-110K1-2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | 15 | Planned | October | October
TO-18-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | Unknown | 15 | Reference (Planned) | October | October
TO-18-GI-T2101-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | Unknown | 15 | Planned | October | October
TO-18-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown | 15 | Planned | October | October
TO-18-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | 3 | Planned | October | October
TO-18-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | 5 | Planned | October | October
TO-18-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | 4 | Planned | October | October
TO-18-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | Unknown | 3 | Planned | October | October
TO-18-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | Unknown | 3 | Planned | October | October
TO-18-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | Unknown | 3 | Planned | October | October
TO-18-INC-MAY-1-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | Unknown | 46 | Planned | October | December
TO-18-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | Unknown | 61 | Planned | October | January
TO-18-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | 1 | Planned | October | October
TO-18-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | 3 | Planned | October | October
TO-18-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | 3 | Planned | October | October
TO-18-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | 1 | Planned | October | October
TO-18-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-CSH-GAL-2-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-SAL-1-02 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | 1 | Planned | October | October
TO-18-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | 3 | Planned | October | October
TO-18-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | Unknown | 5 | Planned | October | October
TO-18-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | Unknown | 3 | Planned | October | October
TO-18-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | Unknown | 8 | Planned | October | October
TO-18-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | Unknown | 3 | Planned | October | October
TO-18-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | Unknown | 5 | Planned | October | October
TO-18-TB-TRL-1-04 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | October | October
TO-18-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown |  | Reference (Planned) | October | October
TO-18-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | 1 | Planned | October | October
TO-18-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | October | October
TO-18-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | 2 | Planned | October | October
TO-18-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | Unknown | 5 | Planned | October | October
TO-18-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | 13 | Planned | October | November
TO-18-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | Unknown | 1 | Planned | October | October
TO-18-CDY-110SA1-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | 2 | Planned | October | October
TO-18-CDY-110SA2-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | 2 | Planned | October | October
TO-18-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | Unknown | 4 | Planned | October | October
TO-18-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | Unknown | 2 | Reference (Planned) | October | October
TO-18-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | 1 | Planned | October | October
TO-18-FIN GIS-T2106-09 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 2 | Planned | October | October
TO-18-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | Unknown | 3 | Planned | October | October
TO-18-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | Unknown | 3 | Planned | October | October
TO-18-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | 4 | Reference (Planned) | October | October
TO-18-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | 4 | Planned | October | October
TO-18-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | 4 | Planned | October | October
TO-18-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | 2 | Planned | October | October
TO-18-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | 2 | Planned | October | October
TO-18-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | 2 | Planned | October | October
TO-18-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-1-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-2-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-3-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | Unknown | 8 | Planned | October | November
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November
TO-18-110 kV A1/A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A3 | Unknown | 2 | Planned | November | November
TO-18-110 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2-A4 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-3-04 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | 2 | Planned | November | November
TO-18-CDU-110SA2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 2 | Planned | November | November
TO-18-110 kV B1/B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B3 | Unknown |  | Planned | November | November
TO-18-110 kV B2/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-2-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-3-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | 2 | Planned | November | November
TO-18-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 2 | Planned | November | November
TO-18-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 1 | Planned | November | November
TO-18-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 1 | Planned | November | November
TO-18-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | 1 | Planned | November | November
TO-18-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | 1 | Planned | November | November
TO-18-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | 1 | Reference (Planned) | November | November
TO-18-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | 1 | Reference (Planned) | November | November
TO-18-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November
TO-18-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SB2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SB2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | 6 | Planned | November | November
TO-18-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | 3 | Planned | November | November
TO-18-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | 2 | Planned | November | November

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AA-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G2-T102 | 57 |  | Scheduled | 18/03/2018 | 13/05/2018
TO-18-AA-DRU-1-01 | 110kV FEEDER - ARDNACRUSHA 110-DRUMLINE 110-1 | 83 | 55 | Scheduled | 20/03/2018 | 10/06/2018
TO-18-AA-T103-02 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G3-T103 | 55 | 38 | Scheduled | 15/04/2018 | 08/06/2018
TO-18-AA-110K1-2-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA 110-ARDNACRUSHA 110-110K1-2 | 54 | 38 | Scheduled | 16/04/2018 | 08/06/2018
TO-18-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | 2 | 2 | Scheduled | 30/04/2018 | 01/05/2018
TO-18-MP GIS-T4201-03 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-110 kV A2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110K2-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-AA GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-KPG-TRL-2-02 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | 8 | 5 | Scheduled | 02/05/2018 | 09/05/2018
TO-18-KPG-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA2-4CB | 1 | 1 | Scheduled | 03/05/2018 | 03/05/2018
TO-18-KPG-KNR-1-220-01 | 220kV FEEDER - KILPADDOGE 220-KNOCKANURE 220-1-220 | 58 | 40 | Scheduled | 03/05/2018 | 29/06/2018
TO-18-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | 5 | 4 | Scheduled | 07/05/2018 | 11/05/2018
TO-18-110 kV A1/A2/A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1-A2-A3 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110K2-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K2 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110K3-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-AA-T102-02 | GENERATOR TRANSFORMER - ARDNACRUSHA 110-ARDNACRUSHA G2-T102 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-KLN-110K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 110-KILLONAN 110-110K1-2 | 3 | 3 | Scheduled | 08/05/2018 | 10/05/2018
TO-18-AUG-TB-1-01 | 110kV FEEDER - AUGHINISH 110-TARBERT 110-1 | 114 | 80 | Scheduled | 10/05/2018 | 31/08/2018
TO-18-KNR-TB-1-01 | 110kV FEEDER - KNOCKANURE 110-TARBERT 110-1 | 118 | 82 | Scheduled | 10/05/2018 | 04/09/2018
TO-18-AA GIS-SNG-1-03 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-CTN-KLN-1-01 | 110kV FEEDER - CAUTEEN 110-KILLONAN 110-1 | 10 | 8 | Scheduled | 14/05/2018 | 23/05/2018
TO-18-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-AA-AA GIS-1-02 | 110kV FEEDER - ARDNACRUSHA 110-ARDNACRUSHA GIS 110-1 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-110 kV A3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-110 kV B3 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110K3-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110K3 | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-AA GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-3CB | 19 | 14 | Scheduled | 21/05/2018 | 08/06/2018
TO-18-ATE-DRO-1-01 | 110kV FEEDER - ATHEA 110-DROMADA 110-1 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-ATE-KNR-1-01 | 110kV FEEDER - ATHEA 110-KNOCKANURE 110-1 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 21/05/2018 | 21/05/2018
TO-18-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 21/05/2018 | 21/05/2018
TO-18-CTN-T141-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T141 | 3 | 3 | Reference | 21/05/2018 | 23/05/2018
TO-18-DRO-T121-01 | GENERATOR TRANSFORMER - DROMADA 110-DROMADA 20-T121 | 5 | 5 | Scheduled | 21/05/2018 | 25/05/2018
TO-18-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | 5 |  | Tentative | 21/05/2018 | 25/05/2018
TO-18-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 2 | 2 | Scheduled | 22/05/2018 | 23/05/2018
TO-18-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 2 | 2 | Scheduled | 22/05/2018 | 23/05/2018
TO-18-CTN-110SA1-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-110SA2-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | 2 | 2 | Reference | 24/05/2018 | 25/05/2018
TO-18-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | 2 | 2 | Reference | 24/05/2018 | 25/05/2018
TO-18-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 24/05/2018 | 24/05/2018
TO-18-CTN-110SA1-04 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-CTN-110SA2-04 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | 1 | 1 | Scheduled | 25/05/2018 | 25/05/2018
TO-18-AUG-CFM-1-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-1 | 1 | 1 | Scheduled | 28/05/2018 | 28/05/2018
TO-18-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | 1 | 1 | Reference | 28/05/2018 | 28/05/2018
TO-18-TB-TRL-1-01 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | 22 | 15 | Scheduled | 30/05/2018 | 20/06/2018
TO-18-110 kV A1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110A1 | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-110 kV B1 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B1 | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-2CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SA1-3CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-AA GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110SB1-2CB | 8 | 5 | Scheduled | 01/06/2018 | 08/06/2018
TO-18-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-LSN-110SA1-2-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA1-2 | 3 | 3 | Proposed | 05/06/2018 | 07/06/2018
TO-18-LSN-110SA2-4-01 | SECTIONALISING DISCONNECT - LISHEEN 110-LISHEEN 110-110SA2-4 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-LSN-T122-01 | GENERATOR TRANSFORMER - LISHEEN 110-LISHEEN 20-T122 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-LSN-T142-01 | DISTRIBUTION TRANSFORMER - LISHEEN 110-LISHEEN 38-T142 | 3 | 3 | Reference | 05/06/2018 | 07/06/2018
TO-18-LSN-THU-1-01 | 110kV FEEDER - LISHEEN 110-THURLES 110-1 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-AA GIS-T104-02 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G4-T104 | Unknown | 1 | Planned | June | June
TO-18-AA GIS-SNG-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 2 | Scheduled | 07/06/2018 | 08/06/2018
TO-18-AA GIS-SNG-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-SINGLAND 110-1 | 2 | 0 | Scheduled | 09/06/2018 | 10/06/2018
TO-18-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CKN-CGL-1-01 | 110kV FEEDER - CLONKEEN 110-COOMAGEARLAHY 110-1 | 5 |  | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-110SA1-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-110SA2-01 | SECTIONALISING DISCONNECT - COOMAGEARLAHY 110-COOMAGEARLAHY 110-110SA2 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-GAE-1-01 | 110kV FEEDER - COOMAGEARLAHY 110-GLANLEE 110-1 | 9 | 7 | Scheduled | 11/06/2018 | 19/06/2018
TO-18-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CGL-T122-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T122 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-DRU-CAP2-02 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | 2 | 2 | Proposed | 11/06/2018 | 12/06/2018
TO-18-GAE-T121-01 | GENERATOR TRANSFORMER - GLANLEE 110-GLANLEE 20-T121 | 9 | 7 | Scheduled | 11/06/2018 | 19/06/2018
TO-18-KLN-T2104-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2104 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-TB-T2004-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G4-T2004 | 1 | 1 | Scheduled | 11/06/2018 | 11/06/2018
TO-18-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 4 | 4 | Scheduled | 12/06/2018 | 15/06/2018
TO-18-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | 3 | 3 | Scheduled | 13/06/2018 | 15/06/2018
TO-18-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | 3 | 3 | Scheduled | 13/06/2018 | 15/06/2018
TO-18-ENN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 8 | 6 | Scheduled | 13/06/2018 | 20/06/2018
TO-18-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | 3 | 3 | Reference (Proposed) | 13/06/2018 | 15/06/2018
TO-18-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | 3 | 3 | Reference (Proposed) | 13/06/2018 | 15/06/2018
TO-18-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 | Scheduled | 18/06/2018 | 29/06/2018
TO-18-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | Scheduled | 18/06/2018 | 19/06/2018
TO-18-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-ENN-T102-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T102 | 3 | 3 | Reference | 18/06/2018 | 20/06/2018
TO-18-ENN-T142-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T142 | 3 | 3 | Reference | 18/06/2018 | 20/06/2018
TO-18-KLN-220K1-2-01 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-KLN-220K1-2-02 | COUPLER/SECTIONALISING CB - KILLONAN 220-KILLONAN 220-220K1-2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-110SA1-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA1 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-110SA2-01 | SECTIONALISING DISCONNECT - SLIEVECALLAN 110-SLIEVECALLAN 110-110SA2 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-SLC-T122-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T122 | 3 | 3 | Scheduled | 18/06/2018 | 20/06/2018
TO-18-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | 1 | 1 | Reference (Proposed) | 25/06/2018 | 25/06/2018
TO-18-SNG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SINGLAND 110-SINGLAND 110-110SA1-2CB | 3 | 3 | Proposed | 25/06/2018 | 27/06/2018
TO-18-220 kV A2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | 5 | 5 | Proposed | 25/06/2018 | 29/06/2018
TO-18-TB-T2102-01 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 117 | 84 | Proposed | 25/06/2018 | 19/10/2018
TO-18-TB-T2102-02 | TRANSFORMER - TARBERT 220-TARBERT 110-T2102 | 117 | 84 | Proposed | 25/06/2018 | 19/10/2018
TO-18-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | 5 | Planned | July | July
TO-18-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | 15 | Planned | July | July
TO-18-KNR-TRI-2-02 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | 15 | Planned | July | July
TO-18-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | 5 | Planned | July | July
TO-18-220 kV B2 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | 8 | Planned | July | July
TO-18-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | Unknown | 2 | Planned | July | July
TO-18-BYH-110K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K1 | Unknown | 1 | Planned | July | July
TO-18-BYH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-CBA-110SA1-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA1 | Unknown | 1 | Planned | July | July
TO-18-CBA-110SA2-02 | SECTIONALISING DISCONNECT - CLOGHBOOLA 110-CLOGHBOOLA 110-110SA2 | Unknown | 1 | Planned | July | July
TO-18-CBA-T122-01 | DISTRIBUTION TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 20-T122 | Unknown | 1 | Reference (Planned) | July | July
TO-18-CBA-T131-02 | GENERATOR TRANSFORMER - CLOGHBOOLA 110-CLOGHBOOLA 30-T131 | Unknown | 1 | Planned | July | July
TO-18-CBA-TRI-1-02 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | 1 | Planned | July | July
TO-18-MP-OST-1-04 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 74 | Planned | July | October
TO-18-MP-OST-1-05 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown |  | Planned | July | November
TO-18-MP-OST-1-02 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-BYH-110K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110K2 | Unknown | 1 | Planned | July | July
TO-18-BYH-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 110-BALLYNAHULLA 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-BVK-220K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K1 | Unknown | 1 | Planned | July | July
TO-18-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | 1 | Planned | July | July
TO-18-220 kV A2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | 40 | Planned | July | September
TO-18-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 5 | Planned | July | July
TO-18-KPG-110K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K3 | Unknown | 1 | Planned | July | July
TO-18-KPG-110K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110K4 | Unknown |  | Planned | July | July
TO-18-THU-CAP2-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP2 | Unknown | 5 | Planned | July | July
TO-18-KPG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA1-3CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220K3-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K3 | Unknown | 1 | Planned | July | July
TO-18-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | Unknown | 1 | Planned | July | July
TO-18-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220K4-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220K4 | Unknown | 1 | Planned | July | July
TO-18-IKE-T141-02 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | 2 | Reference (Planned) | July | July
TO-18-IKE,T-IKE-1-02 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | 2 | Planned | July | July
TO-18-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | 2 | Planned | July | July
TO-18-IKE,T-THU-1-02 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | 2 | Planned | July | July
TO-18-MP-T4001-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown |  | Planned | July | November
TO-18-MP-T4001-02 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G1-T4001 | Unknown | 83 | Planned | July | November
TO-18-KPG-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KPG-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SA1-3CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K1 | Unknown | 1 | Planned | July | July
TO-18-KNR-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-TB-TRL-1-02 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | July | July
TO-18-KNR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-KNR-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-BYH-220K1-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K1 | Unknown | 1 | Planned | July | July
TO-18-BYH-220K2-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220K2 | Unknown | 1 | Planned | July | July
TO-18-KHL-T131-01 | GENERATOR TRANSFORMER - KILL HILL 110-KILL HILL 33-T131 | Unknown | 1 | Planned | July | July
TO-18-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-400 kV B1 @ MP-01 | BUSBAR SECTION - MONEYPOINT 400-MONEYPOINT 400-400B1 | Unknown | 5 | Planned | July | August
TO-18-MP-400K1-2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT 400-MONEYPOINT 400-400K1-2 | Unknown | 8 | Planned | July | August
TO-18-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | Unknown | 1 | Planned | July | July
TO-18-THU-CAP1-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-CAP1 | Unknown |  | Planned | July | August
TO-18-BYH-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SA1-2CB | Unknown | 1 | Planned | July | July
TO-18-BYH-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYNAHULLA 220-BALLYNAHULLA 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | 1 | Planned | August | August
TO-18-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-BOL-T121-02 | GENERATOR TRANSFORMER - BOOLTIAGH 110-BOOLTIAGH 20-T121 | Unknown | 1 | Planned | August | August
TO-18-CLH-110SA1-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA1 | Unknown | 2 | Planned | August | August
TO-18-CLH-110SA2-01 | SECTIONALISING DISCONNECT - CLAHANE 110-CLAHANE 110-110SA2 | Unknown | 2 | Planned | August | August
TO-18-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | 2 | Planned | August | August
TO-18-CLH-TRL-1-02 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | 2 | Planned | August | August
TO-18-CLH-TRI-1-01 | 110kV FEEDER - CLAHANE 110-TRIEN 110-1 | Unknown | 4 | Planned | August | August
TO-18-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | 7 | Planned | August | August
TO-18-BVK-110K1-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K1 | Unknown | 1 | Planned | August | August
TO-18-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-KNR-110K4-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110K4 | Unknown | 1 | Planned | August | August
TO-18-KNR-220K2-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K2 | Unknown | 1 | Planned | August | August
TO-18-TRI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-2CB | Unknown | 3 | Planned | August | August
TO-18-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | 8 | Planned | August | August
TO-18-KPG-TB-1-02 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | 8 | Planned | August | August
TO-18-KNR-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220K1 | Unknown | 1 | Planned | August | August
TO-18-KNR-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 220-KNOCKANURE 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SB1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | 1 | Planned | August | August
TO-18-TRI-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - TRIEN 110-TRIEN 110-110SA1-3CB | Unknown | 3 | Planned | August | August
TO-18-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220K1-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K1 | Unknown | 1 | Planned | August | August
TO-18-MP GIS-220K2-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 220-MONEYPOINT GIS 220-220K2 | Unknown | 1 | Planned | August | August
TO-18-MP-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT 400-MONEYPOINT G2-T4002 | Unknown | 5 | Planned | August | August
TO-18-MP GIS-400K3-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K3 | Unknown | 1 | Planned | August | August
TO-18-MP GIS-400K4-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400K4 | Unknown | 1 | Planned | August | August
TO-18-KHL-THU-1-01 | 110kV FEEDER - KILL HILL 110-THURLES 110-1 | Unknown | 6 | Planned | August | September
TO-18-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | 2 | 2 | Proposed | 28/08/2018 | 29/08/2018
TO-18-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | 5 | Planned | September | September
TO-18-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 3 | Planned | September | September
TO-18-220 kV B2 @ TB-02 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B2 | Unknown | 19 | Planned | September | October
TO-18-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | 5 | Planned | September | September
TO-18-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | 5 | Planned | September | September
TO-18-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | 3 | 3 | Reference | 10/09/2018 | 12/09/2018
TO-18-SK-T103-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G3-T103 | Unknown | 5 | Planned | September | September
TO-18-AA GIS-LIM-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-LIMERICK 110-1 | Unknown | 4 | Planned | September | September
TO-18-KNR-TRI-1-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-1 | Unknown | 1 | Planned | September | September
TO-18-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | 1 | Planned | September | September
TO-18-KLN-LIM-2-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-2 | Unknown | 2 | Planned | September | September
TO-18-REM-110SA1-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA1 | Unknown | 5 | Planned | September | September
TO-18-REM-110SA2-01 | SECTIONALISING DISCONNECT - REAMORE 110-REAMORE 110-110SA2 | Unknown | 5 | Planned | September | September
TO-18-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | 5 | Reference (Planned) | September | September
TO-18-REM-T142-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T142 | Unknown | 5 | Reference (Planned) | September | September
TO-18-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | 5 | Reference (Planned) | September | September
TO-18-CLH-TRL-1-01 | 110kV FEEDER - CLAHANE 110-TRALEE 110-1 | Unknown | 3 | Planned | September | September
TO-18-TB-TRL-1-06 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | September | September
TO-18-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | 5 | Planned | September | September
TO-18-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-TRL-CAP2-02 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-TRL-T141-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T141 | Unknown | 3 | Reference (Planned) | September | September
TO-18-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 3 | Planned | September | September
TO-18-KPG-TRL-2-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-2 | Unknown | 3 | Planned | September | September
TO-18-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | 2 | Planned | September | September
TO-18-TRL-T142-01 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | Unknown | 2 | Reference (Planned) | September | September
TO-18-TBK-T142-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T142 | Unknown | 3 | Reference (Planned) | September | September
TO-18-TBK,T-BOL-1-01 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-BOL-1-03 | 110kV FEEDER - TULLABRACK tee-BOOLTIAGH 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-MP GIS-1-01 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-MP GIS-1-03 | 110kV FEEDER - TULLABRACK tee-MONEYPOINT GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-TBK,T-TBK-1-01 | 110kV FEEDER - TULLABRACK tee-TULLABRACK 110-1 | Unknown | 3 | Planned | September | September
TO-18-KLN-TB-1-01 | 220kV FEEDER - KILLONAN 220-TARBERT 220-1 | Unknown | 2 | Planned | September | September
TO-18-220 kV A2 @ TB-03 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A2 | Unknown | 5 | Planned | October | October
TO-18-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | Unknown | 3 | Planned | October | October
TO-18-THU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - THURLES 110-THURLES 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | Unknown | 5 | Planned | October | October
TO-18-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | Unknown | 3 | Planned | October | October
TO-18-TB-TRL-1-04 | 110kV FEEDER - TARBERT 110-TRALEE 110-1 | Unknown | 3 | Planned | October | October
TO-18-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | 2 | Planned | October | October
TO-18-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | Unknown | 5 | Planned | October | October
TO-18-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | 4 | Reference (Planned) | October | October
TO-18-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | 4 | Planned | October | October
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-MP GIS-T4201-01 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November
TO-18-MP GIS-T4201-02 | TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS 220-T4201 | Unknown | 2 | Planned | November | November

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 65 | 45 | Scheduled | 09/04/2018 | 12/06/2018
TO-18-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | 12 | 10 | Scheduled | 23/04/2018 | 04/05/2018
TO-18-110 kV A2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | 22 | 15 | Scheduled | 30/04/2018 | 21/05/2018
TO-18-110 kV B2 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | 22 | 15 | Scheduled | 30/04/2018 | 21/05/2018
TO-18-BWR-T124-03 | GENERATOR TRANSFORMER - BALLYWATER 110-BALLYWATER 20-T124 | 2 | 2 | Reference | 01/05/2018 | 02/05/2018
TO-18-BWR-CRA-1-02 | 110kV FEEDER - BALLYWATER 110-CRANE 110-1 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-BLK-T142-03 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference | 08/05/2018 | 08/05/2018
TO-18-BLK,T-BLK-1-03 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Scheduled | 08/05/2018 | 08/05/2018
TO-18-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 11 | 9 | Scheduled | 08/05/2018 | 18/05/2018
TO-18-LWD-220K1-2-01 | COUPLER/SECTIONALISING CB - LODGEWOOD 220-LODGEWOOD 220-220K1-2 | 3 | 3 | Scheduled | 08/05/2018 | 10/05/2018
TO-18-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | 2 | 2 | Scheduled | 09/05/2018 | 10/05/2018
TO-18-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | 2 | 0 | Reference | 12/05/2018 | 13/05/2018
TO-18-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 2 | 0 | Scheduled | 12/05/2018 | 13/05/2018
TO-18-CUL-T2101-01 | TRANSFORMER - CULLENAGH 220-CULLENAGH 110-T2101 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-BLK-T142-04 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 1 | 1 | Reference | 18/05/2018 | 18/05/2018
TO-18-BLK,T-BLK-1-04 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 1 | 1 | Scheduled | 18/05/2018 | 18/05/2018
TO-18-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 3 | 3 | Reference (Tentative) | 21/05/2018 | 23/05/2018
TO-18-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-BLK,T-NEW-1-03 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-GI-110K1-2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | 112 |  | Scheduled | 22/05/2018 | 10/09/2018
TO-18-GI-T2102-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-GI-WAT-2-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-GI-WEX-1-02 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 22 | 15 | Scheduled | 22/05/2018 | 12/06/2018
TO-18-CUS-PLS-1-02 | 110kV FEEDER - CUSHALING 110-PORTLAOISE 110-1 | 29 | 20 | Scheduled | 01/06/2018 | 29/06/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 4 | Scheduled | 04/06/2018 | 08/06/2018
TO-18-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-GI-KKY-1-03 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-ST101-03 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-ST101-01 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 21 | 15 | Reference | 13/06/2018 | 03/07/2018
TO-18-GI-T2101-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-T2101-04 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-GI-WAT-1-04 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 21 | 15 | Scheduled | 13/06/2018 | 03/07/2018
TO-18-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-ANR-T101-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ANR-T103-01 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 1 | Reference (Planned) | June | June
TO-18-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-CAH-TIP-1-02 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | Scheduled | 18/06/2018 | 19/06/2018
TO-18-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | 1 | Planned | June | June
TO-18-DOO-110SA2-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | Unknown | 1 | Planned | June | June
TO-18-DOO-CAP1-01 | CAPACITOR/SVC/REACTOR - DOON 110-DOON 110-CAP1 | Unknown | 5 | Planned | June | June
TO-18-DOO-T141-01 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ANR-DOO-1-02 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | 1 | Reference (Planned) | June | June
TO-18-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | 1 | Reference (Planned) | June | June
TO-18-BDN-DOO-1-02 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 1 | Planned | June | June
TO-18-DOO-110SA1-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | 1 | Planned | June | June
TO-18-DOO-110SA2-02 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA2 | Unknown | 1 | Planned | June | June
TO-18-DOO-T141-02 | DISTRIBUTION TRANSFORMER - DOON 110-DOON 38-T141 | Unknown | 1 | Reference (Planned) | June | June
TO-18-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-CUS-T101-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G1-T101 | 5 | 5 | Proposed | 25/06/2018 | 29/06/2018
TO-18-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 4 | 4 | Proposed | 25/06/2018 | 28/06/2018
TO-18-WOH-110SA1-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA1 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-WOH-110SA2-01 | SECTIONALISING DISCONNECT - WOODHOUSE 110-WOODHOUSE 110-110SA2 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | 1 | 1 | Proposed | 25/06/2018 | 25/06/2018
TO-18-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | 2 | 2 | Proposed | 28/06/2018 | 29/06/2018
TO-18-CAH-CAP2/4-01 | CAPACITOR/SVC/REACTOR - CAHIR 110-CAHIR 110-CAP2/4 | Unknown | 5 | Planned | July | July
TO-18-DGN-WOH-1-04 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 3 | Planned | July | July
TO-18-DGN-WOH-1-03 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | 3 | Planned | July | July
TO-18-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | 4 | Planned | July | July
TO-18-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 20 | Planned | July | August
TO-18-CUS-NEW-1-02 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | 20 | Planned | July | August
TO-18-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | 1 | Planned | July | July
TO-18-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | 2 | Planned | July | July
TO-18-ATY-PLS-1-01 | 110kV FEEDER - ATHY 110-PORTLAOISE 110-1 | Unknown | 20 | Planned | July | August
TO-18-BDN-DOO-1-03 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | 10 | Planned | July | July
TO-18-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | Unknown | 4 | Planned | July | July
TO-18-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | Unknown | 4 | Planned | July | July
TO-18-BDN-110SA1-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | 3 | Planned | July | July
TO-18-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | 3 | Planned | July | July
TO-18-BDN-MRK3-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | 5 | Planned | July | July
TO-18-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | 6 | Planned | July | July
TO-18-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | 3 | Planned | July | July
TO-18-BDN-110SA2-02 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | 3 | Planned | July | July
TO-18-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | Unknown | 7 | Planned | July | August
TO-18-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | 3 | Planned | July | July
TO-18-BDN-T141-01 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | Unknown | 3 | Reference (Planned) | July | July
TO-18-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-GI-WAT-2-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-GI-WEX-1-07 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | 22 |  | Scheduled | 30/07/2018 | 20/08/2018
TO-18-BDA-MON-1-01 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | 2 | Planned | August | August
TO-18-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 4 | Planned | August | August
TO-18-CUL-DGN-1-01 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 4 | Planned | August | August
TO-18-CUL-DGN-1-02 | 110kV FEEDER - CULLENAGH 110-DUNGARVAN 110-1 | Unknown | 4 | Planned | August | August
TO-18-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | 4 | Planned | August | August
TO-18-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | 4 | Planned | August | August
TO-18-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | 4 | Reference (Planned) | August | August
TO-18-KLS-110K1-2-01 | COUPLER/SECTIONALISING CB - KELLIS 110-KELLIS 110-110K1-2 | Unknown | 3 | Planned | August | August
TO-18-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | Unknown | 1 | Planned | August | August
TO-18-GI-ST101-02 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | Unknown |  | Planned | August | December
TO-18-GI-110K1-2-04 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | 15 | Planned | August | September
TO-18-GI-KKY-1-02 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | Unknown |  | Planned | August | October
TO-18-GI-KKY-1-04 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-ST101-04 | GENERATOR TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND G1-ST101 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-T141-04 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | 63 | 45 | Reference | 21/08/2018 | 22/10/2018
TO-18-GI-T141-02 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | Unknown |  | Reference (Planned) | August | September
TO-18-GI-T2101-02 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | Unknown |  | Planned | August | September
TO-18-GI-T2101-05 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-GI-WAT-1-02 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown |  | Planned | August | September
TO-18-GI-WAT-1-06 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | 63 | 45 | Scheduled | 21/08/2018 | 22/10/2018
TO-18-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | Unknown | 2 | Planned | August | August
TO-18-ARK-CKM GIS-1-05 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 2 | Planned | August | August
TO-18-ARK-CKM GIS-1-04 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 7 | Planned | September | September
TO-18-GI-WEX-1-08 | 110kV FEEDER - GREAT ISLAND 110-WEXFORD 110-1 | Unknown | 10 | Planned | September | September
TO-18-WEX-110SA1-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA1 | Unknown | 10 | Planned | September | September
TO-18-WEX-110SA2-01 | SECTIONALISING DISCONNECT - WEXFORD 110-WEXFORD 110-110SA2 | Unknown | 10 | Planned | September | September
TO-18-WEX-T141-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T141 | Unknown | 10 | Reference (Planned) | September | September
TO-18-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-PLS-110K1-2-01 | COUPLER/SECTIONALISING CB - PORTLAOISE 110-PORTLAOISE 110-110K1-2 | Unknown | 7 | Planned | September | September
TO-18-110 kV A1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A1 | Unknown | 15 | Planned | September | October
TO-18-110 kV B1 @ GI-01 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B1 | Unknown | 15 | Planned | September | October
TO-18-CUL-GI GIS-1-01 | 220kV FEEDER - CULLENAGH 220-GREAT ISLAND GIS 220-1 | Unknown | 7 | Planned | September | September
TO-18-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | 6 | Planned | September | September
TO-18-BUT-KTN-1-01 | 110kV FEEDER - BUTLERSTOWN 110-KILLOTERAN 110-1 | Unknown | 5 | Planned | September | September
TO-18-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | Unknown | 4 | Planned | September | September
TO-18-GI GIS-T2004-01 | GENERATOR TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND GIS G4-T2004 | Unknown | 1 | Planned | October | October
TO-18-GI-110K1-2-03 | COUPLER/SECTIONALISING CB - GREAT ISLAND 110-GREAT ISLAND 110-110K1-2 | Unknown | 15 | Planned | October | October
TO-18-GI-T141-03 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | Unknown | 15 | Reference (Planned) | October | October
TO-18-GI-T2101-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2101 | Unknown | 15 | Planned | October | October
TO-18-GI-WAT-1-03 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown | 15 | Planned | October | October
TO-18-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-CUL-110K1-2-01 | COUPLER/SECTIONALISING CB - CULLENAGH 110-CULLENAGH 110-110K1-2 | Unknown | 3 | Planned | October | October
TO-18-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | 4 | Planned | October | October
TO-18-DAL,T-PLS-1-01 | 110kV FEEDER - DALLOW tee-PORTLAOISE 110-1 | Unknown | 4 | Planned | October | October

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-CBR-110SA1-02 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-CBR-110SA2-02 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 84 | 57 | Scheduled | 02/04/2018 | 24/06/2018
TO-18-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 114 | 80 | Scheduled | 03/04/2018 | 25/07/2018
TO-18-COS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICK ON SHANNON 110-CARRICK ON SHANNON 110-110SA1-2CB | 114 | 80 | Scheduled | 03/04/2018 | 25/07/2018
TO-18-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | 114 |  | Scheduled | 03/04/2018 | 25/07/2018
TO-18-COS-T141-01 | DISTRIBUTION TRANSFORMER - CARRICK ON SHANNON 110-CARRICK ON SHANNON 38-T141 | 114 | 80 | Reference | 03/04/2018 | 25/07/2018
TO-18-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-CLO-1-01 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 4 | 4 | Scheduled | 30/04/2018 | 03/05/2018
TO-18-SLI-SRA-1-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-1 | 2 | 2 | Scheduled | 30/04/2018 | 01/05/2018
TO-18-CSH-T2104-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 4 | 4 | Scheduled | 08/05/2018 | 11/05/2018
TO-18-CF-CLO-2-02 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | 5 | 3 | Scheduled | 09/05/2018 | 13/05/2018
TO-18-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 3 | 1 | Scheduled | 11/05/2018 | 13/05/2018
TO-18-CSH-T2102-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 19 | 15 | Scheduled | 14/05/2018 | 01/06/2018
TO-18-DRM-110SA1-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-110SA2-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-LET-1-03 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-DRM-MEE-1-01 | 110kV FEEDER - DRUMKEEN 110-MEENTYCAT 110-1 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-MEE-T121-01 | GENERATOR TRANSFORMER - MEENTYCAT 110-MEENTYCAT 20-T121 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-DRM-110SA1-02 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA1 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-DRM-110SA2-01 | SECTIONALISING DISCONNECT - DRUMKEEN 110-DRUMKEEN 110-110SA2 | 2 | 2 | Scheduled | 16/05/2018 | 17/05/2018
TO-18-BIN-LET-1-02 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-BIN-LET-1-03 | 110kV FEEDER - BINBANE 110-LETTERKENNY 110-1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-110SA1-2-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-110SA1-2-SA2-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-110SA1-3-SA1-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA1 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-LET-110SA1-3-SA3-01 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA3 | 89 | 63 | Scheduled | 04/06/2018 | 31/08/2018
TO-18-LET-M/CAP1-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-PST-01 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-SVC-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 0 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-LET-T141-01 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 0 | Reference | 04/06/2018 | 04/06/2018
TO-18-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-KNY-SAL-1-02 | 110kV FEEDER - KNOCKRANNY-SALTHILL 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | 5 | 5 | Proposed | 11/06/2018 | 15/06/2018
TO-18-GAL-SAL-1-01 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 4 | 4 | Scheduled | 12/06/2018 | 15/06/2018
TO-18-OST-T4202-03 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | 2 | 2 | Trip Testing | 14/06/2018 | 15/06/2018
TO-18-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 12 | 10 | Scheduled | 18/06/2018 | 29/06/2018
TO-18-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 5 | 5 | Scheduled | 18/06/2018 | 22/06/2018
TO-18-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 50 | 35 | Proposed | 20/06/2018 | 08/08/2018
TO-18-CF-T104-02 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | 50 | 35 | Scheduled | 20/06/2018 | 08/08/2018
TO-18-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | 3 | 1 | Scheduled | 22/06/2018 | 24/06/2018
TO-18-CBR-SVC-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | 3 | 1 | Scheduled | 22/06/2018 | 24/06/2018
TO-18-CBR-T141-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | 3 | 1 | Reference | 22/06/2018 | 24/06/2018
TO-18-KNY-FILTER1-01 | CAPACITOR/SVC/REACTOR - KNOCKRANNY 110-KNOCKRANNY 110-FILTER1 | 1 | 0 | Scheduled | 23/06/2018 | 23/06/2018
TO-18-CBG-CBR-1-02 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CBG-T142-02 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CSH-SAL-1-02 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-CBR-110SA1-03 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-110SA2-03 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-CAP2-02 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | 1 | 1 | Scheduled | 25/06/2018 | 25/06/2018
TO-18-CBR-DLT-1-02 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-CBR-DLT-1-04 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-CBR-T142-02 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | 1 | 1 | Reference | 25/06/2018 | 25/06/2018
TO-18-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 3 | 3 | Scheduled | 25/06/2018 | 27/06/2018
TO-18-CSH-CAP1-02 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | Unknown | 6 | Planned | July | July
TO-18-CUN-110SA1-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA1 | Unknown | 2 | Planned | July | July
TO-18-CUN-110SA2-01 | SECTIONALISING DISCONNECT - CUNGHILL 110-CUNGHILL 110-110SA2 | Unknown | 2 | Planned | July | July
TO-18-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | 2 | Planned | July | July
TO-18-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | 2 | Planned | July | July
TO-18-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-BK-CBR-1-03 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 0 | Planned | July | July
TO-18-CBR-110SA1-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | Unknown | 0 | Planned | July | July
TO-18-CBR-110SA2-05 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | Unknown | 0 | Planned | July | July
TO-18-CBR-CLN-1-04 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 0 | Planned | July | July
TO-18-CBR-SVC-04 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 0 | Planned | July | July
TO-18-CBR-T141-04 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | Unknown | 0 | Reference (Planned) | July | July
TO-18-CBR-CLN-1-05 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-09 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-10 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-CLN-1-11 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | 24 | Planned | July | August
TO-18-CBR-SVC-05 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 24 | Planned | July | August
TO-18-CBR-SVC-07 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | Unknown | 24 | Planned | July | August
TO-18-CBR-T141-05 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T141 | Unknown | 24 | Reference (Planned) | July | August
TO-18-MP-OST-1-01 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown |  | Planned | July | November
TO-18-MP-OST-1-02 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-MP-OST-1-04 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 74 | Planned | July | October
TO-18-MP-OST-1-05 | 400kV FEEDER - MONEYPOINT 400-OLDSTREET 400-1 | Unknown | 83 | Planned | July | November
TO-18-OST-400SA1-02 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown | 74 | Planned | July | October
TO-18-OST-400SA1-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA1 | Unknown |  | Planned | July | October
TO-18-OST-400SA2-01 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown |  | Planned | July | October
TO-18-OST-400SA2-02 | SECTIONALISING DISCONNECT - OLDSTREET 400-OLDSTREET 400-400SA2 | Unknown | 74 | Planned | July | October
TO-18-OST-T4202-01 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown |  | Planned | July | October
TO-18-OST-T4202-04 | TRANSFORMER - OLDSTREET 400-OLDSTREET 220-T4202 | Unknown | 74 | Planned | July | October
TO-18-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 74 | Planned | July | October
TO-18-OST-TY-1-03 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | 0 | Planned | July | July
TO-18-CLN-110SA1-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | 0 | Planned | July | July
TO-18-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | Unknown | 0 | Planned | July | July
TO-18-CLN-T141-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | Unknown | 0 | Reference (Planned) | July | July
TO-18-110 kV A2 @ CF-01 | BUSBAR SECTION - CATHALEENS FALL 110-CATHALEENS FALL 110-110A2 | Unknown | 2 | Planned | July | July
TO-18-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY-UGGOOL 110-1 | Unknown | 3 | Planned | July | July
TO-18-TAW-T1/T2-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T1/T2 | Unknown | 2 | Reference (Planned) | July | July
TO-18-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | 3 | Planned | July | July
TO-18-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | 3 | Planned | July | July
TO-18-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | 3 | Planned | July | July
TO-18-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | 3 | Planned | July | July
TO-18-ARI-T121-01 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown |  | Reference (Planned) | July | July
TO-18-ARI,T-ARI-1-01 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | 1 | Planned | July | July
TO-18-ARI,T-COS-1-01 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | 60 | Planned | July | October
TO-18-ARI,T-COS-1-02 | 110kV FEEDER - ARIGNA tee-CARRICK ON SHANNON 110-1 | Unknown | 60 | Planned | July | October
TO-18-ARI,T-CDY-1-01 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | July | July
TO-18-ARI,T-CDY-1-04 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | July | July
TO-18-ARI,T-CDY-1-03 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 2 | Planned | July | July
TO-18-CDY-110SA1-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | 2 | Planned | July | July
TO-18-CDY-110SA2-01 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | 2 | Planned | July | July
TO-18-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | Unknown | 2 | Planned | July | July
TO-18-CDY-T121-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T121 | Unknown | 2 | Reference (Planned) | July | July
TO-18-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | Unknown | 2 | Planned | July | July
TO-18-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | 2 | Planned | July | July
TO-18-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 38-T141 | Unknown | 2 | Reference (Planned) | July | July
TO-18-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | 2 | Planned | July | July
TO-18-SRA-110K1-2-01 | COUPLER/SECTIONALISING CB - SRANANAGH 110-SRANANAGH 110-110K1-2 | Unknown | 5 | Planned | July | August
TO-18-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | 1 | Planned | August | August
TO-18-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | 1 | Reference (Planned) | August | August
TO-18-GAL-KNY-1-02 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | Unknown | 9 | Planned | August | August
TO-18-CF-SRA-2-02 | 110kV FEEDER - CATHALEENS FALL 110-SRANANAGH 110-2 | Unknown | 1 | Planned | August | August
TO-18-BK-CBR-1-04 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | 0 | Planned | August | August
TO-18-CBR-110SA1-06 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA1 | Unknown | 0 | Planned | August | August
TO-18-CBR-110SA2-06 | SECTIONALISING DISCONNECT - CASTLEBAR 110-CASTLEBAR 110-110SA2 | Unknown | 0 | Planned | August | August
TO-18-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | 4 | Planned | August | August
TO-18-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | 5 | Planned | August | August
TO-18-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | 2 | Planned | August | August
TO-18-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | 2 | Reference (Planned) | August | August
TO-18-GLR-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 6 | Planned | August | August
TO-18-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 10 | Planned | August | August
TO-18-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | 10 | Planned | August | August
TO-18-GLR-MOY-1-03 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | 6 | Planned | August | August
TO-18-GLR-T142-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T142 | Unknown | 4 | Reference (Planned) | August | August
TO-18-KNY-110K2-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K2 | Unknown | 1 | Planned | August | August
TO-18-KNY-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-KNY-110K1-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110K1 | Unknown | 1 | Planned | August | August
TO-18-KNY-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRANNY 110-KNOCKRANNY 110-110SA1-2CB | Unknown | 1 | Planned | August | August
TO-18-LET-TLK-1-01 | 110kV FEEDER - LETTERKENNY 110-TRILLICK 110-1 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-T122-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T122 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-T124-01 | DISTRIBUTION TRANSFORMER - SORNE HILL 110-SORNE HILL 20-T124 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOR-TLK-1-01 | 110kV FEEDER - SORNE HILL 110-TRILLICK 110-1 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-TLK-T141-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T141 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-TLK-T142-01 | DISTRIBUTION TRANSFORMER - TRILLICK 110-TRILLICK 38-T142 | 17 | 13 | Reference | 15/08/2018 | 31/08/2018
TO-18-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown |  | Planned | August | August
TO-18-CSH-GAL-2-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | Unknown | 7 | Planned | August | September
TO-18-CSH-T2101-02 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | 6 | Planned | August | September
TO-18-CSH-TY-1-02 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | 4 | Planned | August | September
TO-18-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-TY-220SA1-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA1 | Unknown | 4 | Planned | August | September
TO-18-TY-220SA2-01 | SECTIONALISING DISCONNECT - TYNAGH 220-TYNAGH 220-220SA2 | Unknown | 4 | Planned | August | September
TO-18-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | 4 | Planned | August | September
TO-18-DRM-LET-1-02 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-2-SA1-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-2-SA2-02 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-3-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-110SA1-3-SA3-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-3-SA3 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-M/CAP1-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-M/CAP1 | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-PST-02 | TRANSFORMER - LETTERKENNY 110-STRABANE 110-PST | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-SVC-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-SVC | 1 | 0 | Scheduled | 01/09/2018 | 01/09/2018
TO-18-LET-T141-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T141 | 1 | 0 | Reference | 01/09/2018 | 01/09/2018
TO-18-AGL-DYN-1-01 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | 3 | Planned | September | September
TO-18-AGL-DYN-1-02 | 110kV FEEDER - AGANNYGAL 110-DERRYBRIEN 110-1 | Unknown | 3 | Planned | September | September
TO-18-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | 3 | Reference (Planned) | September | September
TO-18-GOL,T-LET-1-01 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-110SA1-2-SA1-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA1 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-110SA1-2-SA2-03 | SECTIONALISING DISCONNECT - LETTERKENNY 110-LETTERKENNY 110-110SA1-2-SA2 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | 3 | 3 | Scheduled | 03/09/2018 | 05/09/2018
TO-18-LET-CAP2-02 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | 5 | Planned | September | September
TO-18-LET-T142-02 | DISTRIBUTION TRANSFORMER - LETTERKENNY 110-LETTERKENNY 38-T142 | 3 | 3 | Reference | 03/09/2018 | 05/09/2018
TO-18-CSH-GAL-3-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | Unknown | 7 | Planned | September | September
TO-18-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | 3 | Planned | September | September
TO-18-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | 10 | Planned | September | September
TO-18-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | 4 | Planned | September | September
TO-18-CF-T104-03 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | 4 | Planned | September | September
TO-18-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-SAL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SALTHILL 110-SALTHILL 110-110SA1-2CB | Unknown | 5 | Planned | September | September
TO-18-CSH-GAL-1-02 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | Unknown | 1 | Planned | September | September
TO-18-CLO-110K1-2-01 | COUPLER/SECTIONALISING CB - CLOGHER 110-CLOGHER 110-110K1-2 | Unknown | 2 | Planned | September | September
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-GLR-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | 7 | Planned | October | October
TO-18-GLR-MOY-1-02 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown |  | Planned | October | October
TO-18-CSH-220K2-4-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K2-4 | Unknown | 3 | Planned | October | October
TO-18-GAL-110K1-2-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | Unknown | 3 | Planned | October | October
TO-18-CSH-GAL-1-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-CSH-GAL-2-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-CSH-GAL-3-01 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K1-2-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-2 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K1-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-110K2-3-01 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-KNY-1-01 | 110kV FEEDER - GALWAY-KNOCKRANNY 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-GAL-SAL-1-02 | 110kV FEEDER - GALWAY 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 11/10/2018 | 12/10/2018
TO-18-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-GAL-110K1-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K1-3 | Unknown | 3 | Planned | October | October
TO-18-TAW-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TAWNAGHMORE 110-TAWNAGHMORE 110-110SA1-2CB | Unknown | 3 | Planned | October | October
TO-18-ARI-T121-02 | DISTRIBUTION TRANSFORMER - ARIGNA 110-ARIGNA 20-T121 | Unknown |  | Reference (Planned) | October | October
TO-18-ARI,T-ARI-1-02 | 110kV FEEDER - ARIGNA tee-ARIGNA 110-1 | Unknown | 1 | Planned | October | October
TO-18-ARI,T-CDY-1-02 | 110kV FEEDER - ARIGNA tee-CORDERRY 110-1 | Unknown | 1 | Planned | October | October
TO-18-COS-FLA-2-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-2 | Unknown | 13 | Planned | October | November
TO-18-CDY-110SA1-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA1 | Unknown | 2 | Planned | October | October
TO-18-CDY-110SA2-02 | SECTIONALISING DISCONNECT - CORDERRY 110-CORDERRY 110-110SA2 | Unknown | 2 | Planned | October | October
TO-18-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | Unknown | 4 | Planned | October | October
TO-18-CDY-T122-01 | DISTRIBUTION TRANSFORMER - CORDERRY 110-CORDERRY 20-T122 | Unknown | 2 | Reference (Planned) | October | October
TO-18-GAL-110K2-3-02 | COUPLER/SECTIONALISING CB - GALWAY 110-GALWAY 110-110K2-3 | Unknown | 3 | Planned | October | October
TO-18-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-DLT-1-01 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-1-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-2-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-2 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-GAL-3-03 | 110kV FEEDER - CASHLA 110-GALWAY 110-3 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-CSH-T2104-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2104 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | 114 | 80 | Scheduled | 03/04/2018 | 25/07/2018
TO-18-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | 10 | 7 | Scheduled | 30/04/2018 | 09/05/2018
TO-18-CDU-PLA-1-04 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-RRU-T122-02 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | 7 | 5 | Scheduled | 08/05/2018 | 14/05/2018
TO-18-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | 7 | 5 | Reference | 08/05/2018 | 14/05/2018
TO-18-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-LA-MUL-1-02 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | 8 | 6 | Scheduled | 21/05/2018 | 28/05/2018
TO-18-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | 3 | 3 | Scheduled | 28/05/2018 | 30/05/2018
TO-18-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-GOR-220K1-2-01 | COUPLER/SECTIONALISING CB - GORMAN 220-GORMAN 220-220K1-2 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | 2 | 2 | Scheduled | 05/06/2018 | 06/06/2018
TO-18-DFR-T122-04 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | 2 | 0 | Reference | 09/06/2018 | 10/06/2018
TO-18-DFR,T-DFR-1-04 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | 2 | 0 | Proposed | 09/06/2018 | 10/06/2018
TO-18-DFR,T-KIN-1-02 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | 2 | 2 | Proposed | 09/06/2018 | 10/06/2018
TO-18-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 0 | Scheduled | 09/06/2018 | 10/06/2018
TO-18-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-MUL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MULLINGAR 110-MULLINGAR 110-110SA1-2CB | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | 5 | 5 | Scheduled | 11/06/2018 | 15/06/2018
TO-18-MUL-T102-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 10-T102 | 5 | 5 | Reference | 11/06/2018 | 15/06/2018
TO-18-MUL-T142-01 | DISTRIBUTION TRANSFORMER - MULLINGAR 110-MULLINGAR 38-T142 | 5 | 5 | Reference | 11/06/2018 | 15/06/2018
TO-18-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | 5 | 5 | Scheduled | 18/06/2018 | 22/06/2018
TO-18-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | 10 | 8 | Scheduled | 18/06/2018 | 27/06/2018
TO-18-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | 3 | 3 | Scheduled | 25/06/2018 | 27/06/2018
TO-18-CUS-MLC-1-02 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MLC-110SA1-02 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA1 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MLC-110SA2-03 | SECTIONALISING DISCONNECT - MOUNTLUCAS 110-MOUNTLUCAS 110-110SA2 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-MLC-T121-02 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-DRY-PLA-1-02 | 110kV FEEDER - DRYBRIDGE 110-PLATIN 110-1 | 2 | 2 | Scheduled | 28/06/2018 | 29/06/2018
TO-18-DRY-LOU-1-01 | 110kV FEEDER - DRYBRIDGE 110-LOUTH 110-1 | Unknown | 10 | Planned | July | July
TO-18-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | 10 | Planned | July | July
TO-18-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | 2 | Planned | July | July
TO-18-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | 10 | Planned | July | July
TO-18-KIN-T102-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | 10 | Planned | July | July
TO-18-LA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - LANESBORO 110-LANESBORO 110-110SA1-2CB | Unknown | 3 | Planned | July | July
TO-18-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | 5 | Planned | July | July
TO-18-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | 5 | Planned | July | July
TO-18-SH-T104-01 | GENERATOR TRANSFORMER - SHANNONBRIDGE 110-SHANNONBRIDGE G4-T104 | Unknown | 1 | Planned | July | July
TO-18-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | 2 | Planned | July | July
TO-18-IKE,T-SH-1-02 | 110kV FEEDER - IKERRIN tee-SHANNONBRIDGE 110-1 | Unknown | 2 | Planned | July | July
TO-18-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | 5 | Planned | July | July
TO-18-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | Unknown | 7 | Planned | July | August
TO-18-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-KLN-SH-1-02 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | 10 | Planned | July | August
TO-18-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | 5 | Planned | July | August
TO-18-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | 5 | Planned | July | August
TO-18-MLN-T122-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T122 | Unknown | 2 | Planned | July | August
TO-18-MLN-T121-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T121 | Unknown | 2 | Planned | August | August
TO-18-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | Unknown | 3 | Planned | August | August
TO-18-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | 3 | Planned | August | August
TO-18-COR-GWE-1-01 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | 1 | Planned | August | August
TO-18-GWE-T101-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T101 | Unknown | 1 | Planned | August | August
TO-18-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | 5 | Planned | August | August
TO-18-GOR-NAV-1-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-GOR-NAV-3-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-KUR-NAV-1-02 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | 5 | 5 | Reference | 13/08/2018 | 17/08/2018
TO-18-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | 5 | 5 | Reference | 13/08/2018 | 17/08/2018
TO-18-NAV-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - NAVAN 110-NAVAN 110-110SA1-2CB | 5 | 5 | Scheduled | 13/08/2018 | 17/08/2018
TO-18-NAV-T142-01 | DISTRIBUTION TRANSFORMER - NAVAN 110-NAVAN 38-T142 | 5 |  | Reference | 13/08/2018 | 17/08/2018
TO-18-SKL-M/CAP2-01 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | Unknown | 5 | Planned | August | August
TO-18-SOM,T-CSH-1-03 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SH-1-03 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SOM-1-02 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-CSH-1-02 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown |  | Planned | August | August
TO-18-ARV-NAV-1-01 | 110kV FEEDER - ARVA 110-NAVAN 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-CSH-1-04 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SH-1-04 | 110kV FEEDER - SOMERSET tee-SHANNONBRIDGE 110-1 | Unknown | 1 | Planned | August | August
TO-18-SOM,T-SOM-1-03 | 110kV FEEDER - SOMERSET tee-SOMERSET 110-1 | Unknown | 1 | Planned | August | August
TO-18-ARV-110K1-2-01 | COUPLER/SECTIONALISING CB - ARVA 110-ARVA 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-LIS-SKL-1-01 | 110kV FEEDER - LISDRUM 110-SHANKILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-LOU-MTH-1-02 | 110kV FEEDER - LOUTH 110-MEATH HILL 110-1 | Unknown | 1 | Planned | September | September
TO-18-KIN-MUL-1-01 | 110kV FEEDER - KINNEGAD 110-MULLINGAR 110-1 | Unknown | 3 | Planned | September | September
TO-18-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | 2 | Planned | September | September
TO-18-LA-T104-01 | GENERATOR TRANSFORMER - LANESBORO 110-LANESBORO G4-T104 | Unknown | 5 | Planned | September | September
TO-18-SH-110K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-AGL-SH-1-01 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | Unknown | 3 | Planned | October | October
TO-18-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | 3 | Planned | October | October
TO-18-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | 1 | Planned | October | October
TO-18-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | 3 | Planned | October | October
TO-18-SOM,T-CSH-1-01 | 110kV FEEDER - SOMERSET tee-CASHLA 110-1 | 2 | 2 | Trip Testing | 25/10/2018 | 26/10/2018

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-FIN-GLA-1-01 | 110kV FEEDER - FINGLAS 110-GLASMORE 110-1 | 53 | 36 | Reference | 20/03/2018 | 11/05/2018
TO-18-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-DSN-T4202-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4202 | 19 | 14 | Scheduled | 23/04/2018 | 11/05/2018
TO-18-110 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 110-FINGLAS 110-110A2 | 21 | 14 | Scheduled | 30/04/2018 | 20/05/2018
TO-18-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | 3 | 3 | Scheduled | 30/04/2018 | 02/05/2018
TO-18-COL-CDU-1-05 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-110K1-2-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-110K1-3-06 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-PLA-1-04 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-RYB GIS-1-03 | 110kV FEEDER - CORDUFF 110-RYEBROOK GIS 110-1 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CDU-T2101-03 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | 1 | 1 | Scheduled | 02/05/2018 | 02/05/2018
TO-18-INC-220K1-2-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | 2 | 2 | Scheduled | 03/05/2018 | 04/05/2018
TO-18-INC-MAY-1-06 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 03/05/2018 | 04/05/2018
TO-18-BLK,T-MAY-1-03 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | Scheduled | 08/05/2018 | 08/05/2018
TO-18-FIN-220K1-2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1-2 | 1 | 1 | Scheduled | 09/05/2018 | 09/05/2018
TO-18-FIN GIS-T2106-03 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Scheduled | 10/05/2018 | 11/05/2018
TO-18-FIN-GLA-1-02 | 110kV FEEDER - FINGLAS 110-GLASMORE 110-1 | 2 | 2 | Reference | 10/05/2018 | 11/05/2018
TO-18-FIN-FIN GIS-1-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-1 | 1 | 1 | Scheduled | 11/05/2018 | 11/05/2018
TO-18-CLE-WOO-1-02 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | 2 | 1 | Scheduled | 13/05/2018 | 14/05/2018
TO-18-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | 2 | 1 | Scheduled | 13/05/2018 | 14/05/2018
TO-18-FIN GIS-T2101-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2101 | 4 | 4 | Scheduled | 14/05/2018 | 17/05/2018
TO-18-FIN-SVN-1-01 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 44 |  | Reference | 14/05/2018 | 26/06/2018
TO-18-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | 5 | 3 | Scheduled | 16/05/2018 | 20/05/2018
TO-18-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | 5 | 3 | Scheduled | 16/05/2018 | 20/05/2018
TO-18-TH-T2001/2-02 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 1 | 1 | Scheduled | 16/05/2018 | 16/05/2018
TO-18-INC-MAY-1-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 22 | 15 | Scheduled | 17/05/2018 | 07/06/2018
TO-18-INC-MAY-2-02 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 22 | 15 | Scheduled | 17/05/2018 | 07/06/2018
TO-18-BLK,T-MAY-1-04 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 1 | 1 | Scheduled | 18/05/2018 | 18/05/2018
TO-18-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 3 | 3 | Tentative | 21/05/2018 | 23/05/2018
TO-18-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-CDU-T2101-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2101 | 3 | 3 | Scheduled | 21/05/2018 | 23/05/2018
TO-18-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | 10 | 8 | Scheduled | 23/05/2018 | 01/06/2018
TO-18-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | 10 | 8 | Scheduled | 23/05/2018 | 01/06/2018
TO-18-INC-MAY-1-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-INC-MAY-2-01 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | 14 | 9 | Scheduled | 25/05/2018 | 07/06/2018
TO-18-CDU-T2102-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2102 | 5 | 5 | Scheduled | 28/05/2018 | 01/06/2018
TO-18-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | 1 | 1 | Scheduled | 04/06/2018 | 04/06/2018
TO-18-DSN-KLS-1-01 | 220kV FEEDER - DUNSTOWN 220-KELLIS 220-1 | 5 | 4 | Scheduled | 04/06/2018 | 08/06/2018
TO-18-CLG-110K1-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | Unknown | 4 | Planned | June | June
TO-18-CLG-110K1-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K1 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-CLG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | Unknown | 1 | Planned | June | June
TO-18-CLG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | Unknown | 1 | Planned | June | June
TO-18-CLG-FIN GIS-1-01 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | Unknown | 1 | Planned | June | June
TO-18-CLG-MCE-1-02 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | 28 | 20 | Scheduled | 05/06/2018 | 02/07/2018
TO-18-CLG-MCE-1-01 | 110kV FEEDER - CLOGHRAN 110-MACETOWN 110-1 | Unknown | 20 | Planned | June | July
TO-18-CLG-T121-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | Unknown | 4 | Planned | June | June
TO-18-CLG-T121-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T121 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-CLG-T123-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | Unknown | 1 | Planned | June | June
TO-18-CLG-T123-02 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T123 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-KTL-CAP1-01 | CAPACITOR/SVC/REACTOR - KILTEEL 110-KILTEEL 110-CAP1 | 2 | 2 | Scheduled | 05/06/2018 | 06/06/2018
TO-18-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | 4 | 4 | Scheduled | 05/06/2018 | 08/06/2018
TO-18-PB-220K2-3-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K2-3 | 3 | 3 | Scheduled | 05/06/2018 | 07/06/2018
TO-18-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | 1 | 1 | Scheduled | 08/06/2018 | 08/06/2018
TO-18-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | 2 | 0 | Scheduled | 09/06/2018 | 10/06/2018
TO-18-BAL-110SA1-02 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-BAL-110SA2-02 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-BAL-CDU-1-03 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | 2 | 2 | Reference | 11/06/2018 | 12/06/2018
TO-18-CLG-T124-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T124 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-CDU-220SA2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SA2-4 | 1 | 1 | Scheduled | 11/06/2018 | 11/06/2018
TO-18-CDU-MUL-1-03 | 110kV FEEDER - CORDUFF 110-MULLINGAR 110-1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | 2 | Planned | June | June
TO-18-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SA1-3CB-05 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN GIS-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | 2 | 2 | Scheduled | 11/06/2018 | 12/06/2018
TO-18-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 19 | 15 | Scheduled | 11/06/2018 | 29/06/2018
TO-18-FIN-SVN-1-03 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 2 | 2 | Reference | 11/06/2018 | 12/06/2018
TO-18-MAY-SH-1-01 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-MAY-SH-1-02 | 220kV FEEDER - MAYNOOTH 220-SHANNONBRIDGE 220-1 | 16 | 12 | Scheduled | 11/06/2018 | 26/06/2018
TO-18-NW-PB-1-04 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | 47 | 35 | Proposed | 11/06/2018 | 27/07/2018
TO-18-PB-220K3-4-01 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-220K3-4-03 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-R223-4-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-SHL-1-03 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 12 | 10 | Scheduled | 11/06/2018 | 22/06/2018
TO-18-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | 12 | 10 | Proposed | 11/06/2018 | 22/06/2018
TO-18-PB-TF4-01 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | 12 | 10 | Reference (Proposed) | 11/06/2018 | 22/06/2018
TO-18-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | 3 | 3 | Scheduled | 11/06/2018 | 13/06/2018
TO-18-CLG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SA1-2CB | 1 | 1 | Scheduled | 13/06/2018 | 13/06/2018
TO-18-CLG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110SB1-2CB | 1 | 1 | Scheduled | 14/06/2018 | 14/06/2018
TO-18-CDU-220SB2-4-01 | SECTIONALISING DISCONNECT - CORDUFF 220-CORDUFF 220-220SB2-4 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 2 | 2 | Scheduled | 14/06/2018 | 15/06/2018
TO-18-FIN-SVN-1-04 | 110kV FEEDER - FINGLAS 110-STEPHENSTOWN 110-1 | 2 | 2 | Reference | 14/06/2018 | 15/06/2018
TO-18-CLE-220K2-01 | COUPLER/SECTIONALISING CB - CLONEE 220-CLONEE 220-220K2 | 1 | 1 | Scheduled | 18/06/2018 | 18/06/2018
TO-18-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | 3 | 3 | Scheduled | 19/06/2018 | 21/06/2018
TO-18-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | 1 | 1 | Scheduled | 21/06/2018 | 21/06/2018
TO-18-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | 2 | 2 | Scheduled | 21/06/2018 | 22/06/2018
TO-18-FIN GIS-T2106-06 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | 2 | 2 | Scheduled | 25/06/2018 | 26/06/2018
TO-18-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 12 | 10 | Scheduled | 25/06/2018 | 06/07/2018
TO-18-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | 5 | 5 | Scheduled | 25/06/2018 | 29/06/2018
TO-18-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | 3 | 3 | Scheduled | 25/06/2018 | 27/06/2018
TO-18-ART-FIN-1-01 | 110kV FEEDER - ARTANE 110-FINGLAS 110-1 | Unknown | 30 | Reference (Planned) | June | August
TO-18-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 1 | Planned | June | June
TO-18-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | June | June
TO-18-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | June | June
TO-18-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | 15 | Planned | July | July
TO-18-FIN GIS-T2106-07 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 15 | Planned | July | July
TO-18-SHL-D1/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB2 | Unknown | 2 | Planned | July | July
TO-18-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | 1 | Planned | July | July
TO-18-SHL-T2014-02 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G4-T2014 | Unknown | 3 | Planned | July | July
TO-18-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 2 | Planned | July | July
TO-18-CDU-HN-1-02 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | 2 | Planned | July | July
TO-18-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | 2 | Planned | July | July
TO-18-OST-WOO-1-01 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | 74 | Planned | July | October
TO-18-RYB GIS-T104-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T104 | Unknown | 3 | Planned | July | July
TO-18-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | 3 | Planned | July | July
TO-18-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | 1 | Planned | July | July
TO-18-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SA2-4CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-2CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB1-3CB | Unknown | 1 | Planned | July | July
TO-18-RYB GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - RYEBROOK GIS 110-RYEBROOK GIS 110-110SB2-4CB | Unknown | 1 | Planned | July | July
TO-18-MAY-110K3-4-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | 5 | Planned | July | July
TO-18-MAY-110K3-4-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K3-4 | Unknown | 5 | Planned | July | July
TO-18-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | 10 | Planned | July | July
TO-18-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | 10 | Planned | July | July
TO-18-MAY-T2104-03 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown |  | Planned | July | July
TO-18-RYB GIS-T105-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T105 | Unknown | 3 | Planned | July | July
TO-18-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | 15 | Planned | July | August
TO-18-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 5 | Planned | July | July
TO-18-PB-220K3-4-02 | COUPLER/SECTIONALISING CB - POOLBEG 220-POOLBEG 220-220K3-4 | Unknown | 5 | Planned | July | July
TO-18-PB-R223-4-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | 5 | Planned | July | July
TO-18-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | 5 | Planned | July | July
TO-18-PB-TF4-02 | TRANSFORMER - POOLBEG 220-POOLBEG 110-TF4 | Unknown | 5 | Reference (Planned) | July | July
TO-18-CDU-PLA-1-02 | 110kV FEEDER - CORDUFF 110-PLATIN 110-1 | Unknown | 2 | Planned | July | July
TO-18-110 kV B4 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B4 | Unknown | 5 | Planned | July | July
TO-18-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | 5 | Planned | July | July
TO-18-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown |  | Planned | July | July
TO-18-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | 15 | Planned | July | August
TO-18-FIN GIS-T2106-08 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 15 | Planned | July | August
TO-18-RYB GIS-T106-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T106 | Unknown | 3 | Planned | July | July
TO-18-NW-PB-1-03 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | 4 | Planned | July | July
TO-18-110 kV A6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | July | July
TO-18-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | July | July
TO-18-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | 2 | Planned | July | July
TO-18-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | 5 | Planned | July | August
TO-18-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | 14 | Planned | July | August
TO-18-RYB GIS-T107-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T107 | Unknown | 3 | Planned | July | August
TO-18-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | 4 | Planned | August | August
TO-18-RYB GIS-T108-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T108 | Unknown | 3 | Planned | August | August
TO-18-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | 7 | Planned | August | August
TO-18-FIN-FIN GIS-2-01 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | 2 | Planned | August | August
TO-18-220 kV A1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220A1 | Unknown | 5 | Planned | August | August
TO-18-220 kV B1 @ CKM-01 | BUSBAR SECTION - CARRICKMINES 220-CARRICKMINES 220-220B1 | Unknown | 5 | Planned | August | August
TO-18-220 kV A1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220A1 | Unknown | 2 | Planned | August | August
TO-18-220 kV B1 @ CKM GIS-01 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-2CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SA1-3CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | Unknown | 2 | Planned | August | August
TO-18-CKM GIS-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | Unknown | 2 | Planned | August | August
TO-18-CKM-T2101-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 110-T2101 | Unknown | 98 | Reference (Planned) | August | December
TO-18-110 kV A6 @ FIN GIS-03 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | August | August
TO-18-FIN GIS-110K6-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | August | August
TO-18-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | August | August
TO-18-FIN-PTN-1-01 | 110kV FEEDER - FINGLAS 110-PELLETSTOWN 110-1 | Unknown | 30 | Reference (Planned) | August | September
TO-18-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | 7 | Planned | August | August
TO-18-RYB GIS-T109-01 | TSO CUSTOMER TRANSFORMER - RYEBROOK GIS 110-RYEBROOK 10-T109 | Unknown | 3 | Planned | August | August
TO-18-220 kV B1 @ CKM GIS-02 | BUSBAR SECTION - CARRICKMINES GIS 220-CARRICKMINES GIS 220-220B1 | Unknown | 1 | Planned | August | August
TO-18-CKM GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-2CB | Unknown | 1 | Planned | August | August
TO-18-CKM GIS-220SB1-3CB-02 | COUPLER/SECTIONALISING CB - CARRICKMINES GIS 220-CARRICKMINES GIS 220-22SB1-3CB | Unknown | 1 | Planned | August | August
TO-18-WOO-T4201-02 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | 5 | Planned | August | August
TO-18-ISH-SHL-1-01 | 220kV FEEDER - IRISHTOWN 220-SHELLYBANKS 220-1 | Unknown | 5 | Planned | August | August
TO-18-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | Unknown | 7 | Planned | August | August
TO-18-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | 8 | Planned | August | September
TO-18-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | 6 | Planned | August | September
TO-18-ARK-CKM GIS-1-05 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 2 | Planned | August | August
TO-18-ARK-CKM GIS-1-04 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | 7 | Planned | September | September
TO-18-INC-220K1-2-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K1-2 | Unknown | 4 | Planned | September | September
TO-18-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | 3 | Planned | September | September
TO-18-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | 5 | Planned | September | September
TO-18-110 kV A6 @ FIN GIS-04 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | 2 | Planned | September | September
TO-18-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110K6-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110SA4-6CB-04 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | 2 | Planned | September | September
TO-18-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | 2 | Planned | September | September
TO-18-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | 3 | Planned | September | September
TO-18-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | 2 | Planned | September | September
TO-18-INC-ISH-1-01 | 220kV FEEDER - INCHICORE 220-IRISHTOWN 220-1 | Unknown | 1 | Planned | September | September
TO-18-CKM GIS-ISH-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-IRISHTOWN 220-1 | Unknown | 5 | Planned | September | September
TO-18-CLG-FIN GIS-1-02 | 110kV FEEDER - CLOGHRAN 110-FINGLAS GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-110 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | Unknown | 5 | Planned | September | September
TO-18-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | 3 | Planned | September | September
TO-18-ISH-T2001-01 | GENERATOR TRANSFORMER - IRISHTOWN 220-IRISHTOWN G1-T2001 | Unknown | 1 | Planned | September | September
TO-18-FIN-FIN GIS-2-02 | 110kV FEEDER - FINGLAS 110-FINGLAS GIS 110-2 | Unknown | 2 | Planned | September | September
TO-18-COL-FIN GIS-1-03 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | 3 | Planned | September | September
TO-18-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | Unknown | 1 | Planned | October | October
TO-18-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | Unknown | 5 | Planned | October | October
TO-18-CLE-T224-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T224 | Unknown | 1 | Planned | October | October
TO-18-NW-T2004/5-03 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | 3 | Planned | October | October
TO-18-INC-MAY-1-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-1 | Unknown | 46 | Planned | October | December
TO-18-INC-MAY-2-03 | 220kV FEEDER - INCHICORE 220-MAYNOOTH 220-2 | Unknown | 61 | Planned | October | January
TO-18-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | 1 | Planned | October | October
TO-18-WOO-400K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | 3 | Planned | October | October
TO-18-110 kV B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B4 | Unknown | 8 | Planned | October | October
TO-18-220 kV A2 @ FIN-04 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | 1 | Planned | October | October
TO-18-FIN GIS-T2106-09 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2106 | Unknown | 2 | Planned | October | October
TO-18-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | 2 | Planned | October | October
TO-18-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | 2 | Planned | October | October
TO-18-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | 2 | Planned | October | October
TO-18-110 kV A4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | Unknown | 8 | Planned | October | November
TO-18-110 kV A1/A3 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A1-A3 | Unknown | 2 | Planned | November | November
TO-18-110 kV A2/A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A2-A4 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-3-04 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | 2 | Planned | November | November
TO-18-CDU-110SA2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 2 | Planned | November | November
TO-18-110 kV B1/B3 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B1-B3 | Unknown |  | Planned | November | November
TO-18-110 kV B2/B4 @ CDU-02 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110B2-B4 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-2-03 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | 2 | Planned | November | November
TO-18-CDU-110K1-3-05 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | 2 | Planned | November | November
TO-18-CDU-110SB2-4-02 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 2 | Planned | November | November
TO-18-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SA2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SA2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SA2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SB2-4-04 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-110SB2-4-03 | SECTIONALISING DISCONNECT - CORDUFF 110-CORDUFF 110-110SB2-4 | Unknown | 6 | Planned | November | November
TO-18-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | 6 | Planned | November | November
TO-18-PB-R2001-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | Unknown | 3 | Planned | November | November
TO-18-BAL-CDU-1-02 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | 2 | Planned | November | November

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Required Work Days | Outage Status | Start | Finish
TO-18-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | 67 |  | Scheduled | 20/03/2018 | 25/05/2018
TO-18-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | 85 | 59 | Scheduled | 03/04/2018 | 26/06/2018
TO-18-MID-T141-02 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 10 | 8 | Reference | 25/04/2018 | 04/05/2018
TO-18-BGH-110SA1-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA1 | 5 |  | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-110SA2-01 | SECTIONALISING DISCONNECT - BOGGERAGH 110-BOGGERAGH 110-110SA2 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-CLA-1-01 | 110kV FEEDER - BOGGERAGH 110-CLASHAVOON 110-1 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T121-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 20-T121 | 5 |  | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T132-01 | GENERATOR TRANSFORMER - BOGGERAGH 110-BOGGERAGH 33-T132 | 5 | 5 | Scheduled | 30/04/2018 | 04/05/2018
TO-18-BGH-T142-01 | DISTRIBUTION TRANSFORMER - BOGGERAGH 110-BOGGERAGH 38-T142 | 5 |  | Reference | 30/04/2018 | 04/05/2018
TO-18-KRA-220K1-2-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1-2 | 3 | 3 | Scheduled | 02/05/2018 | 04/05/2018
TO-18-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | 2 | 2 | Scheduled | 08/05/2018 | 09/05/2018
TO-18-KRA-MID-1-03 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 10 | 8 | Scheduled | 08/05/2018 | 17/05/2018
TO-18-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | 3 | 3 | Scheduled | 09/05/2018 | 11/05/2018
TO-18-IA-T101-01 | GENERATOR TRANSFORMER - INNISCARRA 110-INNISCARRA G1-T101 | 5 | 5 | Scheduled | 14/05/2018 | 18/05/2018
TO-18-KBY-110K1-2-01 | COUPLER/SECTIONALISING CB - KILBARRY 110-KILBARRY 110-110K1-2 | 2 | 2 | Scheduled | 14/05/2018 | 15/05/2018
TO-18-AD-LPT-1-01 | 220kV FEEDER - AGHADA 220-LONG POINT 220-1 | 3 | 3 | Scheduled | 16/05/2018 | 18/05/2018
TO-18-LPT-T2002-01 | GENERATOR TRANSFORMER - LONG POINT 220-LONG POINT G1-T2002 | 3 | 3 | Scheduled | 16/05/2018 | 18/05/2018
TO-18-KRA-T2103-03 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | 2 | 2 | Scheduled | 23/05/2018 | 24/05/2018
TO-18-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | 15 | 10 | Scheduled | 28/05/2018 | 11/06/2018
TO-18-220 kV B2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B2 | 15 | 10 | Scheduled | 28/05/2018 | 11/06/2018
TO-18-AD-KRA-2-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-2 | 65 | 46 | Scheduled | 28/05/2018 | 31/07/2018
TO-18-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | 13 | 8 | Tentative | 30/05/2018 | 11/06/2018
TO-18-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | 2 | 2 | Scheduled | 06/06/2018 | 07/06/2018
TO-18-CD-KBY-1-01 | 110kV FEEDER - CARRIGADROHID 110-KILBARRY 110-1 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-CD-T103-01 | GENERATOR TRANSFORMER - CARRIGADROHID 110-CARRIGADROHID G3-T103 | 4 | 4 | Scheduled | 11/06/2018 | 14/06/2018
TO-18-KRA-MID-1-04 | 110kV FEEDER - KNOCKRAHA 110-MIDLETON 110-1 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | 3 | 3 | Scheduled | 12/06/2018 | 14/06/2018
TO-18-MID-110SA1-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MID-110SA2-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | 4 | 4 | Proposed | 12/06/2018 | 15/06/2018
TO-18-MID-T141-03 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | 4 | 4 | Reference (Proposed) | 12/06/2018 | 15/06/2018
TO-18-RAF-T2102-01 | TRANSFORMER - RAFFEEN 220-RAFFEEN 110-T2102 | 3 | 3 | Proposed | 18/06/2018 | 20/06/2018
TO-18-KRA-WOH-1-01 | 110kV FEEDER - KNOCKRAHA 110-WOODHOUSE 110-1 | 4 | 4 | Proposed | 25/06/2018 | 28/06/2018
TO-18-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | 5 | Planned | July | July
TO-18-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | 4 | Reference (Planned) | July | July
TO-18-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | 4 | Planned | July | July
TO-18-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | 4 | Planned | July | July
TO-18-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | 4 | Planned | July | July
TO-18-MR-TBG-1-01 | 110kV FEEDER - MARINA 110-TRABEG 110-1 | Unknown | 6 | Planned | July | July
TO-18-WHI-CKB-T101-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T101 | Unknown | 1 | Planned | July | July
TO-18-WHI-CKB-T102-01 | TSO CUSTOMER TRANSFORMER - WHITEGATE 110-WHITEGATE 10-CKB-T102 | Unknown | 1 | Planned | July | July
TO-18-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | 5 | Planned | July | July
TO-18-TBG-110K1-2-01 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | 3 | Planned | July | July
TO-18-220 kV A1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | 20 | Planned | July | August
TO-18-220 kV B1 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220B1 | Unknown | 20 | Planned | July | August
TO-18-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 61 | Planned | July | October
TO-18-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | 61 | Planned | July | October
TO-18-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | 4 | Planned | July | July
TO-18-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-1-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 5 | Planned | August | August
TO-18-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | 5 | Planned | August | August
TO-18-KBY-MR-1-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-1-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-1 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 7 | Planned | August | August
TO-18-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | 7 | Planned | August | August
TO-18-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | 30 | Reference (Planned) | August | October
TO-18-CUL-KRA-1-03 | 220kV FEEDER - CULLENAGH 220-KNOCKRAHA 220-1 | Unknown | 2 | Planned | August | August
TO-18-KRA-RAF-1-05 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | 3 | Planned | August | August
TO-18-RAF-TBG-1-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown |  | Planned | August | September
TO-18-RAF-TBG-1-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | 24 | Planned | August | September
TO-18-CLA-110K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 110-CLASHAVOON 110-110K1-2 | Unknown | 6 | Planned | August | September
TO-18-RAF-TBG-2-01 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | 5 | Planned | August | August
TO-18-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | 5 | Planned | August | August
TO-18-CVW-COW-1-01 | 110kV FEEDER - CASTLEVIEW 110-COW CROSS 110-1 | Unknown | 2 | Planned | September | September
TO-18-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | 5 | Planned | September | September
TO-18-KRA-T2101-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | 3 | Planned | September | September
TO-18-KRA-T2103-02 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2103 | Unknown | 3 | Planned | September | September
TO-18-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | 3 | Planned | September | September
TO-18-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | Unknown | 1 | Planned | September | September
TO-18-BVK-CLA-1-01 | 220kV FEEDER - BALLYVOUSKILL 220-CLASHAVOON 220-1 | Unknown | 3 | Planned | September | September
TO-18-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 1 | Planned | October | October
TO-18-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 1 | Planned | October | October
TO-18-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | 1 | Planned | October | October
TO-18-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | 1 | Planned | October | October
TO-18-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | 1 | Reference (Planned) | October | October
TO-18-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | 30 | Planned | October | November
TO-18-BRI-T101-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T101 | Unknown | 30 | Reference (Planned) | October | November
TO-18-AD-ST101-01 | GENERATOR TRANSFORMER - AGHADA 110-AGHADA 10-ST101 | Unknown | 4 | Planned | October | October
TO-18-AD-KRA-1-02 | 220kV FEEDER - AGHADA 220-KNOCKRAHA 220-1 | Unknown | 1 | Planned | October | October
TO-18-AD-WHI-1-01 | 110kV FEEDER - AGHADA 110-WHITEGATE 110-1 | Unknown | 3 | Planned | October | October
TO-18-MR-110K1-2-01 | COUPLER/SECTIONALISING CB - MARINA 110-MARINA 110-110K1-2 | Unknown | 5 | Planned | October | October
TO-18-CLA-220K1-2-01 | COUPLER/SECTIONALISING CB - CLASHAVOON 220-CLASHAVOON 220-220K1-2 | Unknown | 1 | Planned | October | October
TO-18-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | 1 | Planned | November | November
TO-18-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | 1 | Planned | November | November
TO-18-BAN-CAP1-01 | CAPACITOR/SVC/REACTOR - BANDON 110-BANDON 110-CAP1 | Unknown | 1 | Planned | November | November
TO-18-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | 1 | Planned | November | November
TO-18-BAN-T101-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 10-T101 | Unknown | 1 | Reference (Planned) | November | November
TO-18-BAN-T141-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | 1 | Reference (Planned) | November | November