## Plan
SUB 1 | SUB 2 | Task Name | kV | Duration | Start | Finish
|  | Start: Mon 06/01/20 - Sun 12/01/20 |  | 25d | Mon 06/01/20 | Mon 10/02/20
KILROOT | TANDRAGEE | CT CHANGE BAY TBC 3 CT'S GJ75 GJ70 (PROJECTS) - GJ71 GJ74 CT REPLACEMENT | 275 | 3 wks | Mon 06/01/20 | Fri 24/01/20
ENNISKILLEN |  | ENN PST MAINT 7P0 7P4,7P6 & 7P8(ISOLATOR MAINTENANCE) - MAINTENANCE | 110 | 1 wk | Mon 06/01/20 | Fri 10/01/20
HANNAHSTOWN |  | HANNAHSTOWN MAIN SECTION 1L/1R BUSBAR (PROJECTS) - MG43,MG33 REPLACEMENT | 110 | 4 wks | Mon 06/01/20 | Fri 31/01/20
ENNISKILLEN |  | PST - ISOLATORS ONLY | 110 | 3 wks | Mon 06/01/20 | Fri 24/01/20
COOLKEERAGH | LISAGHMORE 'B' | 12H1 & EH21 MAINT | 110 | 2 days | Wed 08/01/20 | Thu 09/01/20
COOLKEERAGH | LISAGHMORE 'A' | 14H1 & EH21 MAINT | 110 | 2 days | Mon 06/01/20 | Tue 07/01/20
BALLYLUMFORD |  | BPS GD64 & GD74 MAINT | 275 | 1 wk | Mon 06/01/20 | Fri 10/01/20
CARMONEY | EDEN 'A' | CAR 1C2,5C2,3C2 AND EDEN 'A' CVT | 110 | 5 days | Mon 06/01/20 | Fri 10/01/20
Ballylumford | NIB31 | GEN | GEN | 3 days | Mon 06/01/20 | Wed 08/01/20
KILROOT | NIKGT1 | GEN | GEN | 3 days | Tue 07/01/20 | Thu 09/01/20
Lisahally | NILPS | GEN | GEN | 25 days | Tue 07/01/20 | Mon 10/02/20
KILROOT | NIKGT2 | GEN | GEN | 1 day | Thu 09/01/20 | Thu 09/01/20
Moyle | MOYLE | GEN | GEN | 1 day | Fri 10/01/20 | Fri 10/01/20
CASTLEREAGH |  | MC58 & MC60 MAINT | 110 | 4 days | Mon 06/01/20 | Thu 09/01/20
|  | Start: Mon 13/01/20 - Sun 19/01/20 |  | 25d | Mon 13/01/20 | Fri 14/02/20
CARMONEY |  | CAR 4C4,6C2,2C4 (ISOL ESW ONLY) - MAINTENANCE | 110 | 3 days | Mon 13/01/20 | Wed 15/01/20
HANNAHSTOWN |  | HANNAHSTOWN MAIN SECTION 2L/2R BUSBAR (PROJECTS) - MG48,MG38 REPLACEMENT | 110 | 5 wks | Mon 13/01/20 | Fri 14/02/20
TAMNAMORE | TREMOGE | TMN - TMG FREQUECNY ISSUES CUST (TOWER 180 CLIP ON WIRES) - OHL MAINTENANCE | 110 | 1 day | Tue 14/01/20 | Tue 14/01/20
DUNGANNON |  | 5J0 MAINT | 110 | 2 days | Mon 13/01/20 | Tue 14/01/20
BALLYLUMFORD |  | B10 OUTAGE MD65 MAINT | 110 | 1 day | Thu 16/01/20 | Thu 16/01/20
CARMONEY | CASTLEREAGH 'A' | CAR 2C4,6C2,4C4 AND CAS 'B' CVT | 110 | 5 days | Mon 13/01/20 | Fri 17/01/20
EDEN | CARNMONEY 'B' | CVT MAINT | 110 | 2 days | Thu 16/01/20 | Fri 17/01/20
COOLKEERAGH | SPRINGTOWN 'A' | GCB 13H0 ,CVT AND 13H3 MAINT | 110 | 1 wk | Mon 13/01/20 | Fri 17/01/20
KILROOT | NIK2 | GEN | GEN | 5 days | Thu 16/01/20 | Wed 22/01/20
KELLS |  | GF55 MAINT | 275 | 1 wk | Mon 13/01/20 | Fri 17/01/20
KELLS |  | GF55 MAINT | 275 | 1 wk | Mon 13/01/20 | Fri 17/01/20
KILROOT | KELLS 'A' | PROXIMITY OUTAGE | 275 | 1 day | Sun 19/01/20 | Sun 19/01/20
ENNISKILLEN |  | PST LOW OIL LEVEL | 110 | 1 day | Fri 17/01/20 | Fri 17/01/20
KILROOT | kells 'B' | WALL BUSHING FAULT | 275 | 3 days | Wed 15/01/20 | Fri 17/01/20
|  | Start: Mon 20/01/20 - Sun 26/01/20 |  | 11d | Mon 20/01/20 | Wed 05/02/20
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) - 13H1 | 110 | 2 days | Mon 20/01/20 | Tue 21/01/20
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R (BUSBAR) - 8H8,9H2 & 9H3 | 110 | 2 days | Thu 23/01/20 | Fri 24/01/20
HANNAHSTOWN | LISBURN 'B' | HOUSING DEVELOPMENT POLES (HAN - LIS 'B') - POLE CHANGES | 110 | 5 days | Mon 20/01/20 | Fri 24/01/20
TANDRAGEE |  | SECTION '1R' ISOLATORS - MAINTENANCE MB83,MB84 & MB91 | 110 | 5 days | Mon 20/01/20 | Fri 24/01/20
DUNGANNON |  | 4J0 MAINT | 110 | 2 days | Mon 20/01/20 | Tue 21/01/20
CASTLEREAGH |  | GC15 MAINT | 110 | 5 days | Mon 20/01/20 | Fri 24/01/20
Coolkeeragh | NIC30 | GEN | GEN | 1 day | Tue 21/01/20 | Tue 21/01/20
KILROOT | NIK1 | GEN | GEN | 2 days | Tue 21/01/20 | Wed 22/01/20
Coolkeeragh | NICGT8 | GEN | GEN | 2 days | Tue 21/01/20 | Wed 22/01/20
Coolkeeragh | NICGT8 | GEN | GEN | 11 days | Wed 22/01/20 | Wed 05/02/20
KELLS |  | GF105 MAINT | 275 | 1 wk | Mon 20/01/20 | Fri 24/01/20
CASTLEREAGH | CARMONEY 'B' | MC12,MC13 AND CAR 'B' CVT | 110 | 1 wk | Mon 20/01/20 | Fri 24/01/20
|  | Start: Mon 27/01/20 - Sun 02/02/20 |  | 5d | Mon 27/01/20 | Mon 03/02/20
HANNAHSTOWN | LISBURN 'A' | HOUSING DEVELOPMENT POLES (HAN - LIS 'A') - POLE CHANGES | 110 | 5 days | Mon 27/01/20 | Fri 31/01/20
OMAGH |  | 6M0 MAINT | 110 | 2 days | Mon 27/01/20 | Tue 28/01/20
CASTLEREAGH |  | GC35 MAINT | 110 | 5 days | Mon 27/01/20 | Fri 31/01/20
BALLYLUMFORD |  | GD20 | 275 | 4 days | Tue 28/01/20 | Fri 31/01/20
Coolkeeragh | NIC30 | GEN | GEN | 4 days | Wed 29/01/20 | Sun 02/02/20
KILROOT | NIKGT4 | GEN | GEN | 1 day | Thu 30/01/20 | Thu 30/01/20
CASTLEREAGH | ROSEBANK 'A' | MC8 AND MC9 MAINT SECT '2L' | 110 | 3 days | Mon 27/01/20 | Wed 29/01/20
TANDRAGEE |  | TANDRAGEE IBTX3 MINOR | 275 | 1 wk | Tue 28/01/20 | Mon 03/02/20
SPRINGTOWN |  | TX1 MINOR | 110 | 1 wk | Mon 27/01/20 | Fri 31/01/20
|  | Start: Mon 03/02/20 - Sun 09/02/20 |  | 10d | Mon 03/02/20 | Tue 18/02/20
KILROOT |  | CT CHANGE BAY GJ55 3 GJ56,GJ54 CT'S (PROJECTS) - 2 sets CT REPLACEMENT | 275 | 2 wks | Mon 03/02/20 | Fri 14/02/20
EDEN | BALLYLUMFORD 'A' | CVT AND ISOLS BPS A (LINE PLANT) - ISOLATOR MAINTENANCE | 110 | 1 wk | Mon 03/02/20 | Fri 07/02/20
GLENGORMLEY | GLENGORMLEY 'A' | EM171 AND CSE'S (STEEL REPAIRS) - | 110 | 1 day | Mon 03/02/20 | Mon 03/02/20
EDEN |  | 1T0 MAINT PLUS CX101,1T2,3T2 | 110 | 5 days | Mon 03/02/20 | Fri 07/02/20
COLERAINE |  | 9L0 MAINT & CAP BANK MAINT | 110 | 5 days | Mon 03/02/20 | Fri 07/02/20
DONEGALL | FINAGHY 'A' | cable sheath test | 110 | 1 day | Mon 03/02/20 | Mon 03/02/20
DONEGALL | FINAGHY 'B' | cable sheath test | 110 | 1 day | Mon 03/02/20 | Mon 03/02/20
STRABANE |  | CX231,4S4,2S4,1S8 | 110 | 3 days | Wed 05/02/20 | Fri 07/02/20
STRABANE |  | CX238,1S4 AND 8S8 | 110 | 3 days | Mon 03/02/20 | Wed 05/02/20
BALLYLUMFORD |  | GD40 SF6 LEAK TESTS | 275 | 2 days | Wed 05/02/20 | Thu 06/02/20
BALLYLUMFORD |  | GD55 SF6 LEAK TESTS | 275 | 2 days | Wed 05/02/20 | Thu 06/02/20
Coolkeeragh | NICGT8 | GEN | GEN | 8 days | Wed 05/02/20 | Fri 14/02/20
COOLKEERAGH |  | GT8 OUTAGE FOR CESB | 110 | 2 wks | Wed 05/02/20 | Tue 18/02/20
TANDRAGEE | LISBURN 'A' | MB65 MINOR | 110 | 4 days | Mon 03/02/20 | Thu 06/02/20
FINAGHY |  | TX1 MINOR | 110 | 8 days | Mon 03/02/20 | Wed 12/02/20
|  | Start: Mon 10/02/20 - Sun 16/02/20 |  | 5d | Mon 10/02/20 | Mon 17/02/20
KILROOT |  | CT CHANGE BAY GJ55 3 GJ56,GJ54 CT'S (PROJECTS) - 2 sets CT REPLACEMENT matching GJ75 | 275 | 2 days | Thu 13/02/20 | Fri 14/02/20
COOLKEERAGH |  | 10H0 SF6 GAS GUAGE REPLACEMENT | 110 | 2 days | Thu 13/02/20 | Fri 14/02/20
BALLYLUMFORD | BALLYVALLAGH 'A' | CABLE SHEATH TESTS | 110 | 1 day | Tue 11/02/20 | Tue 11/02/20
BALLYLUMFORD | BALLYVALLAGH 'B' | CABLE SHEATH TESTS | 110 | 0.5 days | Tue 11/02/20 | Tue 11/02/20
BALLYLUMFORD |  | GD60 post trip inspection and testing | 275 | 3 days | Mon 10/02/20 | Wed 12/02/20
KILROOT | NIKGT2 | GEN | GEN | 1 day | Wed 12/02/20 | Wed 12/02/20
TANDRAGEE | LISBURN 'B' | MB55 MINOR | 110 | 4 days | Mon 10/02/20 | Thu 13/02/20
BALLYLUMFORD | BALLYVALLAGH 'B' | MD75 | 110 | 5 days | Tue 11/02/20 | Mon 17/02/20
|  | Start: Mon 17/02/20 - Sun 23/02/20 |  | 20d | Mon 17/02/20 | Mon 16/03/20
COOLKEERAGH |  | CPS CIRCUIT BREAKER LEAKING (1,10,12 AND 13HO GAS GUAGES) - DEFECT REPAIRS | 110 | 7 days | Tue 18/02/20 | Wed 26/02/20
HANNAHSTOWN |  | HANNAHSTOWN MAIN INTERBUS T3 MINOR (275/110) (BUSHING REPAIRS ) - | 275 | 4 wks | Tue 18/02/20 | Mon 16/03/20
MAGHERAFELT | TAMNAMORE 'B' | TMN - MAG 'B' (OHL WORK) - SINGLE TENSION TOWER | 275 | 2.5 days | Fri 21/02/20 | Tue 25/02/20
COOLKEERAGH |  | 1H0 SF6 GAS GUAGE REPLACENT | 110 | 2 days | Thu 20/02/20 | Fri 21/02/20
COOLKEERAGH |  | 12H0 SF6 GUAGE REPLACEMENT | 110 | 2 days | Mon 17/02/20 | Tue 18/02/20
BELFAST NORTH MAIN | DONEGALL | A' CIRCUIT OILWORKS, cable identification & leak repairs | 110 | 2 wks | Sun 23/02/20 | Thu 05/03/20
KILROOT | NIK1 | GEN | GEN | 2 days | Wed 19/02/20 | Thu 20/02/20
KILROOT | NIKGT3 | GEN | GEN | 1 day | Thu 20/02/20 | Thu 20/02/20
KILROOT |  | GJ56,GJ52,GJ53 AND CVT | 275 | 5 days | Fri 21/02/20 | Thu 27/02/20
HANNAHSTOWN | BALLYLUMFORD 'B' | HAN - BALLYLUMFORD 'B' FAULT ON CLAMP GG22 | 275 | 1 day | Wed 19/02/20 | Wed 19/02/20
TAMNAMORE |  | INTERBUS 1 MINOR + eg407 & em313 | 275 | 1 wk | Mon 17/02/20 | Fri 21/02/20
TANDRAGEE |  | MB90 MINOR & MB88 ISOLATOR. | 110 | 4 days | Mon 17/02/20 | Thu 20/02/20
BALLYLUMFORD |  | MD50 oil sampling | 110 | 1 day | Wed 19/02/20 | Wed 19/02/20
powerstation west |  | TX 'B' premove checks | 110 | 5 days | Tue 18/02/20 | Mon 24/02/20
BALLYLUMFORD |  | wall bushing oil sampling | 110 | 1 day | Thu 20/02/20 | Thu 20/02/20
BALLYLUMFORD |  | wall bushing oil sampling | 110 | 1 day | Fri 21/02/20 | Fri 21/02/20
|  | Start: Mon 24/02/20 - Sun 01/03/20 |  | 20d | Mon 24/02/20 | Fri 20/03/20
EDEN | BALLYLUMFORD 'B' | CVT AND ISOLS BPS B (LINE PLANT) - ISOLATOR MAINTENANCE | 110 | 1 wk | Mon 24/02/20 | Fri 28/02/20
EDEN |  | 2T0 MAINT & cx102,et2. | 110 | 5 days | Wed 26/02/20 | Tue 03/03/20
COOLKEERAGH |  | 3H0 outage to measure | 110 | 1 day | Tue 25/02/20 | Tue 25/02/20
ENNISKILLEN |  | 5P0 MAINT | 110 | 2.5 days | Mon 24/02/20 | Wed 26/02/20
ENNISKILLEN |  | 6P0 MAINT | 110 | 2.5 days | Wed 26/02/20 | Fri 28/02/20
BALLYLUMFORD |  | B10 MD63 OUTAGE | 110 | 2 days | Thu 27/02/20 | Fri 28/02/20
BALLYLUMFORD |  | B10 MD64 OUTAGE | 110 | 2 days | Mon 24/02/20 | Tue 25/02/20
BALLYLUMFORD |  | GD5 ( GENERATOR 6) | 275 | 5 days | Mon 24/02/20 | Fri 28/02/20
BALLYLUMFORD |  | GD65 REMOVE CT'S FOR COOLKEERAGH | 275 | 4 wks | Mon 24/02/20 | Fri 20/03/20
BALLYLUMFORD |  | GD65 REMOVE CT'S FOR COOLKEERAGH plus section A4 | 275 | 3 wks | Wed 26/02/20 | Tue 17/03/20
Ballylumford | NIB32 | GEN | GEN | 2 days | Tue 25/02/20 | Wed 26/02/20
KILROOT | NIKGT3 | GEN | GEN | 1 day | Fri 28/02/20 | Fri 28/02/20
Ballylumford | NIB31 | GEN | GEN | 2 days | Fri 28/02/20 | Sat 29/02/20
TANDRAGEE | NEWRY 'B' | MB20 mech box repair date TBC | 110 | 5 days | Mon 24/02/20 | Fri 28/02/20
CASTLEREAGH | CARMONEY 'B' | ohl fault t126-127. | 110 | 2 days | Mon 24/02/20 | Tue 25/02/20
|  | Start: Mon 02/03/20 - Sun 08/03/20 |  | 25d | Mon 02/03/20 | Fri 03/04/20
KILROOT |  | KPS CT CHANGE BAY TBC 3 CT'S beside EG244 (PROJECTS) - CT REPLACEMENT | 275 | 2 wks | Mon 02/03/20 | Fri 13/03/20
TANDRAGEE | NEWRY 'A' | TAN - NRY A (OHL WORK) -painting and arching horns on tower 151 | 110 | 2 wks | Mon 02/03/20 | Fri 13/03/20
TANDRAGEE | NEWRY 'A' | TAN - NRY A (PROJECTS) - TELEPROTECTION CHANGE AND DISTANCE PROTECTION | 110 | 5 wks | Mon 02/03/20 | Fri 03/04/20
NEWRY |  | TX1 PAINTING AND MAJOR (PROJECTS) - PROJECT WORK | 110 | 5 wks | Mon 02/03/20 | Fri 03/04/20
STRABANE | OMAGH | 6S8 ISOLATOR REPAIR | 110 | 1 day | Thu 05/03/20 | Thu 05/03/20
KILROOT | NIK1 | GEN | GEN | 5 days | Mon 02/03/20 | Fri 06/03/20
TAMNAMORE | MAGHERAFELT 'A' | GP25 MAINT | 275 | 1 wk | Mon 02/03/20 | Fri 06/03/20
BALLYLUMFORD | BALLYVALLAGH 'A' | MD80 | 110 | 5 days | Mon 02/03/20 | Fri 06/03/20
TANDRAGEE |  | SECTION '1R' MB81 IBTX3 | 110 | 1.5 days | Mon 02/03/20 | Tue 03/03/20
TANDRAGEE |  | section '2L' MB57 WEATHERSHIELD DEFECT | 110 | 1 day | Fri 06/03/20 | Fri 06/03/20
TANDRAGEE |  | SECTION '2R' MB78 IBTX3 | 110 | 1.5 days | Tue 03/03/20 | Wed 04/03/20
TANDRAGEE | BANBBRIDGE 'B' | SECTION '2R' MB86 IBTX3 | 110 | 1.5 days | Tue 03/03/20 | Wed 04/03/20
TANDRAGEE | NEWRY 'A' | TAN - NRY 'A' MB50 and cable oil works | 110 | 1 wk | Mon 02/03/20 | Fri 06/03/20
|  | Start: Mon 09/03/20 - Sun 15/03/20 |  | 5d | Mon 09/03/20 | Mon 16/03/20
TANDRAGEE |  | TANDRAGEE MAIN SECTION A1 BUSBAR (BUSBAR) - GB93 MAINT. | 275 | 3 days | Wed 11/03/20 | Fri 13/03/20
TANDRAGEE |  | TANDRAGEE MAIN SECTION A2 BUSBAR (BUSBAR) - GB94 MAINT | 275 | 2 days | Fri 13/03/20 | Mon 16/03/20
COOLKEERAGH | LISAGHMORE 'B' | 12h3 repair | 110 | 1 day | Sat 14/03/20 | Sat 14/03/20
BALLYLUMFORD |  | B10 REPLACE BUSBARS MD65 | 110 | 1 day | Mon 09/03/20 | Mon 09/03/20
KILROOT | NIKGT3 | GEN | GEN | 1 day | Tue 10/03/20 | Tue 10/03/20
KILROOT | NIKGT4 | GEN | GEN | 1 day | Wed 11/03/20 | Wed 11/03/20
KILROOT | NIKGT3 | GEN | GEN | 1 day | Thu 12/03/20 | Thu 12/03/20
TAMNAMORE |  | GP25 MAINT | 275 | 1 day | Tue 10/03/20 | Tue 10/03/20
TAMNAMORE | TANDRAGEE 'A' | GP65 MAINT | 275 | 1 wk | Mon 09/03/20 | Fri 13/03/20
KILROOT |  | KPS CT MATCHIN EG244 ( PROJECTS) | 275 | 1 day | Fri 13/03/20 | Fri 13/03/20
TANDRAGEE |  | MB10 ( bus-coupler) | 110 | 5 days | Mon 09/03/20 | Fri 13/03/20
BALLYVALLAGH | BALLYLUMFORD 'A' | ME30 MAINT | 110 | 4 days | Mon 09/03/20 | Thu 12/03/20
|  | Start: Mon 16/03/20 - Sun 22/03/20 |  | 8d | Mon 16/03/20 | Fri 27/03/20
BALLYLUMFORD | MAGHERAFELT | BPS - MAG (OHL WORK) - TROLLEY WORK AND TOWER PAINTING | 275 | 1 wk | Wed 18/03/20 | Tue 24/03/20
BALLYLUMFORD |  | BPS IBTX 1 sealing end repairs | 275 | 2 days | Fri 20/03/20 | Sun 22/03/20
TANDRAGEE |  | TANDRAGEE MAIN INTERBUS 1 MINOR and TR1(WTI MEASUREMENTS) - MEASURE WTI FOR JAMIE MC HENDRY | 275 | 1 day | Wed 18/03/20 | Wed 18/03/20
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2L ( BUSBAR ) 2H2 | 110 | 2 days | Thu 19/03/20 | Fri 20/03/20
KILROOT | NIK2 | GEN | GEN | 8 days | Mon 16/03/20 | Wed 25/03/20
KILROOT | NIKGT4 | GEN | GEN | 1 day | Wed 18/03/20 | Wed 18/03/20
BALLYVALLAGH | BALLYLUMFORD 'B' | ME40 MAINT | 110 | 4 days | Mon 16/03/20 | Thu 19/03/20
LIMAVADY |  | TX2 CX193 BROKEN CLAMP | 110 | 1 day | Sat 21/03/20 | Sat 21/03/20
FINAGHY |  | TX2 MAJOR | 110 | 8 days | Wed 18/03/20 | Fri 27/03/20
|  | Start: Mon 23/03/20 - Sun 29/03/20 |  | 5d | Mon 23/03/20 | Thu 02/04/20
KILROOT | NIKGT1 | GEN | GEN | 1 day | Tue 24/03/20 | Tue 24/03/20
KILROOT | NIKGT2 | GEN | GEN | 1 day | Fri 27/03/20 | Fri 27/03/20
TAMNAMORE | TANDRAGEE 'B' | GP85 MAINT | 275 | 1 wk | Fri 27/03/20 | Thu 02/04/20
TANDRAGEE | DRUMNAKELLY 'B' | MB15 DRU B | 110 | 5 days | Mon 23/03/20 | Fri 27/03/20
BALLYVALLAGH | BALLYLUMFORD 'A' | me30 ct retest | 110 | 1 day | Wed 25/03/20 | Wed 25/03/20
TREMOGE | OMAGH | TRE - OMA ( Lines ) - Diversion around fox's Yard | 110 | 1 wk | Mon 23/03/20 | Fri 27/03/20
TREMOGE | OMAGH | TRE - OMA ( Lines ) - Diversion around fox's Yard Undercrossing poles 338-337. | 110 | 1 day | Wed 25/03/20 | Wed 25/03/20
BALLYMENA |  | TX1 MINOR | 110 | 4 days | Mon 23/03/20 | Thu 26/03/20
TREMOGE | OMAGH | undercrossing pole 337 - 338 | 110 | 1 day | Wed 25/03/20 | Wed 25/03/20
|  | Start: Mon 30/03/20 - Sun 05/04/20 |  | 30d | Mon 30/03/20 | Tue 12/05/20
COLERAINE |  | COLERAINE T1 (ETX CHANGE) - PROJECT WORK | 110 | 1 wk | Fri 03/04/20 | Thu 09/04/20
COLERAINE |  | COLERAINE T1 (TRANSFORMER '1') - EARTHING TRANSFORMER INSTALLATION | 110 | 1 wk | Fri 03/04/20 | Thu 09/04/20
NEWTOWNARDS |  | FIT SWAN DIVERTIERS ON CAS-NAR A (BIRD DIVERTER AT BILLY NEIL PLAYING FIELD T242-244) - OHL WORK | 110 | 1 day | Thu 02/04/20 | Thu 02/04/20
NEWTOWNARDS |  | FIT SWAN DIVERTIERS ON CAS-NAR B (BIRD DIVERTER AT BILLY NEIL PLAYING FIELD T242-244) - OHL WORK | 110 | 1 day | Wed 01/04/20 | Wed 01/04/20
KELLS |  | INTERLOCKING OUTAGES (PROJECTS) - | 110 | 6 wks | Wed 01/04/20 | Tue 12/05/20
TANDRAGEE |  | SECTION '1R' ISOLATORS (MB39 AND EM23) - MAINTENANCE | 110 | 3 days | Wed 01/04/20 | Fri 03/04/20
COOLKEERAGH |  | 11h0 sf6 leak detection /top up | 110 | 1 day | Wed 01/04/20 | Wed 01/04/20
KILROOT | NIK1 | GEN | GEN | 2 days | Wed 01/04/20 | Thu 02/04/20
TANDRAGEE | Newry A | MB50 MINOR | 110 | 4 days | Mon 30/03/20 | Thu 02/04/20
BALLYMENA |  | T2 MINOR | 110 | 4 days | Mon 30/03/20 | Thu 02/04/20
COOLKEERAGH |  | TX1 LNER top up | 110 | 1 day | Fri 03/04/20 | Fri 03/04/20
|  | Start: Mon 06/04/20 - Sun 12/04/20 |  | 5d | Mon 06/04/20 | Fri 10/04/20
CASTLEREAGH | CARMONEY 'A' | CAR MC25 (CAR A) - MINOR AND ASSOCIATED PLANT | 110 | 5 days | Mon 06/04/20 | Fri 10/04/20
COLERAINE |  | 4L0 MAINT and sf6 leak detection | 110 | 2 days | Mon 06/04/20 | Tue 07/04/20
TANDRAGEE | TAMNAMORE 'A' | GB25 MAINT | 275 | 5 days | Mon 06/04/20 | Fri 10/04/20
BALLYLUMFORD | KELLS | GD50 | 275 | 5 days | Mon 06/04/20 | Fri 10/04/20
Ballylumford | NIB32 | GEN | GEN | 1 day | Tue 07/04/20 | Tue 07/04/20
Ballylumford | NIB31 | GEN | GEN | 1 day | Tue 07/04/20 | Tue 07/04/20
|  | Start: Mon 13/04/20 - Sun 19/04/20 |  | 2d | Wed 15/04/20 | Fri 17/04/20
CARMONEY | CASTLEREAGH 'B' | cvt maintenance | 110 | 2 days | Wed 15/04/20 | Thu 16/04/20
BANBRIDGE |  | TX1 & TX3 LNER | 110 | 1 day | Thu 16/04/20 | Thu 16/04/20
RATHGAEL |  | TX1 LNER | 110 | 1 day | Fri 17/04/20 | Fri 17/04/20
BANBRIDGE |  | TX2 & TX4 LNER | 110 | 1 day | Fri 17/04/20 | Fri 17/04/20
|  | Start: Mon 20/04/20 - Sun 26/04/20 |  | 10d | Mon 20/04/20 | Thu 07/05/20
BALLYLUMFORD |  | BPS IBTX 1 MAJOR AND C/B'S (ETX CHANGE) - MINOR | 275 | 7 days | Mon 20/04/20 | Tue 28/04/20
TANDRAGEE | NEWRY 'B' | TAN - NRY B (TOWER PAINTING ) - TOWER PAINTING | 110 | 2 wks | Fri 24/04/20 | Thu 07/05/20
OMAGH |  | 2M0 MAINT | 110 | 2 days | Wed 22/04/20 | Thu 23/04/20
COOLKEERAGH | LIMAVADY | 6H0 MINOR | 110 | 4 days | Mon 20/04/20 | Thu 23/04/20
COOLKEERAGH |  | 6H0 MINOR | 110 | 4 days | Mon 20/04/20 | Thu 23/04/20
KILROOT |  | GJ25 MAINT | 110 | 5 days | Mon 20/04/20 | Fri 24/04/20
CASTLEREAGH |  | INTERBUS TX1 MINOR and oil works | 275 | 1 wk | Wed 22/04/20 | Tue 28/04/20
NEWRY |  | TX1 tap changer repair to mech box | 110 | 3 days | Tue 21/04/20 | Thu 23/04/20
|  | Start: Mon 27/04/20 - Sun 03/05/20 |  | 25d | Mon 27/04/20 | Wed 03/06/20
BALLYLUMFORD |  | BPS IBTX2 MAJOR AND C/B'S (ETX CHANGE) - MINOR | 275 | 7 days | Mon 27/04/20 | Tue 05/05/20
COOLKEERAGH | STRABANE 'B' | 4H0 MINOR ( INCLUDE 4H2) | 110 | 4 days | Mon 27/04/20 | Thu 30/04/20
BALLYMENA |  | ballymena TX4 sheath test | 110 | 1 day | Fri 01/05/20 | Fri 01/05/20
TANDRAGEE | TAMNAMORE 'B' | GB15 MAINT | 275 | 5 days | Mon 27/04/20 | Fri 01/05/20
Moyle | MOYLE | GEN | GEN | 1 day | Thu 30/04/20 | Thu 30/04/20
HANNAHSTOWN | DONEGALL 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | Thu 30/04/20 | Wed 03/06/20
CASTLEREAGH |  | INTERBUS tx3 MINOR and guage/22kv bushing repairs | 275 | 1 wk | Tue 28/04/20 | Mon 04/05/20
GORT |  | MT10 MAINT | 110 | 4 days | Mon 27/04/20 | Thu 30/04/20
|  | Start: Mon 04/05/20 - Sun 10/05/20 |  | 25d | Mon 04/05/20 | Wed 10/06/20
CARMONEY |  | CAR 3C4 (ISOL ESW ONLY) - MAINTENANCE | 110 | 3 days | Wed 06/05/20 | Fri 08/05/20
COOLKEERAGH |  | INTERBUS TRANSFORMER 1 MINOR ( oil sampling cables) | 275 | 4 days | Mon 04/05/20 | Thu 07/05/20
TANDRAGEE | DRUMNAKELLY 'C' | MB25 (DRU C) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Mon 04/05/20 | Thu 07/05/20
TANDRAGEE | NEWRY 'B' | TAN - NRY B (PROJECTS) - TELEPROTECTION CHANGE AND DISTANCE PROTECTION | 110 | 5 wks | Thu 07/05/20 | Wed 10/06/20
NEWRY |  | TX2 PAINTING (PROJECTS) - PROJECT WORK | 110 | 2 wks | Thu 07/05/20 | Wed 20/05/20
TAMNAMORE | CREAGH | creagh - tamnamore sheath tests | 110 | 1 day | Wed 06/05/20 | Wed 06/05/20
BALLYVALLAGH | LARNE 'B' | ME35 MAINT | 110 | 4 days | Mon 04/05/20 | Thu 07/05/20
|  | Start: Mon 11/05/20 - Sun 17/05/20 |  | 10d | Mon 11/05/20 | Tue 26/05/20
COOLKEERAGH |  | CPS IBTX2 MINOR | 275 | 1 wk | Mon 11/05/20 | Fri 15/05/20
CREGAGH |  | CRE TX B MAJOR & DEFECTS GASSING ON TRANSFORMER (INVESTIGATION WORKS) - WORK FOR LEONARD TAGGART | 110 | 2 wks | Wed 13/05/20 | Tue 26/05/20
GORT |  | GRT TX (MAINT) - INSTALL NEW BUSHING SPACES TO NEUTRAL | 110 | 2 days | Mon 11/05/20 | Tue 12/05/20
CREGAGH |  | TX A DEFECTS OIL LEAKS AND GASSING ON TRANSFORMER (INVESTIGATION WORKS) - WORK FOR LEONARD TAGGART | 110 | 1 wk | Thu 14/05/20 | Wed 20/05/20
LIMAVADY | COLERAINE | Isols assoc with Col circuit | 110 | 1 wk | Wed 13/05/20 | Tue 19/05/20
LIMAVADY | COOLKEERAGH | Isols assoc with CPS Circuit + CVT maint only | 110 | 1 wk | Mon 11/05/20 | Fri 15/05/20
BALLYLUMFORD | EDEN 'A' | MD60 | 110 | 5 days | Mon 11/05/20 | Fri 15/05/20
CASTLEREAGH | CREGAGH 'B' | OIL WORKS AND SHEATH TESTS | 110 | 2 wks | Wed 13/05/20 | Tue 26/05/20
CASTLEREAGH | CREGAGH 'b' | SHEATH TESTS | 110 | 2 wks | Wed 13/05/20 | Tue 26/05/20
GORT |  | TX2 MAJOR & MT15 MAINT | 110 | 8 days | Mon 11/05/20 | Wed 20/05/20
|  | Start: Mon 18/05/20 - Sun 24/05/20 |  | 5d | Mon 18/05/20 | Fri 22/05/20
KELLS | BALLYLUMFORD | KELLS - BPS CVT (KELLS & BUS COUPLER ISOLATOR ) - CVT MAINTENANCE & TESTING PLUS EG118 | 275 | 3 days | Wed 20/05/20 | Fri 22/05/20
DRUMNAKELLY | TAMNAMORE 'A' | 4K4,3K8,CX42 & EK3 | 110 | 2.5 days | Mon 18/05/20 | Wed 20/05/20
DRUMNAKELLY | TAMNAMORE 'B' | 6K4,5K8,CX44 & EK5 | 110 | 2.5 days | Wed 20/05/20 | Fri 22/05/20
LIMAVADY |  | 54v0 measurements | 110 | 1 day | Wed 20/05/20 | Wed 20/05/20
KELLS | GLENGORMLEY 'A' | cable sheath tests | 110 | 1 day | Wed 20/05/20 | Wed 20/05/20
KELLS | GLENGORMLEY 'B' | CABLE SHEATH TESTS & CABLE WORKS | 110 | 1 day | Tue 19/05/20 | Tue 19/05/20
Coolkeeragh | NICGT8 | GEN | GEN | 5 days | Mon 18/05/20 | Fri 22/05/20
KILROOT | NIK1 | GEN | GEN | 3 days | Wed 20/05/20 | Fri 22/05/20
KILROOT |  | GJ35 SF6 TOP UP | 275 | 1 day | Thu 21/05/20 | Thu 21/05/20
KILROOT |  | GJ45 SF6 TOP UP | 275 | 1 day | Thu 21/05/20 | Thu 21/05/20
COOLKEERAGH |  | GT8 OUTAGE FOR CESB | 110 | 1 wk | Mon 18/05/20 | Fri 22/05/20
COOLKEERAGH |  | gt8 sheath test | 110 | 1 day | Tue 19/05/20 | Tue 19/05/20
BALLYLUMFORD | EDEN 'B' | MD55 | 110 | 5 days | Mon 18/05/20 | Fri 22/05/20
KELLS |  | MF30 SF6 LEAK REPAIRS | 110 | 1 day | Fri 22/05/20 | Fri 22/05/20
KILLYMALLAGHT |  | TX 1 MAJOR & MR20 MAINT | 110 | 5 days | Mon 18/05/20 | Fri 22/05/20
|  | Start: Mon 25/05/20 - Sun 31/05/20 |  | 15d | Tue 26/05/20 | Mon 15/06/20
STRABANE |  | PST REFURBISHMENT - ISOLATORS ONLY | 110 | 3 wks | Tue 26/05/20 | Mon 15/06/20
STRABANE |  | 2SO AND ISOLATORS | 110 | 3 wks | Tue 26/05/20 | Mon 15/06/20
STRABANE |  | 9S0 MAINT AND ISOLATORS | 110 | 3 wks | Tue 26/05/20 | Mon 15/06/20
DRUMNAKELLY | TANDRAGEE 'A' | CVT maint | 110 | 1.5 days | Tue 26/05/20 | Wed 27/05/20
DRUMNAKELLY | TANDRAGEE 'B' | CX40,2K4,1K8 & EK9 | 110 | 2.5 days | Wed 27/05/20 | Fri 29/05/20
BALLYLUMFORD |  | GD40 MAINTENANCE | 275 | 5 days | Tue 26/05/20 | Mon 01/06/20
KILROOT |  | GJ65 MAINT | 275 | 5 days | Tue 26/05/20 | Mon 01/06/20
GORT |  | MT40 MAINT | 110 | 4 days | Tue 26/05/20 | Fri 29/05/20
COOLKEERAGH | SPRINGTOWN 'B' | sheath repair at coolkeeragh | 110 | 1 day | Fri 29/05/20 | Fri 29/05/20
|  | Start: Mon 01/06/20 - Sun 07/06/20 |  | 25d | Mon 01/06/20 | Thu 09/07/20
CASTLEREAGH | RATHGAEL 'A' | CAS - RAT A (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Fri 05/06/20 | Thu 09/07/20
NEWRY |  | TX2 MAJOR | 110 | 2 wks | Fri 05/06/20 | Thu 18/06/20
DUNGANNON |  | 1J0 MAINT | 110 | 2 days | Mon 01/06/20 | Tue 02/06/20
DUNGANNON |  | 2J0 MAINT | 110 | 2 days | Wed 03/06/20 | Thu 04/06/20
ENNISKILLEN |  | 3P0 MAINT | 110 | 3 days | Tue 02/06/20 | Thu 04/06/20
COOLKEERAGH | SPRINGTOWN 'B' | 16H0 SF6 GUAGE REPAIR | 110 | 1 day | Thu 04/06/20 | Thu 04/06/20
COOLKEERAGH |  | CAP BANK CT FAULT AND 15H1 MAINT | 110 | 2 days | Tue 02/06/20 | Wed 03/06/20
ENNISKILLEN |  | ENN 3P0 MINOR AND SF6 LEAKS | 110 | 3 days | Tue 02/06/20 | Thu 04/06/20
KELLS |  | GF115 MAINT | 275 | 4 days | Tue 02/06/20 | Fri 05/06/20
HANNAHSTOWN | LISBURN 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stage 1 | 110 | 5 wks | Mon 01/06/20 | Fri 03/07/20
HANNAHSTOWN | LISBURN 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stage 2 | 110 | 5 wks | Mon 01/06/20 | Fri 03/07/20
TANDRAGEE | NEWRY 'A' | TAN - NRY 'A' cable oil works | 110 | 1 wk | Mon 01/06/20 | Fri 05/06/20
TANDRAGEE | NEWRY 'B' | TAN - NRY 'B' CABLE OIL WORKS | 110 | 1 wk | Fri 05/06/20 | Thu 11/06/20
DONEGALL |  | TX D MAJOR | 110 | 2 wks | Mon 01/06/20 | Fri 12/06/20
|  | Start: Mon 08/06/20 - Sun 14/06/20 |  | 10d | Mon 08/06/20 | Thu 25/06/20
BALLYLUMFORD |  | BALLYLUMFORD GTTX2 110KV CABLE (BALLYLUMFORD GTTX2 110KV CABLE) - SHEATH TEST | 110 | 2 days | Fri 12/06/20 | Mon 15/06/20
COOLKEERAGH | MAGHERAFELT | CPS-MAG 'B' COUPLING CAPACITOR - COUPLING CAPACITOR JOB | 275 | 5 days | Mon 08/06/20 | Fri 12/06/20
LARNE |  | LARNE TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES AND TAPCHANGER REPAIR | 110 | 2 wks | Fri 12/06/20 | Thu 25/06/20
COOLKEERAGH | MAGHERAFELT | GA55 MAINT | 275 | 5 days | Mon 08/06/20 | Fri 12/06/20
Ballylumford | NIB31 | GEN | GEN | 4 days | Wed 10/06/20 | Sat 13/06/20
Ballylumford | NIB32 | GEN | GEN | 4 days | Sun 14/06/20 | Wed 17/06/20
MAGHERAFELT | COOLKEERAGH 'B' | GH45 MAINT | 275 | 5 days | Mon 08/06/20 | Fri 12/06/20
OMAGH |  | TX1 MAJOR | 110 | 8 days | Mon 08/06/20 | Wed 17/06/20
|  | Start: Mon 15/06/20 - Sun 21/06/20 |  | 25d | Mon 15/06/20 | Thu 23/07/20
MAGHERAFELT | COOLKEERAGH 'B' | CPS EARTHING UPGRADE OUTAGES (PROJECTS) - PROJECT WORK SURGE ARRESTOR EARTH | 275 | 1 day | Mon 15/06/20 | Mon 15/06/20
DUNGANNON |  | DUNGANNON MAIN T1 MAJOR ( 110/33KV) (COOLER UPGRADES) - | 110 | 3 wks | Mon 15/06/20 | Fri 03/07/20
ENNISKILLEN |  | ENNISKILLEN MAIN T1 (110/33) (TX1 COOLER REPAIRS) - OIL LEAK REPAIRS | 110 | 2 wks | Fri 19/06/20 | Thu 02/07/20
COOLKEERAGH |  | 8H0 minor | 110 | 2 days | Mon 15/06/20 | Tue 16/06/20
COOLKEERAGH |  | 8H0 minor ,8h3 and cvt --- change over Tue pm | 110 | 3 days | Tue 16/06/20 | Thu 18/06/20
MAGHERAFELT | COOLKEERAGH 'B' | cvt maint | 275 | 2 days | Mon 15/06/20 | Tue 16/06/20
KILROOT | NIK2 | GEN | GEN | 2 days | Mon 15/06/20 | Tue 16/06/20
Ballylumford | NIB32 | GEN | GEN | 3 days | Wed 17/06/20 | Fri 19/06/20
Coolkeeragh | NIC30 | GEN | GEN | 2 days | Fri 19/06/20 | Sun 21/06/20
HANNAHSTOWN | LISBURN 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stage 3 | 110 | 5 wks | Fri 19/06/20 | Thu 23/07/20
HANNAHSTOWN | FINAGHY 'A' | MG17 REPAIR | 110 | 1 day | Thu 18/06/20 | Thu 18/06/20
KILLYMALLAGHT |  | MR5 MAINT --- change over Tue pm | 110 | 3 days | Tue 16/06/20 | Thu 18/06/20
KILLYMALLAGHT |  | MR5 MAINT and cvt | 110 | 2 days | Mon 15/06/20 | Tue 16/06/20
RATHGAEL |  | TRANSFORMER '1' MAJOR | 110 | 2 wks | Mon 15/06/20 | Fri 26/06/20
|  | Start: Mon 22/06/20 - Sun 28/06/20 |  | 20d | Mon 22/06/20 | Thu 23/07/20
CASTLEREAGH | KNOCK 'A' | CAS-KNO A (PROJECTS) - CABLE DIVERSION WORK | 110 | 4 wks | Fri 26/06/20 | Thu 23/07/20
TAMNAMORE | Drumkee | CONNECT NEW BATTERY STORAGE FACILITIES (DRUMKEE CONNECTION) - PROJECT WORK | 110 | 1 day | Tue 23/06/20 | Tue 23/06/20
HANNAHSTOWN |  | IBTX 1 MG21 REPAIR | 110 | 1 day | Thu 25/06/20 | Thu 25/06/20
STRABANE | killymallaght | KMT cvt at strabane | 110 | 1.5 days | Tue 23/06/20 | Wed 24/06/20
CASTLEREAGH | KNOCK 'A' | MC80 MINOR | 110 | 5 days | Fri 26/06/20 | Thu 02/07/20
KELLS | BALLYVALLAGH 'A' | MF90 MAINT | 110 | 4 days | Mon 22/06/20 | Thu 25/06/20
KILLYMALLAGHT |  | MR15 MAINT | 110 | 4 days | Tue 23/06/20 | Fri 26/06/20
KILLYMALLAGHT |  | MR15 MAINT & cvt -- change over Tue. evening | 110 | 2 days | Mon 22/06/20 | Tue 23/06/20
TAMNAMORE | section 1 busbar | proximity outage build MP15 stage 1 | 110 | 2 days | Tue 23/06/20 | Wed 24/06/20
COOLKEERAGH | SPRINGTOWN 'A' | sheath repair at coolkeeragh | 110 | 1 day | Thu 25/06/20 | Thu 25/06/20
|  | Start: Mon 29/06/20 - Sun 05/07/20 |  | 60d | Mon 29/06/20 | Fri 18/09/20
COOLKEERAGH |  | CPS IBTX2 MINOR (PROJECTS) - PROTECTION CHANGE | 275 | 12 wks | Mon 29/06/20 | Fri 18/09/20
COOLKEERAGH |  | civils start of july IBTX2 | 275 | 2 wks | Mon 29/06/20 | Fri 10/07/20
COLERAINE | LOGUESTOWN 'B' | COL- LOG B (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 29/06/20 | Fri 03/07/20
TANDRAGEE | mullavilly | CONNECT NEW BATTERY STORAGE FACILITIES (MULLAVILLY CONNECTION) - | 110 | 1 day | Wed 01/07/20 | Wed 01/07/20
Moyle | MOYLE | GEN | GEN | 3 days | Tue 30/06/20 | Thu 02/07/20
HANNAHSTOWN | LISBURN 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stage 4 replace mg47 downdropper | 110 | 5 wks | Thu 02/07/20 | Wed 05/08/20
LIMAVADY | COOLKEERAGH | LIM - CPS (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 29/06/20 | Fri 10/07/20
TAMNAMORE | section 2 busbar | proximity outage build MP14/em309 stage 2 | 110 | 2 days | Mon 29/06/20 | Tue 30/06/20
TANDRAGEE | section 1L busbar | Section 1L plus DRU C & War A proximity build MB31/EM6A STG1 | 110 | 3 days | Wed 01/07/20 | Fri 03/07/20
ANTRIM |  | TX1 SHEATH TEST | 110 | 1 day | Fri 03/07/20 | Fri 03/07/20
LOGUESTOWN |  | TX2 MAJOR | 110 | 2 wks | Mon 29/06/20 | Fri 10/07/20
|  | Start: Mon 06/07/20 - Sun 12/07/20 |  | 22.5d | Mon 06/07/20 | Wed 05/08/20
TAMNAMORE | DRUMNAKELLY 'B' | TMN - DRU 'B' (POLE REPLACEMENT AND TOWER PAINTING) - POLE REPLACEMENT AND TOWER PAINTING | 110 | 1 wk | Fri 10/07/20 | Thu 16/07/20
CARMONEY |  | 2C0 repair | 110 | 2 days | Mon 06/07/20 | Tue 07/07/20
DUNGANNON |  | 8J0 MAINT | 110 | 2 days | Mon 06/07/20 | Tue 07/07/20
Ballylumford | NIBGT2 | GEN | GEN | 1 day | Mon 06/07/20 | Mon 06/07/20
HANNAHSTOWN | LISBURN 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stg1 | 110 | 4.5 wks | Mon 06/07/20 | Wed 05/08/20
HANNAHSTOWN | LISBURN 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stg2 | 110 | 4.5 wks | Mon 06/07/20 | Wed 05/08/20
CASTLEREAGH |  | MC3 MAINT SECT '1L' | 110 | 3 days | Wed 08/07/20 | Fri 10/07/20
TANDRAGEE | section 2L busbar | Section 2L Plus either IBTX1 or NRY B Build MB28/MB29 and rest of bay STG2 | 110 | 3 days | Wed 08/07/20 | Fri 10/07/20
|  | Start: Mon 13/07/20 - Sun 19/07/20 |  | 148d | Mon 13/07/20 | Tue 28/07/20
COLERAINE | LIMAVADY | (OHL WORK) - COL-LIM | 110 | 2 wks | Mon 13/07/20 | Fri 24/07/20
HANNAHSTOWN | BALLYCRONANMORE | HAN - BYC (OHL WORK) - TROLLEY WORK AND TOWER PAINTING | 275 | 1 wk | Wed 15/07/20 | Tue 21/07/20
HANNAHSTOWN | BALLYCRONANMORE | HAN - BYC CVT FAULT (REPLACE CLAMP WITH NEW CLAMPS) - | 275 | 1 day | Wed 15/07/20 | Wed 15/07/20
CASTLEREAGH | NEWTOWNARDS 'B' | CABLE SHEATH TESTS & CABLE WORKS | 110 | 3 days | Wed 15/07/20 | Fri 17/07/20
KILROOT | TANDRAGEE | OHL insulator replacement | 275 | 2 days | Wed 15/07/20 | Thu 16/07/20
OMAGH |  | TX2 Tapchanger maintenance requested by Major | 110 | 2 wks | Wed 15/07/20 | Tue 28/07/20
|  | Start: Mon 20/07/20 - Sun 26/07/20 |  | 148d | Mon 20/07/20 | Tue 25/08/20
COLERAINE |  | COLERAINE T2 (ETX CHANGE) - PROJECT WORK | 110 | 1 wk | Mon 20/07/20 | Fri 24/07/20
KILROOT |  | KPS CT CHANGE BAY 9 CT'S Kells,B whole bay GJ26 side,GJ34 side,GJ31 side(PROJECTS) - CT REPLACEMENT BAY ( also gj35 & gj30 maint) | 275 | 5 wks | Mon 20/07/20 | Fri 21/08/20
LISBURN |  | LISBURN MAIN T1 (LISBURN MAIN T1) - 33KV BUSHINGS & COOLERS | 110 | 3 wks | Wed 22/07/20 | Tue 11/08/20
KILROOT | NIK1 | GEN | GEN | 21 days | Mon 20/07/20 | Mon 17/08/20
KILROOT | NIKGT1 | GEN | GEN | 21 days | Mon 20/07/20 | Mon 17/08/20
KILROOT |  | GJ30 MAINT | 275 | 5 days | Mon 20/07/20 | Fri 24/07/20
KILROOT |  | GJ35 MAINT | 275 | 5 days | Mon 20/07/20 | Fri 24/07/20
HANNAHSTOWN | LISBURN 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stg3 | 110 | 4.5 wks | Fri 24/07/20 | Tue 25/08/20
TAMNAMORE | section 1 busbar | MP13 build plus DUN B remove sect 1 stage 3 | 110 | 4 days | Wed 22/07/20 | Sat 25/07/20
|  | Start: Mon 27/07/20 - Sun 02/08/20 |  | 15d | Mon 27/07/20 | Fri 14/08/20
LIMAVADY |  | 53V0 MAINT | 110 | 1 wk | Mon 27/07/20 | Fri 31/07/20
CASTLEREAGH |  | INTERBUS TX2 MAJOR and oil guage AND TERTIARY BUSHINGS (WITH REACTOR) | 275 | 3 wks | Mon 27/07/20 | Fri 14/08/20
|  | Start: Mon 03/08/20 - Sun 09/08/20 |  | 210.5d | Mon 03/08/20 | Mon 07/09/20
COLERAINE | COOLKEERAGH | (OHL WORK) - COL-CPS | 110 | 2 wks | Tue 04/08/20 | Tue 18/08/20
COLERAINE | LOGUESTOWN 'A' | COL- LOG A (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 03/08/20 | Fri 07/08/20
ENNISKILLEN | AGHYOULE | ENN - AGY (OHL WORK) - | 110 | 3 days | Mon 03/08/20 | Wed 05/08/20
TANDRAGEE | WARINGSTOWN 'A' | MB35 (WAR A) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Fri 07/08/20 | Wed 12/08/20
TANDRAGEE |  | SECTION '2L' ISOLATORS - MAINTENANCE | 110 | 8 days | Tue 04/08/20 | Thu 13/08/20
TANDRAGEE | BANBRIDGE 'A' | TAN - BAN A (LINES) - POLE REPLACEMENT | 110 | 1 wk | Mon 03/08/20 | Fri 07/08/20
LIMAVADY |  | 51V0 MAINT | 110 | 1 wk | Mon 03/08/20 | Fri 07/08/20
LIMAVADY |  | CVT assoc with CPS - testing | 110 | 1 day | Fri 07/08/20 | Fri 07/08/20
KILROOT | NIKGT2 | GEN | GEN | 7 days | Fri 07/08/20 | Mon 17/08/20
KILROOT | NIK2 | GEN | GEN | 7 days | Fri 07/08/20 | Mon 17/08/20
HANNAHSTOWN | LISBURN 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT stg4 | 110 | 4.5 wks | Thu 06/08/20 | Mon 07/09/20
|  | Start: Mon 10/08/20 - Sun 16/08/20 |  | 45d | Mon 10/08/20 | Fri 09/10/20
BALLYLUMFORD | MAGHERAFELT | BPS - MAG (PROJECTS) - CVT CHANGE | 275 | 2 wks | Mon 10/08/20 | Fri 21/08/20
BALLYLUMFORD | MAGHERAFELT | BPS-MAG CVT CHANGE AND OHL (PROJECTS) - OHL REFURB | 275 | 9 wks | Mon 10/08/20 | Fri 09/10/20
BALLYLUMFORD | MAGHERAFELT | BPS-MAG PROTECTION UPGRADE (PROJECTS) - PROTECTION CHANGE | 275 | 9 wks | Mon 10/08/20 | Fri 09/10/20
DUNGANNON |  | DUNGANNON MAIN T2 MAJOR ( 110/33KV) (COOLER UPGRADES) - | 110 | 3 wks | Mon 10/08/20 | Fri 28/08/20
DONEGALL | FINAGHY 'B' | FIN - DON 'B' (OHL WORK) - RESTRINGING | 110 | 2 wks | Mon 10/08/20 | Fri 21/08/20
TANDRAGEE | WARINGSTOWN 'B' | MB45 (WAR B) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Thu 13/08/20 | Tue 18/08/20
MAGHERAFELT | TAMNAMORE 'A' | TMN- MAG 'A' (OHL WORK) - SINGLE TENSION TOWER 228 | 275 | 5 days | Mon 10/08/20 | Fri 14/08/20
CARMONEY |  | 6C0 MAINT | 110 | 5 days | Mon 10/08/20 | Fri 14/08/20
STRABANE |  | 7S0 MAINT | 110 | 1 wk | Mon 10/08/20 | Fri 14/08/20
BALLYLUMFORD | MAGHERAFELT | BPS- MAG TROLLEY WORK | 275 | 1 wk | Mon 10/08/20 | Fri 14/08/20
OMAGH | STRABANE 'A' | EM9 YELLOW PHASE MAINTENANCE ( REPORTED 5/3/20 | 110 | 1 day | Fri 14/08/20 | Fri 14/08/20
HANNAHSTOWN | FINAGHY 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | Mon 10/08/20 | Fri 11/09/20
KELLS | BALLYVALLAGH 'B' | MF100 MAINT | 110 | 4 days | Mon 10/08/20 | Thu 13/08/20
KILLYMALLAGHT |  | MR25 MAINT | 110 | 4 days | Mon 10/08/20 | Thu 13/08/20
FINAGHY |  | TX1 Painting | 110 | 2 wks | Mon 10/08/20 | Fri 21/08/20
NEWTOWNARDS |  | TX2 MAJOR | 110 | 2 wks | Mon 10/08/20 | Fri 21/08/20
|  | Start: Mon 17/08/20 - Sun 23/08/20 |  | 168d | Mon 17/08/20 | Sun 23/08/20
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R (BUSBAR) - EH23 | 110 | 2 days | Thu 20/08/20 | Fri 21/08/20
KELLS | CREAGH | KEL - CRE (OHL WORK) - OHL WORK SPAN 69 -150 POLES ONLY | 110 | 4 days | Mon 17/08/20 | Thu 20/08/20
CREAGH | kellS | Creagh - kells sheath tests | 110 | 1 day | Sun 23/08/20 | Sun 23/08/20
STRABANE |  | CX235,cx242 cvt and ct. inc link cable | 110 | 3 days | Mon 17/08/20 | Wed 19/08/20
CASTLEREAGH |  | INTERBUS tx3 MINOR and oil guage AND BUSHING REPAIR/REPLACEMENT | 275 | 1 wk | Mon 17/08/20 | Fri 21/08/20
KELLS |  | KELLS IBTX1 AND MF45 (WITH REACTOR) | 275 | 1 wk | Mon 17/08/20 | Fri 21/08/20
KELLS | CREAGH | MF40 MAINT | 110 | 3 days | Mon 17/08/20 | Wed 19/08/20
CREAGH |  | MN25 Maint | 110 | 3 days | Mon 17/08/20 | Wed 19/08/20
|  | Start: Mon 24/08/20 - Sun 30/08/20 |  | 183d | Mon 24/08/20 | Fri 25/09/20
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) - 11H1 & 15H1 | 110 | 5 days | Mon 24/08/20 | Fri 28/08/20
KILROOT |  | KPS CT CHANGE BAY 3 CT'S gj44 side of GJ45(PROJECTS) - CT REPLACEMENT BAY (also GJ45 maint) | 275 | 2 wks | Mon 24/08/20 | Fri 04/09/20
RASHARKIN | KELLS | RKN - KEL (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 24/08/20 | Fri 04/09/20
TANDRAGEE | CASTLEREAGH | TAN - CAS (OHL WORK) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Mon 24/08/20 | Fri 04/09/20
LISAGHMORE |  | TX1 (PROJECTS) TCHANGE CONTROLS AND PROTECTION PANELS | 110 | 5 wks | Mon 24/08/20 | Fri 25/09/20
COOLKEERAGH |  | 13H0 SF6 GUAGE REPLACEMENT | 110 | 3 days | Fri 28/08/20 | Tue 01/09/20
COOLKEERAGH | SPRINGTOWN 'A' | 13HO CT test and CVT retest | 110 | 2 days | Fri 28/08/20 | Mon 31/08/20
TANDRAGEE |  | GB74 MAINT | 275 | 3 days | Mon 24/08/20 | Wed 26/08/20
Coolkeeragh | NIC30 | GEN | GEN | 7 days | Sat 29/08/20 | Mon 07/09/20
TANDRAGEE |  | MB60 MINOR | 110 | 4 days | Mon 24/08/20 | Thu 27/08/20
TANDRAGEE |  | TANDRAGEE IBTX2 MAJOR (WITH REACTOR) | 275 | 3 wks | Mon 24/08/20 | Fri 11/09/20
CREAGH |  | TX2 MAJOR & MN20 MAINT | 110 | 2.5 wks | Mon 24/08/20 | Wed 09/09/20
|  | Start: Mon 31/08/20 - Sun 06/09/20 |  | 15d | Mon 31/08/20 | Mon 21/09/20
KELLS | BALLYVALLAGH 'B' | KEL-BVG B (OHL WORK) - OHL WORK | 110 | 7 days | Mon 31/08/20 | Tue 08/09/20
KILROOT | CASTLEREAGH | KPS - CAS (LINES) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Sat 05/09/20 | Thu 17/09/20
LISBURN |  | LISBURN MAIN T2 ( 110/33KV) (LISBURN MAIN T2) - 33KV BUSHINGS & COOLERS | 110 | 3 wks | Tue 01/09/20 | Mon 21/09/20
STRABANE | OMAGH 'B' | STR- OMA B (OHL WORK) - OHL WORK | 110 | 2 wks | Mon 31/08/20 | Fri 11/09/20
TANDRAGEE | DRUMNAKELLY 'A' | TAN - DRU A (OHL WORK) - | 110 | 2 wks | Tue 01/09/20 | Mon 14/09/20
COLERAINE |  | 5L0 MAINT | 110 | 3 days | Wed 02/09/20 | Fri 04/09/20
LIMAVADY |  | 52V0 REPAIR linkage /INVESTIGATION | 110 | 1 day | Mon 31/08/20 | Mon 31/08/20
TAMNAMORE |  | INTERBUS 2 MAJOR AND MP60/GP75 | 275 | 3 wks | Mon 31/08/20 | Fri 18/09/20
CASTLEREAGH | ROSEBANK 'A' | MC11 MAINT SECT '1L' | 110 | 2 days | Tue 01/09/20 | Wed 02/09/20
|  | Start: Mon 07/09/20 - Sun 13/09/20 |  | 30d | Mon 07/09/20 | Thu 22/10/20
CASTLEREAGH | BALLYNAHINCH 'A' | CAS - BNH A (OHL WORK) - OHL WORK | 110 | 2 wks | Mon 07/09/20 | Fri 18/09/20
CASTLEREAGH | BALLYNAHINCH 'A' | CAS - BNH A (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 07/09/20 | Fri 09/10/20
KELLS | BALLYVALLAGH 'A' | KEL - BVG A (OHL WORK) - OHL WORK | 110 | 1 wk | Wed 09/09/20 | Tue 15/09/20
RASHARKIN | COLERAINE | RKN - COL (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 07/09/20 | Fri 18/09/20
COLERAINE | LIMAVADY | 3L4,2L8,CX192 AND EL2 ( LIMAVADY CIRCUIT) | 110 | 3 days | Tue 08/09/20 | Thu 10/09/20
COLERAINE |  | 9L3 isolator maintenance | 110 | 1 day | Mon 07/09/20 | Mon 07/09/20
DONEGALL | FINAGHY 'A' & 'B' | FINAGHY - DONEGALL A & B DOUBLE CIRCUIT EARTH WIRE | 110 | 3 days | Fri 11/09/20 | Tue 15/09/20
TANDRAGEE |  | reactor 3 installation | 110 | 6 wks | Fri 11/09/20 | Thu 22/10/20
CREAGH |  | TX 1 MAJOR & MN10 MAINT | 110 | 2.5 wks | Thu 10/09/20 | Sat 26/09/20
|  | Start: Mon 14/09/20 - Sun 20/09/20 |  | 25d | Mon 14/09/20 | Fri 16/10/20
DONEGALL |  | DONEGALL TX C (PROJECTS) - TRANSFORMER PAINTING | 110 | 2 wks | Mon 14/09/20 | Fri 25/09/20
OMAGH | STRABANE 'A' | OMA - STR A (OHL WORK) - POLE CHANGES AND TOWER WORK | 110 | 1 wk | Mon 14/09/20 | Fri 18/09/20
DONEGALL |  | 1D0 MAJOR | 110 | 1 wk | Mon 14/09/20 | Fri 18/09/20
KILROOT | NIK2 | GEN | GEN | 11 days | Mon 14/09/20 | Mon 28/09/20
HANNAHSTOWN |  | HANNAHSTOWN MG60 CT'S AND MG61/MG62 ISOLATOR SWAP INCLUDING IBTx2 PROXIMITY | 110 | 5 wks | Mon 14/09/20 | Fri 16/10/20
BELFAST NORTH MAIN |  | TX A MAJOR | 110 | 2 wks | Mon 14/09/20 | Fri 25/09/20
DONEGALL |  | TX C MAJOR | 110 | 2 wks | Mon 14/09/20 | Fri 25/09/20
|  | Start: Mon 21/09/20 - Sun 27/09/20 |  | 45d | Mon 21/09/20 | Fri 20/11/20
COOLKEERAGH | SPRINGTOWN 'A' | CPS - SPR 'A' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 21/09/20 | Fri 25/09/20
COOLKEERAGH | STRABANE 'B' | CPS - STR 'B' (OHL WORK) - TOWER PAINTING | 110 | 2.5 wks | Mon 21/09/20 | Wed 07/10/20
TANDRAGEE | KILROOT | TAN - KPS (OHL WORK) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Mon 21/09/20 | Fri 02/10/20
TREMOGE | OMAGH | TRE - OMA (LINES) - POLE CHANGES | 110 | 2 wks | Mon 21/09/20 | Fri 02/10/20
TREMOGE | OMAGH | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION | 110 | 20 days | Mon 21/09/20 | Fri 16/10/20
Ballylumford | NIB31 | GEN | GEN | 45 days | Mon 21/09/20 | Fri 20/11/20
Ballylumford | NIB32 | GEN | GEN | 11 days | Mon 21/09/20 | Mon 05/10/20
|  | Start: Mon 28/09/20 - Sun 04/10/20 |  | 26d | Mon 28/09/20 | Thu 05/11/20
BALLYLUMFORD |  | BALLYLUMFORD GTTX1 110KV CABLE (BALLYLUMFORD GTTX1 110KV CABLE) - SHEATH TEST | 110 | 1 day | Thu 01/10/20 | Thu 01/10/20
TANDRAGEE |  | BUS ZONE (PROJECTS) - PROTECTION CHANGE | 275 | 26 days | Thu 01/10/20 | Thu 05/11/20
COOLKEERAGH | SPRINGTOWN 'B' | CPS - SPR 'B' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 28/09/20 | Fri 02/10/20
BALLYLUMFORD |  | DISCONNECT STATION TX1 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 110 | 3 days | Thu 01/10/20 | Mon 05/10/20
BELFAST NORTH MAIN | DONEGALL | DONEGALL - BELFAST NORTH MAIN CABLE WORKS - CSE REPLACEMENTS | 110 | 1 wk | Mon 28/09/20 | Fri 02/10/20
DRUMNAKELLY |  | DRU (TX1 & TX3 TAPCHANGER PANELS) - PROJECTS | 110 | 2 wks | Mon 28/09/20 | Fri 09/10/20
TAMNAMORE | CREAGH | OHL WORK (POLE REPLACEMENT) - POLES | 110 | 2 wks | Mon 28/09/20 | Fri 09/10/20
LISAGHMORE |  | TX2 (PROJECTS) TCHANGE CONTROLS AND PROTECTION PANELS | 110 | 5 wks | Mon 28/09/20 | Fri 30/10/20
BELFAST NORTH MAIN | DONEGALL | B' CIRCUIT OILWORKS, cable identification & leak repairs | 110 | 2 wks | Mon 28/09/20 | Fri 09/10/20
TANDRAGEE |  | CT RATIO CHANGES 600 - 1000 | 275 | 5 wks | Thu 01/10/20 | Wed 04/11/20
TANDRAGEE | section 2L busbar | Section 1L downdropper to MB31,Busbar Mb29- CSE STG4 | 110 | 5 days | Wed 30/09/20 | Tue 06/10/20
TANDRAGEE | section 1L busbar | Section 2L downdropper to MB28,DRU C matching shots STG3 | 110 | 2 days | Mon 28/09/20 | Tue 29/09/20
BELFAST NORTH MAIN |  | TX B MAJOR | 110 | 2 wks | Mon 28/09/20 | Fri 09/10/20
ROSEBANK |  | TX1 COOLERS | 110 | 3 wks | Mon 28/09/20 | Fri 16/10/20
|  | Start: Mon 05/10/20 - Sun 11/10/20 |  | 50d | Mon 05/10/20 | Fri 11/12/20
BALLYMENA |  | BALLYMENA TX4 CHANGE (TRANSFORMER CHANGE) - | 110 | 10 wks | Mon 05/10/20 | Fri 11/12/20
BALLYLUMFORD |  | DISCONNECT STATION TX3 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 110 | 3 days | Tue 06/10/20 | Thu 08/10/20
TANDRAGEE | LISBURN 'A' | TAN - LIS A (OHL WORK) - OHL WORK | 110 | 1 wk | Mon 05/10/20 | Fri 09/10/20
TANDRAGEE | mullavilly | Busbar to MB109 mullavilly | 110 | 1 day | Mon 05/10/20 | Mon 05/10/20
TAMNAMORE | section 2 busbar | Install MP14 D/dropper and matching Dun C STG4 | 110 | 3 days | Mon 05/10/20 | Wed 07/10/20
TAMNAMORE | section 1 busbar | install Sect 1 Bbars and connect MP16. STG5 | 110 | 4 days | Wed 07/10/20 | Sat 10/10/20
|  | Start: Mon 12/10/20 - Sun 18/10/20 |  | 248d | Mon 12/10/20 | Fri 11/12/20
BALLYLUMFORD | KELLS | BPS - KEL (OHL WORK) - OHL WORK | 275 | 1 wk | Mon 12/10/20 | Fri 16/10/20
BALLYLUMFORD | KELLS | BPS GD49 ( KELLS CCT) GD59 ( B/C ) (KELLS & BUS COUPLER ISOLATOR ) - BUS SECTION ISOLATORS. - SAFETY LINE TO BE FITTED | 275 | 1 wk | Mon 12/10/20 | Fri 16/10/20
BALLYLUMFORD | KELLS | BPS-KELLS ( PROJECTS) - PROTECTION CHANGE | 275 | 9 wks | Mon 12/10/20 | Fri 11/12/20
BALLYLUMFORD | KELLS | BPS-KELLS (PROJECTS) - CVT CHANGE | 275 | 2 wks | Mon 12/10/20 | Fri 23/10/20
CASTLEREAGH | BALLYNAHINCH 'B' | CAS - BNH B (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 12/10/20 | Fri 13/11/20
BALLYLUMFORD | KELLS | KELLS WALLBUSHING - REPLACE WALL BUSHING | 275 | 2 wks | Mon 12/10/20 | Fri 23/10/20
TANDRAGEE | LISBURN 'B' | TAN - LIS B (OHL WORK) - OHL WORK | 110 | 1 wk | Mon 12/10/20 | Fri 16/10/20
TAMNAMORE | Drumkee | drumkee connect busbar MP99 stage 6 | 110 | 1 day | Mon 12/10/20 | Mon 12/10/20
TANDRAGEE | DRUMNAKELLY 'B' | tower painting | 110 | 5 days | Mon 12/10/20 | Fri 16/10/20
|  | Start: Mon 19/10/20 - Sun 25/10/20 |  | 25d | Mon 19/10/20 | Fri 20/11/20
CASTLEREAGH | HANNAHSTOWN 'A' | CASTLEREAGH - HANNAHSTOWN A (LINES) - OHL WORK | 275 | 1 wk | Mon 19/10/20 | Fri 23/10/20
DONEGALL |  | DONEGALL TX A (MAJOR 1ST MAINTENANCE) - MAINTENANCE | 110 | 2 wks | Mon 19/10/20 | Fri 30/10/20
DONEGALL | FINAGHY 'A' | FIN - DON 'A' (OHL WORK) - RESTRINGING | 110 | 2 wks | Mon 19/10/20 | Fri 30/10/20
HANNAHSTOWN |  | MG15 ARCING HORNS (MG15 HANNAHSTOWN MAIN CB (FINAGHY A)) - ARCING HORNS | 110 | 1 day | Mon 19/10/20 | Mon 19/10/20
Coolkeeragh | NICGT8 | GEN | GEN | 2 days | Sat 24/10/20 | Mon 26/10/20
HANNAHSTOWN | FINAGHY 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | Mon 19/10/20 | Fri 20/11/20
DONEGALL |  | TX A MAJOR | 110 | 2 wks | Mon 19/10/20 | Fri 30/10/20
FINAGHY |  | TX2 painting | 110 | 3 wks | Mon 19/10/20 | Fri 06/11/20
|  | Start: Mon 26/10/20 - Sun 01/11/20 |  | 40d | Mon 26/10/20 | Thu 24/12/20
KILROOT |  | Bus-zone 3 zone | 275 | 8 wks | Sun 01/11/20 | Thu 24/12/20
HANNAHSTOWN |  | HANNAHSTOWN INTERBUS 2 MINOR (WITH REACTOR) | 275 | 1 wk | Mon 26/10/20 | Fri 30/10/20
|  | Start: Mon 02/11/20 - Sun 08/11/20 |  | 25d | Mon 02/11/20 | Fri 04/12/20
MAGHERAFELT |  | GH5 BUSCOUPLER PROTECTION (PROJECTS) - PROTECTION CHANGE | 275 | 5 wks | Mon 02/11/20 | Fri 04/12/20
TANDRAGEE | DRUMNAKELLY 'A' | PROTECTION UPGRAGE ON TAN - DRU 'A' | 110 | 5 wks | Mon 02/11/20 | Fri 04/12/20
|  | Start: Mon 16/11/20 - Sun 22/11/20 |  | 6d | Mon 16/11/20 | Sat 21/11/20
COOLKEERAGH | MAGHERAFELT A | CPS EARTHING UPGRADE OUTAGES (PROJECTS) - PROJECT WORK REMOVE SURGE ARRESTOR COUNTER | 275 | 2 days | Mon 16/11/20 | Tue 17/11/20
BALLYLUMFORD |  | GD30 SF6 ANALYSIS | 275 | 0.5 days | Mon 16/11/20 | Mon 16/11/20
KILROOT | NIKGT3 | GEN | GEN | 6 days | Mon 16/11/20 | Sat 21/11/20
|  | Start: Mon 23/11/20 - Sun 29/11/20 |  | 40d | Mon 23/11/20 | Thu 21/01/21
DONEGALL | HANNAHSTOWN | CABLE OIL FLUSHING WORKS (B' CIRCUIT OIL LEAK REPAIRS) - OIL WORKS & SHEATH TESTS, ISOLATOR MAINT REQUIRES TX OUT AT DONEGALL | 110 | 1 day | Sat 28/11/20 | Sat 28/11/20
CASTLEREAGH |  | CAS REACTOR 2 REPLACEMENT (PROJECTS) - REACTOR 2 / CAS IBTX.2 MAINTENANCE | 275 | 8 wks | Fri 27/11/20 | Thu 21/01/21
DONEGALL |  | DONEGALL TX B ISOLATORS (ISOL ESW ONLY) - MAINTENANCE | 110 | 2 days | Mon 23/11/20 | Tue 24/11/20
KILROOT | NIKGT4 | GEN | GEN | 6 days | Mon 23/11/20 | Sat 28/11/20
Coolkeeragh | NIC30 | GEN | GEN | 2 days | Sat 28/11/20 | Mon 30/11/20
HANNAHSTOWN | DONEGALL 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | Mon 23/11/20 | Fri 25/12/20
|  | Start: Mon 30/11/20 - Sun 06/12/20 |  | 30d | Tue 01/12/20 | Mon 11/01/21
MAGHERAFELT |  | Bus-zone 3 zone | 275 | 6 wks | Tue 01/12/20 | Mon 11/01/21
|  | Start: Mon 07/12/20 - Sun 13/12/20 |  | 5d | Mon 07/12/20 | Fri 11/12/20
MAGHERAFELT | COOLKEERAGH 'A' | CPS EARTHING UPGRADE OUTAGES (PROJECTS) - PROJECT WORK SURGE ARRESTOR EARTH | 275 | 1 day | Mon 07/12/20 | Mon 07/12/20
HANNAHSTOWN |  | HANNAHSTOWN INTERBUS 1 MINOR | 275 | 1 wk | Mon 07/12/20 | Fri 11/12/20