## Task_Table1
Text1 | Text2 | Name | Start_Date | Finish_Date | Duration | Text3 | Text4
BALLYMENA |  | BALLYMENA TX4 installation | 2022-02-07 | 2022-03-18 | 6 wks | PROJ | 110
CASTLEREAGH | TANDRAGEE | CAS - TAN PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 2022-02-07 | 2022-04-15 | 10 wks | PROJ | 275
CASTLEREAGH | TANDRAGEE | OHL AND TOWER PAINTING | 2022-02-07 | 2022-02-18 | 2 wks | OHL | 275
CASTLEREAGH |  | CONCRETE SUPPORT REMOVAL WORKS (TAN BAY) | 2022-02-07 | 2022-02-18 | 2 wks | PROJ | 275
TANDRAGEE |  | reactor 3 installation and IBTX3 minor | 2022-01-03 | 2022-02-11 | 6 wks | PROJ | 110
TANDRAGEE | CASTLEREAGH | GB105 MAINT | 2022-02-07 | 2022-02-11 | 1 wk | MAINT | 275
CASTLEREAGH |  | GC75 MAINT | 2022-02-14 | 2022-02-18 | 1 wk | MAINT | 110
BALLYLUMFORD |  | GD40 BUSCOUPLER PROTECTION | 2022-02-28 | 2022-03-25 | 4 wks | PROJ | 275
BALLYLUMFORD |  | BUSZONE 5 ZONE SCHEME | 2022-03-28 | 2022-04-29 | 5 wks | PROJ | 275
ENNISKILLEN |  | Divert cable on 110/33kV Tx1 & 2 | 2022-03-07 | 2022-03-11 | 1 wk | PROJ | 110
ENNISKILLEN |  | Divert cable on 110/33kV Tx3 | 2022-03-07 | 2022-03-11 | 1 wk | PROJ | 110
CASTLEREAGH |  | IBTX3 MAJOR and bushing replacement. Cable sheath test | 2022-02-14 | 2022-03-04 | 3 wks | MAINT | 275
CASTLEREAGH |  | GC65 MAINT | 2022-02-21 | 2022-02-25 | 1 wk | MAINT | 110
HANNAHSTOWN |  | 275KV ISOLATORS 2 SETS BYC GG6,GG7,GG9 | 2022-04-18 | 2022-07-29 | 15 wks | PROJ | 275
HANNAHSTOWN | BALLYCRONANMORE | PROTECTION WORKS FEEDER AND MESH CORNER PROTECTION | 2022-04-18 | 2022-07-29 | 15 wks | PROJ | 275
BALLYCRONANMORE | HANNAHSTOWN | BYC - HAN PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 2022-04-18 | 2022-06-24 | 10 wks | PROJ | 275
HANNAHSTOWN |  | INTERBUS 4 INSTALLATION OF BUND | 2022-04-18 | 2022-05-27 | 6 wks | PROJ | 275
HANNAHSTOWN |  | GG10 MAINT | 2022-04-18 | 2022-04-22 | 1 wk | MAINT | 275
HANNAHSTOWN |  | GG5 MAINT | 2022-04-25 | 2022-04-29 | 1 wk | MAINT | 275
HANNAHSTOWN |  | BYC CVT MAINT | 2022-05-02 | 2022-05-04 | 3 days | MAINT | 275
CASTLEREAGH |  | IBTX2 MAJOR and sheath test | 2022-05-09 | 2022-05-27 | 3 wks | MAINT | 275
CASTLEREAGH |  | GC55 MAINT | 2022-05-09 | 2022-05-13 | 1 wk | MAINT | 110
KILROOT | CASTLEREAGH | OHL AND TOWER PAINTING | 2022-05-09 | 2022-05-20 | 2 wks | OHL | 275
KILROOT |  | GJ90 MAINT | 2022-05-09 | 2022-05-13 | 1 wk | MAINT | 275
CASTLEREAGH |  | KILROOT CVT, GC52,GC53 AND GC56 | 2022-05-16 | 2022-05-20 | 1 wk | MAINT | 275
KILROOT |  | GJ95 MAINT | 2022-05-16 | 2022-05-20 | 1 wk | MAINT | 275
KILROOT |  | GJ70 MAINT | 2022-05-30 | 2022-06-03 | 1 wk | MAINT | 275
KILROOT |  | GJ75 MAINT | 2022-06-06 | 2022-06-10 | 1 wk | MAINT | 275
KILROOT | TANDRAGEE | OHL AND TOWER PAINTING | 2022-05-30 | 2022-06-10 | 2 wks | OHL | 275
TANDRAGEE | KILROOT | GB115 MAINT | 2022-05-30 | 2022-06-03 | 1 wk | MAINT | 275
CASTLEREAGH |  | IBTX1 MAINTENANCE | 2022-08-01 | 2022-08-12 | 2 wks | MAINT | 275
CASTLEREAGH |  | HANNAHSTOWN A CVT AND GC12 , GC13, GC16 | 2022-08-01 | 2022-08-05 | 1 wk | MAINT | 275
HANNAHSTOWN |  | CASTLEREAGH A CT AND CVT MAINT. | 2022-08-08 | 2022-08-12 | 1 wk | MAINT | 275
HANNAHSTOWN | CASTLEREAGH B | PROTECTION WORKS | 2022-08-15 | 2022-10-28 | 11 wks | PROJ | 275
HANNAHSTOWN |  | 275KV ISOLATORS 3 SETS CASTLEREAGH A GG12,GG11,GG14 | 2022-10-31 | 2023-02-10 | 15 wks | PROJ | 275
COOLKEERAGH | MAGHERAFELT | B CIRCUIT OUTAGES MULTIPLES TO SUIT STRINGING SECTIONS 1ST OUTAGE | 2022-04-04 | 2022-05-06 | 5 wks | OHL | 275
COOLKEERAGH | MAGHERAFELT | A CIRCUIT OUTAGES MULTIPLES TO SUIT STRINGING SECTIONS 1ST OUTAGE | 2022-05-09 | 2022-07-01 | 8 wks | OHL | 275
COOLKEERAGH | MAGHERAFELT | B CIRCUIT OUTAGES MULTIPLES TO SUIT STRINGING SECTIONS 2ND OUTAGE | 2022-07-04 | 2022-09-09 | 10 wks | OHL | 275
COOLKEERAGH | MAGHERAFELT | A CIRCUIT OUTAGES MULTIPLES TO SUIT STRINGING SECTIONS 2ND OUTAGE | 2022-09-12 | 2022-10-28 | 7 wks | OHL | 275
COOLKEERAGH | MAGHERAFELT | Tower painting | 2022-04-04 | 2022-10-28 | 30 wks | OHL | 275
MAGHERAFELT |  | GH36 REPLACEMENT INCLUDING NEW STANDALONE EARTH SWITCHES | 2022-04-04 | 2022-04-29 | 4 wks | PROJ | 275
MAGHERAFELT |  | GH34 MAINT | 2022-05-02 | 2022-05-06 | 5 days | MAINT | 275
COOLKEERAGH |  | GA35 MFELT A | 2022-07-04 | 2022-07-15 | 2 wks | MAINT | 275
COOLKEERAGH | MAGHERAFELT | GA36 REPLACEMENT INCLUDING NEW STANDALONE EARTH SWITCHES | 2022-07-18 | 2022-08-12 | 4 wks | PROJ | 275
COOLKEERAGH | MAGHERAFELT | GA56 REPLACEMENT INCLUDING NEW STANDALONE EARTH SWITCHES | 2022-05-09 | 2022-06-03 | 4 wks | PROJ | 275
MAGHERAFELT |  | GH46 REPLACEMENT INCLUDING NEW STANDALONE EARTH SWITCHES | 2022-06-06 | 2022-07-01 | 4 wks | PROJ | 275
COOLKEERAGH |  | GA55 MAINT MFELT B | 2022-09-12 | 2022-09-23 | 2 wks | MAINT | 275
MAGHERAFELT |  | GH44 MAINT | 2022-09-26 | 2022-09-30 | 5 days | MAINT | 275
MAGHERAFELT |  | GH43 MAINT | 2022-10-03 | 2022-10-07 | 5 days | MAINT | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 1ST WEEKEND | 2022-05-14 | 2022-05-15 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 2ND WEEKEND | 2022-05-21 | 2022-05-22 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 3RD WEEKEND | 2022-05-28 | 2022-05-29 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 4TH WEEKEND | 2022-06-04 | 2022-06-05 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 5TH WEEKEND | 2022-06-11 | 2022-06-12 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 6TH WEEKEND | 2022-06-18 | 2022-06-19 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 7TH WEEKEND | 2022-06-25 | 2022-06-26 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 8TH WEEKEND | 2022-07-02 | 2022-07-03 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 9TH WEEKEND | 2022-07-16 | 2022-07-17 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 10TH WEEKEND | 2022-08-06 | 2022-08-07 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 11TH WEEKEND | 2022-08-13 | 2022-08-14 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 12TH WEEKEND | 2022-08-20 | 2022-08-21 | 2 days | OHL | 275
COOLKEERAGH | MAGHERAFELT | A or B circuit restringing plus double circuit outages each weekend june - september 13TH WEEKEND | 2022-08-27 | 2022-08-28 | 2 days | OHL | 275
COLERAINE | RASHARKIN | POLE REPLACEMENTS WORKS | 2022-08-27 | 2022-08-28 | 2 wks | OHL | 110
COLERAINE |  | 1L8, 2L4, CX91, RASHARKIN VT. | 2022-04-04 | 2022-04-08 | 1 wk | MAINT | 110
RASHARKIN |  | MU30 MAINTENANCE | 2022-04-11 | 2022-04-15 | 1 wk | MAINT | 110
CREAGH |  | MN15 MAINT | 2022-04-18 | 2022-04-20 | 3 days | MAINT | 110
TAMNAMORE | CREAGH | POLE REPLACEMENTS WORKS | 2022-04-18 | 2022-04-22 | 1 wk | OHL | 110
COOLKEERAGH | COLERAINE | OHL Pole changes | 2022-07-01 | 2022-07-03 | 3 days | OHL | 110
COOLKEERAGH | COLERAINE | OHL Pole changes | 2022-07-04 | 2022-07-13 | 10 days | OHL | 110
COLERAINE | COOLKEERAGH | CX94 and CABLE SEALING END MAINT | 2022-07-04 | 2022-07-06 | 3 days | MAINT | 110
COOLKEERAGH | COLERAINE | OHL Pole changes | 2022-07-23 | 2022-07-30 | 8 days | OHL | 110
COOLKEERAGH | LIMAVADY | POLE REPLACEMENTS WORKS | 2022-09-22 | 2022-09-25 | 4 days | OHL | 110
COOLKEERAGH | LIMAVADY | POLE REPLACEMENTS WORKS | 2022-07-14 | 2022-07-22 | 9 days | OHL | 110
COLERAINE | LIMAVADY | CVT MAINT | 2022-07-14 | 2022-07-15 | 2 days | MAINT | 110
GARVAGH |  | TRANSFORMER CIRCUIT BREAKER WIRING MODIFICATIONS | 2022-08-08 | 2022-08-19 | 2 wks | PROJ | 110
RASHARKIN |  | MU20 MAINT | 2022-08-08 | 2022-08-12 | 1 wk | MAINT | 110
RASHARKIN |  | GCB MU10 AND CVT | 2022-08-22 | 2022-08-26 | 1 wk | MAINT | 110
RASHARKIN |  | RASHARKIN T2 & MU15 | 2022-08-29 | 2022-09-09 | 2 wks | MAINT | 110
KELLS |  | KEL IBTX '2' (PROJECTS) - REACTOR NOISE ENCLOSURE WORKS | 2022-08-29 | 2022-09-30 | 5 wks | PROJ | 275
KELLS |  | REACTOR '2' COOLERS AND OIL LEAK REPAIRS | 2022-08-29 | 2022-09-16 | 3 wks | PROJ | 275
KELLS |  | INTERBUS 2 MAJOR MAINT | 2022-08-29 | 2022-09-16 | 3 wks | MAINT | 275
KELLS |  | INTERBUS TX1 MAINTENANCE | 2022-10-03 | 2022-10-21 | 3 wks | MAINT | 275
KELLS |  | REACTOR '1' COOLERS AND OIL LEAK REPAIRS | 2022-10-03 | 2022-10-21 | 3 wks | PROJ | 275
ENNISKILLEN |  | INSTALL NEW 110/33 TRANSFORMER 1 | 2022-07-01 | 2022-08-11 | 6 wks | PROJ | 110
ENNISKILLEN |  | PST MAJOR OVERHAUL AND PAINTING | 2022-08-12 | 2022-09-22 | 6 wks | PROJ | 110
AGHYOULE |  | TX1 MAINT | 2022-09-23 | 2022-10-06 | 2 wks | MAINT | 110
ENNISKILLEN |  | AGHYOULE CVT AND CSE | 2022-09-23 | 2022-09-29 | 1 wk | MAINT | 110
ENNISKILLEN |  | INSTALL NEW 110/33 TRANSFORMER 2 | 2022-10-07 | 2022-11-17 | 6 wks | PROJ | 110
STRABANE |  | PST MAJOR OVERHAUL AND PAINTING | 2022-09-30 | 2022-11-10 | 6 wks | PROJ | 110
TANDRAGEE | DRUMNAKELLY C | POLE REPLACEMENTS WORKS | 2022-03-28 | 2022-04-01 | 1 wk | OHL | 110
TANDRAGEE | DRUMNAKELLY C | POLE REPLACEMENTS WORKS | 2022-04-04 | 2022-04-06 | 3 days | OHL | 110
DRUMNAKELLY |  | TAM A CVT | 2022-04-07 | 2022-04-08 | 2 days | MAINT | 110
TANDRAGEE | DRUMNAKELLY A | MB5 MAINT AND CVT | 2022-04-11 | 2022-04-15 | 1 wk | MAINT | 110
TANDRAGEE | DRUMNAKELLY C | CVT MAINT | 2022-05-23 | 2022-05-27 | 1 wk | MAINT | 110
DRUMNAKELLY |  | 1K0 MAINT | 2022-05-30 | 2022-05-31 | 2 days | MAINT | 110
DRUMNAKELLY |  | 8K0 MAINT | 2022-06-01 | 2022-06-02 | 2 days | MAINT | 110
DUNGANNON | TAMNAMORE 'C' | DUN - TAM 'C' | 2022-06-03 | 2022-06-03 | 1 day | MAINT | 110
TREMOGE | OMAGH B | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION | 2022-06-06 | 2022-06-17 | 2 wks | OHL | 110
TAMNAMORE | TREMOGE B | POLE REPLACEMENTS WORKS | 2022-06-20 | 2022-06-22 | 3 days | OHL | 110
DUNGANNON | OMAGH A | POLE REPLACEMENTS WORKS | 2022-06-27 | 2022-07-01 | 1 wk | OHL | 110
DUNGANNON | OMAGH A | ISOLATOR AND CVT MAINT | 2022-06-27 | 2022-07-01 | 1 wk | MAINT | 110
TREMOGE |  | MV10 MAINT | 2022-07-04 | 2022-07-08 | 1 wk | MAINT | 110
TREMOGE |  | MV40 MAINT | 2022-07-11 | 2022-07-15 | 1 wk | MAINT | 110
TREMOGE |  | MV15 AND TRANSFORMER 2 MAINT | 2022-07-18 | 2022-07-22 | 1 wk | MAINT | 110
DUNGANNON |  | 1J8,2J4,CX141 (Tx1) | 2022-07-25 | 2022-07-26 | 2 days | MAINT | 110
TAMNAMORE |  | INTERBUS 1 REACTOR INSTALLATION | 2022-08-12 | 2022-09-15 | 5 wks | PROJ | 275
TAMNAMORE |  | INTERBUS 1 MAJOR | 2022-08-12 | 2022-08-18 | 1 wk | MAINT | 275

## Sheet1
KELLS | MAGHERAFELT | repairs on tower 928 top 4 dishes lower phase cracked. | 01 December 2022 08:00 | 02 December 2022 17:00 | 2 days | OHL | 275
ANTRIM |  | TX2 MAINT | 17 January 2022 08:00 | 04 February 2022 17:00 | 3 wks | MAINT | 110
ANTRIM |  | TX1 MAINT |  |  | 3 wks | MAINT | 110
BALLYCRONANMORE | HANNAHSTOWN A | TOWER PAINTING | 18 April 2022 08:00 | 22 April 2022 17:00 | 1 wk | OHL | 275
BALLYLUMFORD | Unit 4 | GD55 SF6 REMOVAL AND DISCONNECTION |  |  | 1 wk | MAINT | 275
BALLYLUMFORD | Unit 5 | GD65 SF6 REMOVAL AND DISCONNECTION |  |  | 1 wk | MAINT | 275
BALLYLUMFORD | A4-A2 | GD60 MAINT |  |  | 1 wk | MAINT | 275
BALLYLUMFORD | Station Tx2 | MD30 MAINT |  |  | 1 wk | MAINT | 110
BALLYLUMFORD | Station Tx3 | MD45 MAINT |  |  | 1 wk | MAINT | 110
BALLYLUMFORD |  | GT1 MD35 and Sheath | 02 May 2022 08:00 | 06 May 2022 17:00 | 5 days | MAINT | 110
BALLYLUMFORD |  | IBTX1 MAJOR | 03 May 2022 08:00 | 06 June 2022 17:00 | 5 wks | MAINT | 275
BALLYLUMFORD |  | IBTX1 EARTHING TX AND COOLERS | 01 August 2022 08:00 | 02 September 2022 17:00 | 5 wks | PROJ | 275
BALLYLUMFORD | BALLYCRONANMORE | GD10 MAINT | 12 July 2022 08:00 | 18 July 2022 17:00 | 1 wk | MAINT | 275
BALLYLUMFORD | BALLYCRONANMORE | GD10 SF6 ANALYSIS | 12 July 2022 08:00 | 12 July 2022 12:00 | 0.5 days | MAINT | 275
BALLYLUMFORD |  | IBTX2 MajOR | 01 August 2022 08:00 | 02 September 2022 17:00 | 5 wks | MAINT | 275
BALLYLUMFORD |  | IBTX2 EARTHING TX AND COOLERS | 03 May 2022 08:00 | 06 June 2022 17:00 | 5 wks | PROJ | 275
BALLYLUMFORD |  | GT2 MD40 AND sheath | 05 September 2022 08:00 | 09 September 2022 17:00 | 5 days | MAINT | 110
BALLYLUMFORD | Station Tx1 | MD25 MAINT |  |  | 1 wk | MAINT | 110
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT | 25 December 2022 08:00 | 25 December 2022 17:00 | 1 day | PROJ | 275
BALLYLUMFORD |  | DISCONNECT STATION TX2 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 25 December 2022 08:00 | 29 December 2022 17:00 | 1 wk | MAINT | 110
BALLYLUMFORD |  | DISCONNECT STATION TX3 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 25 December 2022 08:00 | 29 December 2022 17:00 | 1 wk | MAINT | 110
BALLYLUMFORD |  | DISCONNECT STATION TX1 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 25 December 2022 08:00 | 29 December 2022 17:00 | 1 wk | MAINT | 110
BALLYLUMFORD | BALLYVALLAGH 'A' | earth wire replacement |  |  | 2 wks | OHL | 110
BALLYLUMFORD | BALLYVALLAGH A & 'B' | final section earth wire Ballylumford side |  |  | 2 days | OHL | 110
BALLYLUMFORD | HANNAHSTOWN 'B' | BPS - HAN +E411B (PROJECTS) - CVT CHANGE |  |  | 2 wks | PROJ | 275
BALLYLUMFORD | HANNAHSTOWN B | TOWER PAINTING |  |  | 2 wks | OHL | 275
BALLYMENA |  | BALLYMENA TX3 MAJOR | 21 March 2022 08:00 | 01 April 2022 17:00 | 2 wks | MAINT | 110
BALLYVALLAGH |  | ME45 BUSCOUPLER |  |  | 1 wk | MAINT | 110
BALLYVALLAGH | KELLS A | ME5 MAINT |  |  | 1 wk | MAINT | 110
BALLYVALLAGH | KELLS B | ME15 MAINT |  |  | 1 wk | MAINT | 110
BALLYVALLAGH |  | SECTION 1 BUSBAR |  |  | 1 wk | MAINT | 110
BALLYVALLAGH |  | SECTION 2 BUSBAR |  |  | 1 wk | MAINT | 110
BALLYVALLAGH | LARNE A | TOWER PAINTING | 01 January 2022 08:00 | 03 January 2022 17:00 | 2 days | OHL | 110
BALLYVALLAGH |  | ME25 MAINT |  |  | 1 wk | MAINT | 110
BALLYVALLAGH | LARNE B | TOWER PAINTING | 01 January 2022 08:00 | 06 January 2022 17:00 | 1 wk | OHL | 110
BANBRIDGE |  | TX2 & TX4 MAINT |  |  | 2 wks | MAINT | 110
BANBRIDGE |  | TX1 & TX3 MAINT |  |  | 2 wks | MAINT | 110
CASTLEREAGH |  | MC5 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH |  | MC110 |  |  | 1 wk | MAINT | 110
CASTLEREAGH | RATHGAEL B | MC75 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH |  | BATTERY STORAGE CONNECTION | 04 January 2022 08:00 | 07 February 2022 17:00 | 5 wks | MAINT | 110
CASTLEREAGH | RATHGAEL A | MC65 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH | NEWTOWNARDS B | MC55 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH | NEWTOWNARDS A | MC45 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH | ROSEBANK A | MC10 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH |  | SECTION 1R BUSBAR |  |  | 1 wk | MAINT | 110
CASTLEREAGH |  | SECTION 2R BUSBAR |  |  | 1 wk | MAINT | 110
CASTLEREAGH | CREGAGH A | MC90 MAINT |  |  | 1 wk | MAINT | 110
CASTLEREAGH | CREGAGH - BELFAST CENTRAL | CAS-CRG-BCM A & B START | 25 December 2022 08:00 | 16 March 2023 17:00 | 60 days | PROJ | 110
CASTLEREAGH | CREGAGH - BELFAST CENTRAL 'A' | CAS-CRG-BCM A (PROJECTS) - 3 ENDED PROTECTION | 25 December 2022 08:00 | 02 February 2023 17:00 | 6 wks | PROJ | 110
CASTLEREAGH | CREGAGH - BELFAST CENTRAL 'B' | CAS-CRG-BCM B (PROJECTS) - 3 ENDED PROTECTION | 25 December 2022 08:00 | 02 February 2023 17:00 | 6 wks | PROJ | 110
COLERAINE |  | 1L0 MAINT | 11 April 2022 08:00 | 12 April 2022 17:00 | 2 days | MAINT | 110
COLERAINE |  | 2L0 MAINT | 13 April 2022 08:00 | 14 April 2022 17:00 | 2 days | MAINT | 110
COLERAINE |  | 3L0 MAINT |  |  | 2 days | MAINT | 110
COLERAINE |  | 7L0 MAINT |  |  | 2 days | MAINT | 110
COLERAINE | LOGUESTOWN 'B' | tower painting |  |  | 1 wk | OHL | 110
COLERAINE | LOGUESTOWN A | CVT MAINT |  |  | 2 days | MAINT | 110
COLERAINE | LOGUESTOWN B | CVT MAINT AND MESH ISOLATORS |  |  | 3 days | MAINT | 110
COLERAINE |  | TX1 MAINT |  |  | 1 wk | MAINT | 110
COLERAINE |  | TX2 MAINT |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | 8H1 EH21
COOLKEERAGH | SPRINGTOWN 'A' | CPS - SPR 'A' (OHL WORK) - TOWER PAINTING |  |  | 1 wk | OHL | 110
COOLKEERAGH | SPRINGTOWN 'B' | CPS - SPR 'b' (OHL WORK) - TOWER PAINTING |  |  | 1 wk | OHL | 110
COOLKEERAGH |  | INTERBUS TRANSFORMER 1 MINOR (INSTALL BUND WALL) - BUND WALL AND BLAST WALL & ETX installation |  |  | 25 days | PROJ | 275
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2L BUSBAR (BUSBAR) - |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION A2 BUSBAR (BUSBAR) - |  |  | 1 wk | MAINT | 275
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION A1 BUSBAR (BUSBAR) - |  |  | 1 wk | MAINT | 275
COOLKEERAGH |  | 10HO AND CVT AND CSE |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | 15H0 MAINT AND CAP BANK |  |  | 1 wk | MAINT | 110
COOLKEERAGH |  | IBTX2 MINOR |  |  | 1 wk | MAINT | 275
COOLKEERAGH |  | IBTX1 MAJOR |  |  | 3 wks | MAINT | 110
COOLKEERAGH |  | LOADSHEDDING (RUNBACK SCHEME) - 3 LOADSHEDDING RELAYS |  |  | TBC | PROJ | 275
DONEGALL |  | TX 'C' 33KV CABLES INTO NEW BOARD | 01 July 2022 08:00 | 14 July 2022 17:00 | 2 wks | PROJ | 110
DONEGALL |  | TX 'B' 33KV CABLES INTO NEW BOARD | 01 July 2022 08:00 | 14 July 2022 17:00 | 2 wks | PROJ | 110
DONEGALL |  | TX C bushings | 01 April 2022 08:00 | 07 April 2022 17:00 | 1 wk | MAINT | 110
DONEGALL |  | TX 'B' REPLACEMENT WITH NEW 33BOARD (PROJECTS ) - INSTALL TX B FROM PSW | 25 December 2022 08:00 | 02 March 2023 17:00 | 10 wks | PROJ | 110
DROMORE |  | MW20 MAINT OMA 'B' |  |  | 1 wk | MAINT | 110
DRUMNAKELLY |  | DRU (TX1 TAPCHANGER PANELS) - PROJECTS |  |  | 4 wks | PROJ | 110
DRUMNAKELLY |  | DRU (TX3 TAPCHANGER PANELS) - PROJECTS |  |  | 4 wks | PROJ | 110
DRUMNAKELLY |  | TX1 MAINT |  |  | 2 wks | MAINT | 110
DRUMNAKELLY |  | TX2 MAINT |  |  | 2 wks | MAINT | 110
DRUMNAKELLY |  | 2K0 MAINT |  |  | 2 days | MAINT | 110
DRUMNAKELLY |  | 3K0 MAINT |  |  | 2 days | MAINT | 110
DUNGANNON | MESH CORNER 4 | ISOLATOR AND CVT MAINT |  |  | 1 wk | MAINT | 110
DUNGANNON |  | 3J0 MAINT |  |  | 2 days | MAINT | 110
DUNGANNON |  | 6J0 MAINT |  |  | 2 days | MAINT | 110
DUNGANNON |  | 7J0 MAINT |  |  | 2 days | MAINT | 110
EDEN |  | TRANSFORMER '1' (110KV BUSHING REPLACEMENT) - plus coolers | 03 May 2022 08:00 | 23 May 2022 17:00 | 3 wks | PROJ | 110
EDEN | BALLYLUMFORD A | CVT MAINT |  |  | 2 days | MAINT | 110
EDEN |  | TRANSFORMER '2' (110KV BUSHING REPLACEMENT) - plus coolers | 04 July 2022 08:00 | 22 July 2022 17:00 | 3 wks | PROJ | 110
ENNISKILLEN |  | ENNISKILLEN MAIN T1 MAJOR (110/33) - OIL LEAK REPAIRS |  |  | 2 wks | MAINT | 110
ENNISKILLEN |  | 2PO MAINT |  |  | 2 days | MAINT | 110
ENNISKILLEN |  | 4PO MAINT |  |  | 2 days | MAINT | 110
ENNISKILLEN |  | TX3 MINOR |  |  | 2 wks | MAINT | 110
ENNISKILLEN |  | TX2 MAINT PLUS ISOLATORS |  |  | 1 day | MAINT | 110
ENNISKILLEN |  | TX1 MAJOR |  |  | 2 wks | MAINT | 110
GLENGORMLEY |  | INSTALL NEW 110KV CABLE AND TRANSFORMER TX |  |  | 6 wks | PROJ | 110
GLENGORMLEY |  | TX B MAJOR |  |  | 3 wks | MAINT | 110
GLENGORMLEY | GLENGORMLEY 'A' | EM171 AND CSE'S (STEEL REPAIRS) - | 25 December 2022 08:00 | 25 December 2022 17:00 | 1 day | PROJ | 110
HANNAHSTOWN |  | 275KV DISCONNECTOR REPLACEMENT (PROJECTS) - 9 TO BE COMPLETE 2021? |  |  | 6 wks | PROJ | 275
HANNAHSTOWN |  | MG60 MAINT |  |  | 1 wk | MAINT | 110
HANNAHSTOWN |  | MG5 MAINT |  |  | 1 wk | MAINT | 110
HANNAHSTOWN | DONEGALL 'A' | MG10 MAINT |  |  | 5 days | MAINT | 110
HANNAHSTOWN |  | MG50 MAINT |  |  | 5 days | MAINT | 110
HANNAHSTOWN |  | IBTX3 MINOR |  |  | 1 wk | MAINT | 275
HANNAHSTOWN |  | MG45 AND CVT, CSE'S |  |  | 1 wk | MAINT | 110
HANNAHSTOWN |  | GG15 MAINT | 03 January 2022 08:00 | 07 January 2022 17:00 | 1 wk | MAINT | 275
HANNAHSTOWN |  | IBTX2 MAJOR | 03 January 2022 08:00 | 21 January 2022 17:00 | 3 wks | MAINT | 275
HANNAHSTOWN |  | REACTOR 3 INSTALLATION - | 03 October 2022 08:00 | 11 November 2022 17:00 | 6 wks | PROJ | 110
HANNAHSTOWN |  | MGXX POLE CHANGE - POLE REPLACEMENT | 25 December 2022 08:00 |  |  | MAINT | 110
HANNAHSTOWN |  | 275KV ISOLATORS 2 SETS BPS TBC | 01 January 2023 08:00 | 13 April 2023 17:00 | 15 wks | PROJ | 275
HANNAHSTOWN |  | 275KV ISOLATORS 3 SETS BPS GG4,GG21,GG22 | 01 January 2023 08:00 | 13 April 2023 17:00 | 15 wks | PROJ | 275
HANNAHSTOWN |  | IBTX1 MINOR PLUS REACTOR |  |  | 1 wk | MAINT | 275
HANNAHSTOWN |  | GG20 MAINT |  |  | 1 wk | MAINT | 275
HANNAHSTOWN |  | RESTRING CATENARIES -?????????? | 25 December 2022 08:00 | 25 December 2022 17:00 | 1 day | PROJ | 110
HANNAHSTOWN | LISBURN A | POLE REPLACEMENTS WORKS |  |  | 2 wks | OHL | 110
HANNAHSTOWN | LISBURN B | POLE REPLACEMENTS WORKS | 02 May 2022 08:00 | 13 May 2022 17:00 | 2 wks | OHL | 110
KELLS | GLENGORMLEY B | TOWER PAINTING |  |  | 1 wk | OHL | 110
KELLS | BALLYMENA 'A' | POLE REPLACEMENTS WORKS |  |  | 2 wks | OHL | 110
KELLS | BALLYMENA 'B' | POLE REPLACEMENTS WORKS |  |  | 2 wks | OHL | 110
KELLS | BALLYVALLAGH 'A' | POLE REPLACEMENTS WORKS |  |  | 2 wks | OHL | 110
KELLS | GLENGORMLEY 'A' | CABLE CONDITION ASSESSMENT FOR FUTURE WORKS | 17 January 2022 08:00 | 21 January 2022 17:00 | 1 wk | PROJ | 110
KELLS |  | GF54 maintenance and repair |  |  | 1 wk | MAINT | 275
KELLS |  | MF60 MAINT ANTRIM B |  |  | 1 wk | MAINT | 110
KELLS |  | MF50 MAINT ANTRIM 'A' |  |  | 1 wk | MAINT | 110
KELLS |  | GF45 MAINTENANCE |  |  | 1 wk | MAINT | 275
KELLS | glengormley 'A' | MF75 AND ISOLATORS sheath tests |  |  | 1 day | MAINT | 110
KELLS | glengormley 'B' | sheath tests |  |  | 1 day | MAINT | 110
KELLS | BALLYMENA 'A' | MF9 MAINTENANCE |  |  | 1 day | MAINT | 110
KELLS |  | GCB MF30 AND CVT |  |  | 1 wk | MAINT | 110
KELLS |  | SECTION 1L BUSBAR |  |  | 1 wk | MAINT | 110
KELLS |  | SECTION 2L BUSBAR |  |  | 1 wk | MAINT | 110
KELLS |  | SECTION 1R BUSBAR |  |  | 1 wk | MAINT | 110
KELLS |  | SECTION 2R BUSBAR |  |  | 1 wk | MAINT | 110
KELLS |  | NEW BATTERY STORAGE CONNECTION | 01 March 2022 08:00 | 25 April 2022 17:00 | 8 wks | PROJ | 110
KELLS |  | CIRCUIT BREAKER FAILS |  |  | 5 wks | PROJ | 275
KELLS |  | NEW CLUSTER CONNECTION ( NAME KELLS CLUSTER) | 01 January 2023 08:00 | 02 February 2023 17:00 | 5 wks | PROJ | 110
KELLS |  | MESH CORNER PROTECTION (PROJECTS) - KELLS - BUSZONE |  |  | 5 wks | PROJ | 275
KILROOT |  | KILROOT GENERATOR T1 (LINES) - PLANT MAINT. (INCL. S/E & OIL TEST) GJ23,GJ26 etc |  |  | 1 day | MAINT | 275
KILROOT |  | CIRCUIT BREAKER FAILS SCHEME ( 13 SETS ) | 28 February 2022 08:00 | 08 April 2022 17:00 | 6 wks | PROJ | 275
KILROOT |  | GJ50 MAINT |  |  | 1 wk | MAINT | 275
KILROOT |  | MAiNT on GJ84,gj83,gj86 and ct |  |  | 1 wk | MAINT | 275
KILROOT |  | NEW GENERATOR 6 BAY |  |  | 12 wks | PROJ | 275
KILROOT |  | NEW GENERATOR 7 BAY |  |  | 12 wks | PROJ | 275
KILROOT |  | KPS CT CHANGE BAY 3 CT'S gj34(PROJECTS) - CT REPLACEMENT BAY | 24 January 2022 08:00 | 11 February 2022 17:00 | 3 wks | PROJ | 275
LARNE |  | LARNE TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES AND TAPCHANGER REPAIR | 03 January 2022 08:00 | 21 January 2022 17:00 | 3 wks | PROJ | 110
LARNE |  | LARNE TX2 BUSHINGS (PROJECTS) - BUSHING CHANGES | 03 January 2022 08:00 | 21 January 2022 17:00 | 3 wks | PROJ | 110
LISBURN |  | TX1 33kv bushing replacement |  |  | 1 wk | PROJ | 110
LISBURN |  | 21L0 AND CX165, EL21 |  |  | 1 wk | MAINT | 110
LISBURN |  | HAN B CVT AND ISOLATORS 24L8,25L4,CX169 AND EL25 |  |  | 1 wk | MAINT | 110
LOGUESTOWN |  | TX1 MAINT |  |  | 2 wks | MAINT | 110
MAGHERAFELT |  | GH15 MAINT BPS Cct ( Kells Staff ) |  |  | 1 wk | MAINT | 275
MAGHERAFELT |  | GH55 MAINT |  |  | 1 wk | MAINT | 275
MAGHERAFELT |  | GH25 MAINT |  |  | 1 wk | MAINT | 275
MAGHERAFELT |  | CIRCUIT BREAKER FAILS SCHEME ( 7 SETS ) |  |  | 1 min | PROJ | 275
MAGHERAFELT | TAMNAMORE 'A' | TMN- MAG 'A' (OHL WORK) - SINGLE TENSION TOWER 228 | 01 November 2022 08:00 | 07 November 2022 17:00 | 1 wk | OHL | 275
MAGHERAFELT |  | (CONTROL PANEL REFURBISHMENT) - | 25 December 2022 08:00 | 25 December 2022 08:03 | 3 mins | PROJ | 275
OMAGH |  | 3M8,4M4 CX53 MAINT (Tx 2) |  |  | 2 days | MAINT | 110
OMAGH |  | 4M0 MAINT |  |  | 2 days | MAINT | 110
OMAGH | DROMORE 'A' & 'B' | OMA - DRO 'A' & 'B' (OHL WORK) - DUAL OUTAGE EARTH WIRE RESTRINGING |  |  | 2 days | OHL | 110
OMAGH | DROMORE 'B' | OMA - DRO B (OHL WORK) - RESTRINGING |  |  | 4 wks | OHL | 110
OMAGH | DROMORE 'A' | OMA - DRO A (OHL WORK) - RESTRINGING |  |  | 4 wks | OHL | 110
OMAGH | TREMOGE | ISOLATOR AND CVT MAINT |  |  | 2 days | MAINT | 110
OMAGH | DROMORE 'A' | sheath tests |  |  | 1 day | MAINT | 110
OMAGH |  | 5M0 MAINT |  |  | 2 days | MAINT | 110
OMAGH | GORT | OMA-GRT AND VT MAINT PLUS CSE MAINT |  |  | 4 days | MAINT | 110
RASHARKIN |  | SECTION 1 BUSBAR |  |  | 1 wk | MAINT | 110
RASHARKIN |  | SECTION 2 BUSBAR |  |  | 1 wk | MAINT | 110
RASHARKIN |  | MU5 MAINT |  |  | 1 wk | MAINT | 110
RATHGAEL |  | TX2 MAINT |  |  | 2 wks | MAINT | 110
ROSEBANK |  | TX1 MAINT |  |  | 3 wks | MAINT | 110
STRABANE |  | 4S0 MAINT |  |  | 3 days | MAINT | 110
STRABANE |  | isolator refurbishment strabane project |  |  | 1 wk | PROJ | 110
STRABANE |  | 5S0 MAJOR |  |  | 1 wk | MAINT | 110
STRABANE |  | TX2 MAINT |  |  | 2 wks | MAINT | 110
TAMNAMORE |  | GP5 MAINT |  |  | 1 wk | MAINT | 110
TAMNAMORE |  | BUSBAR ISOLATORS GP4,GP14,GP24 |  |  | 1 wk | MAINT | 275
TAMNAMORE |  | BUSBAR ISOLATORS GP3,GP13,GP23 |  |  | 1 wk | MAINT | 275
TANDRAGEE |  | GB5 MAINT BUSCOUPLER |  |  | 1 wk | MAINT | 275
TANDRAGEE | BANBRIDGE B | POLE REPLACEMENTS WORKS |  |  | 1 wk | OHL | 110
TANDRAGEE | BANBRIDGE B | MB85 MAINT |  |  | 1 wk | MAINT | 110
TANDRAGEE | BANBRIDGE A | POLE REPLACEMENTS WORKS |  |  | 1 wk | OHL | 110
TANDRAGEE | BANBRIDGE A | MB75 MAINT |  |  | 1 wk | MAINT | 110
TANDRAGEE | WARINGSTOWN A | TOWER PAINTING |  |  | 1 wk | OHL | 110
TANDRAGEE | WARINGSTOWN B | TOWER PAINTING |  |  | 2 days | OHL | 110
TANDRAGEE | WARINGSTOWN A | MB35 MAINT |  |  | 1 wk | MAINT | 110
TANDRAGEE | WARINGSTOWN B | MB45 MAINT |  |  | 1 wk | MAINT | 110
WARINGSTOWN |  | TX2 MAINT |  |  | 2 wks | MAINT | 110
WARINGSTOWN |  | TX1 MAINT |  |  | 2 wks | MAINT | 110
TANDRAGEE |  | TANDRAGEE IBTX2 MINOR |  |  | 1 wk | MAINT | 275
TANDRAGEE | NEWRY 'B' | MB20 MAINT |  |  | 1 day | MAINT | 110
TANDRAGEE |  | SECTION '2R' ISOLATOR |  |  | 1 day | MAINT | 110
TANDRAGEE |  | SECTION '2L' ISOLATORS - MAINTENANCE, MB53 |  |  | 1 day | MAINT | 110
TANDRAGEE |  | TANDRAGEE MAIN SECTION A1 BUSBAR (BUSBAR) |  |  | 3 days | MAINT | 275
TANDRAGEE |  | TANDRAGEE MAIN SECTION A2 BUSBAR (BUSBAR) |  |  | 2 days | MAINT | 275
TANDRAGEE |  | SECTION '1L' ISOLATORS - MAINTENANCE |  |  | 8 days | MAINT | 110
TANDRAGEE |  | SECTION '1R' ISOLATORS - MAINTENANCE |  |  | 8 days | MAINT | 110
TANDRAGEE |  | SECTION '2R' ISOLATORS - MAINTENANCE ( |  |  | 8 days | MAINT | 110
TANDRAGEE |  | SECTION '2L' ISOLATORS - MAINTENANCE |  |  | 8 days | MAINT | 110
TANDRAGEE | LOUTH '1' | GB35 MAINT |  |  | 5 days | MAINT | 275
TANDRAGEE | LOUTH '2' | GB55 MAINT |  |  | 5 days | MAINT | 275
TANDRAGEE | LOUTH A | TOWER PAINTING |  |  | 3 wks | OHL | 275
TANDRAGEE | LOUTH B | TOWER PAINTING |  |  | 3 wks | OHL | 275
TANDRAGEE |  | TANDRAGEE MAIN INTERBUS 1 Minor |  |  | 1 wk | MAINT | 275
TANDRAGEE | LISBURN A | POLE REPLACEMENTS WORKS |  |  | 2 wks | OHL | 110
TANDRAGEE | LISBURN B | 3 3 POLE STRUCTURES |  |  | 2 wks | OHL | 110
TANDRAGEE | NEWRY A | TOWER PAINTING |  |  | 1 wk | OHL | 110
TANDRAGEE |  | TANDRAGEE IBTX3 MINOR |  |  | 1 wk | MAINT | 275
TANDRAGEE |  | (PROJECTS) - C/B POLE CHANGES | 25 December 2022 08:00 | 29 December 2022 17:00 | 1 wk | MAINT | 110
TANDRAGEE |  | RESTRING CATENARIES - | 25 December 2022 08:00 | 19 January 2023 17:00 | 4 wks | PROJ | 275
TREMOGE |  | MV5 MAINT |  |  | 1 wk | MAINT | 110
TREMOGE |  | SECTION 1 BUSBAR |  |  | 1 wk | MAINT | 110
TREMOGE |  | SECTION 2 BUSBAR |  |  | 1 wk | MAINT | 110
COOLKEERAGH | C30 | C30 STPMO | 02 July 2022 08:00 | 02 July 2022 17:00 | 1 day | GEN
BALLYLUMFORD | BGT1 | BGT1 Major overhaul | 01 May 2022 08:00 | 27 June 2022 17:00 | 42 days | GEN
COOLKEERAGH | GT8 | CGT8 Annual inspection | 25 April 2022 08:00 | 29 April 2022 17:00 | 5 days | GEN
KILROOT | K2 | K2 Major overhaul | 29 April 2022 08:00 | 21 July 2022 17:00 | 60 days | GEN
BALLYLUMFORD | BGT2 | BGT2 Borescope inspection | 05 September 2022 08:00 | 13 September 2022 17:00 | 7 days | GEN
KILROOT | KGT3 | KGT3 Borescope inspection | 19 September 2022 08:00 | 17 October 2022 17:00 | 21 days | GEN
KILROOT | KGT4 | KGT4 Borescope inspection | 19 September 2022 08:00 | 17 October 2022 17:00 | 21 days | GEN
COOLKEERAGH | C30 | C30 STPMO | 27 March 2022 08:00 | 27 March 2022 17:00 | 1 day | GEN
MOYLE |  | Moyle double pole outage | 02 April 2022 08:00 | 03 April 2022 17:00 | 2 days | GEN
KILROOT | K1 | K1 Major overhaul | 25 July 2022 08:00 | 14 October 2022 17:00 | 60 days | GEN
BALLYLUMFORD | B31 | B31 partial outage for ST20 Generator Inspection | 24 September 2022 08:00 | 12 October 2022 17:00 | 14 days | GEN
BALLYLUMFORD | B32 | B32 partial outage for ST20 Generator Inspection | 24 September 2022 08:00 | 12 October 2022 17:00 | 14 days | GEN
KILROOT | KGT1 | KGT1 Stack inspection | 24 September 2022 08:00 | 25 September 2022 17:00 | 2 days | GEN
KILROOT | KGT2 | KGT2 Stack inspection | 24 September 2022 08:00 | 25 September 2022 17:00 | 2 days | GEN
COOLKEERAGH | C30 | C30 Annual inspection | 24 September 2022 08:00 | 06 October 2022 17:00 | 10 days | GEN
COOLKEERAGH | C30 | C30 Offline Wash | 19 November 2022 08:00 | 20 November 2022 17:00 | 2 days | GEN
MOYLE |  | Moyle single pole outage | 16 June 2022 08:00 | 28 July 2022 17:00 | 31 days | GEN
MOYLE |  | Moyle double pole outage | 07 June 2022 08:00 | 15 June 2022 17:00 | 7 days | GEN
KILROOT | KGT2 | KGT2 Major overhaul | 01 March 2022 08:00 | 27 April 2022 17:00 | 42 days | GEN
MOYLE |  | Moyle single pole outage | 04 April 2022 08:00 | 06 June 2022 17:00 | 46 days | GEN
KELLS |  | KEL INTERBUS TRANSFORMER 1 & MAJOR(PROJECTS) - PROTECTION CHANGE (WITH REACTOR) | 26 December 2022 08:00 | 03 March 2023 17:00 | 10 wks | PROJ | 275
KELLS |  | KEL REACTOR '1' (PROJECTS) - PROTECTION CHANGE AND NOISE ENCLOSURES | 26 December 2022 08:00 | 03 March 2023 17:00 | 10 wks | PROJ | 275
KELLS |  | KEL INTERBUS TRANSFORMER 2 & MAJOR (PROJECTS) - PROTECTION CHANGE | 26 December 2022 08:00 | 03 March 2023 17:00 | 10 wks | PROJ | 275
KELLS |  | KEL REACTOR '2' (PROJECTS) - PROTECTION CHANGE AND COOLERS REPLACEMENT | 26 December 2022 08:00 | 03 March 2023 17:00 | 10 wks | PROJ | 275
KELLS |  | KEL IBTX '2' (PROJECTS) - MESH CORNER PROTECTION WORKS | 26 December 2022 08:00 | 03 March 2023 17:00 | 10 wks | PROJ | 275