## Information
Transmission Outage Planning Process
A full programme of work for the year ahead has been developed. This includes all project work NIE Networks wish to complete in 2019 as part of their Capital Investment requirements.
Maintenance
NIE Networks are responsible for developing maintenance policy and prioritising maintenance. Outages required to facilitate maintenance are planned and approved in advance with SONI. Where maintenance is required on assets directly connecting generation to the network, these are communicated to the customer with as much notice as possible. Maintenance is planned and scheduled quarterly between NIE Networks and SONI and managed to minimise the impact on the network.
'Project Work' Sheet
This outage plan incorporates project work NIE Networks aim to complete in 2019. The dates proposed are indicative and are dependent on a number of factors, including availability of resources, forced outages in year etc. This outage plan does not contain maintenance works. This outage plan is subject to change.

## Project Work
Task Name | Duration | Start | Finish
Kells - Creagh Lines Work | 2 wks | 2019-05-01 | 2019-05-10
CAS buszone BC1 | 1 wk | 2019-05-13 | 2019-05-17
EDEN TX1 TAPCHANGER REPAIR | 2 wks | 2019-05-13 | 2019-05-24
EDENMAIN TX1 ( Hawker Sid ) Tapchanger Refurbishment | 3 wks | 2019-05-13 | 2019-05-31
Coolkeeragh - Coleraine Lines Work | 2 wks | 2019-06-01 | 2019-06-13
Kells - Ballyvallagh 'A' Lines Work | 1 wk | 2019-06-01 | 2019-06-06
DONEGALL TX C Painting | 2 wks | 2019-06-01 | 2019-06-13
KELLS IBTX.1 MAJOR MAINTENANCE (WITH REACTOR) | 5 wks | 2019-06-03 | 2019-07-05
CAS BUSZONE, KNO A | 4 days | 2019-06-03 | 2019-06-06
CAS BUSZONE, BNH A, CRE A | 1 wk | 2019-06-07 | 2019-06-13
Kells - Ballyvallagh 'B' Lines Work | 1 wk | 2019-06-07 | 2019-06-13
CAS BUSZONE, BNH B CRE B | 1 wk | 2019-06-10 | 2019-06-14
BYC-HAN A Lines Work | 2 wks | 2019-06-12 | 2019-06-25
Limavady - Coleraine Lines Work | 2 wks | 2019-06-14 | 2019-06-27
Dromore - Enniskillen 'A' Lines Work | 1 wk | 2019-06-25 | 2019-06-30
Castlereagh - Ballynahinch 'A' Lines Work | 2 wks | 2019-06-28 | 2019-07-10
KEL-MAG PROTECTION WORKS | 10 wks | 2019-07-01 | 2019-09-06
Omagh - Dromore 'B' Lines Work | 3 days | 2019-07-02 | 2019-07-04
BPS-HAN Lines Work | 2 wks | 2019-08-01 | 2019-08-13
NEWRY TX1 Painting | 2 wks | 2019-08-01 | 2019-08-13
BMA TX.3 REPLACEMENT | 10 wks | 2019-08-01 | 2019-10-08
KPS-TAN Lines Work | 3 wks | 2019-08-05 | 2019-08-22
Castlereagh - Rathgael 'A' Lines Work | 2 wks | 2019-08-05 | 2019-08-15
KELLS Buszone Work | 4 wks | 2019-09-02 | 2019-09-27
DUNGANNON TX1 ( FERRANTI FC6 ) Tapchanger Refurbishment | 3 wks | 2019-09-02 | 2019-09-20
Tx Cooler Replacement Dungannon Tx.1 | 2 wks | 2019-09-02 | 2019-09-13
Tx Cooler Replacement Lisburn TX 1 | 2 wks | 2019-09-02 | 2019-09-19
TANDRAGEE - DRUMNAKELLY A | 5 wks | 2019-09-02 | 2019-10-04
BPS-MAG PROTECTION WORKS | 10 wks | 2019-09-09 | 2019-11-15
HAN MG43, MG38, IBTX.3 | 2 wks | 2019-09-09 | 2019-09-27
Castlereagh - Rathgael 'B' Lines Work | 2 wks | 2019-10-14 | 2019-10-25
NEWRY TX 2 Painting | 2 wks | 2019-10-14 | 2019-10-25