## Sheet1
Task Name | kV | Duration | Start | Finish
275kV WORKS | 275 | 314 days? | Mon 13/01/20 | Thu 25/03/21
BPS | 275 | 214 days | Mon 09/03/20 | Thu 31/12/20
BPS IBTX 1 MAJOR AND C/B'S (ETX CHANGE) - MINOR | 275 | 7 days | Mon 20/04/20 | Tue 28/04/20
BPS IBTX2 MAJOR AND C/B'S (ETX CHANGE) - MINOR | 275 | 7 days | Wed 29/04/20 | Thu 07/05/20
BPS GD49 ( KELLS CCT) GD59 ( B/C ) (KELLS & BUS COUPLER ISOLATOR ) - BUS SECTION ISOLATORS. - SAFETY LINE TO BE FITTED | 275 | 1 wk | Mon 18/05/20 | Fri 22/05/20
CONTROL PANEL REFURBISHMENT - PROJECT | 275 | 1 day | Thu 31/12/20 | Thu 31/12/20
BPS - MAG (OHL WORK) - TROLLEY WORK AND TOWER PAINTING | 275 | 1 wk | Mon 09/03/20 | Fri 13/03/20
BPS - HAN B (OHL WORK) - OHL REFURB | 275 | 2 wks | Mon 10/08/20 | Fri 21/08/20
BPS-KELLS (PROJECTS) - CVT CHANGE | 275 | 2 wks | Mon 18/05/20 | Fri 29/05/20
BPS-MAG CVT CHANGE AND OHL (PROJECTS) - OHL REFURB | 275 | 9 wks | Mon 09/03/20 | Fri 08/05/20
BPS-MAG PROTECTION UPGRADE (PROJECTS) - PROTECTION CHANGE | 275 | 10 wks | Mon 09/03/20 | Fri 15/05/20
BPS - MAG (PROJECTS) - CVT CHANGE | 275 | 2 wks | Mon 09/03/20 | Fri 20/03/20
BPS - KEL (OHL WORK) - OHL WORK | 275 | 1 wk | Mon 18/05/20 | Fri 22/05/20
KELLS WALLBUSHING - REPLACE WALL BUSHING | 275 | 2 wks | Mon 18/05/20 | Fri 29/05/20
BPS - HAN B (PROJECTS) - CVT CHANGE | 275 | 2 wks | Mon 10/08/20 | Fri 21/08/20
BYC | 275 | 50 days | Mon 01/06/20 | Fri 07/08/20
BYC - HAN PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 275 | 10 wks | Mon 01/06/20 | Fri 07/08/20
CAS | 275 | 188 days | Mon 27/04/20 | Wed 13/01/21
CASTLEREAGH - HANNAHSTOWN A (LINES) - OHL WORK | 275 | 1 wk | Mon 27/04/20 | Fri 01/05/20
(PROJECTS) - CONCRETE SUPPORT REPAIR WORKS | 275 | 2 wks | Thu 31/12/20 | Wed 13/01/21
CASTLEREAGH MAIN INTERBUS T1 (275/110) (PROJECTS IN 2020 ) - REPALCEMENT (NO REACTOR) | 275 | 12 wks | Mon 04/05/20 | Fri 24/07/20
CAS - TAN PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 275 | 10 wks | Mon 05/10/20 | Fri 11/12/20
CAS REACTOR 2 REPLACEMENT (PROJECTS) - REACTOR 2 | 275 | 8 wks | Mon 05/10/20 | Fri 27/11/20
CPS | 275 | 176 days? | Mon 04/05/20 | Mon 04/01/21
CPS EARTHING UPGRADE OUTAGES (PROJECTS) - PROJECT WORK | 275 | 3 days | Mon 25/05/20 | Wed 27/05/20
INTERBUS TRANSFORMER 1 (INSTALL BUND WALL) - BUND WALL AND BLAST WALL | 275 |  | Thu 31/12/20
CPS - MAG 'B' (OHL WORK) - OHL AND COUPLING CAPACITOR | 275 |  | Thu 31/12/20
CPS - MAG 'A' (OHL WORK) - OHL WORK | 275 |  | Thu 31/12/20
CPS-MAG COUPLING CAPACITOR - COUPLING CAPACITOR JOB | 275 | 3 days | Thu 31/12/20 | Mon 04/01/21
CPS IBTX2 (PROJECTS) - PROTECTION CHANGE | 275 | 12 wks | Mon 04/05/20 | Fri 24/07/20
CPS - MAG A PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 275 | 10 wks | Mon 27/07/20 | Fri 02/10/20
LOADSHEDDING (RUNBACK SCHEME) - 3 LOADSHEDDING RELAYS | 275 |  | Thu 31/12/20
HAN | 275 | 264 days | Mon 13/01/20 | Thu 14/01/21
HAN - BYC CVT FAULT (REPLACE CLAMP WITH NEW CLAMPS) - | 275 | 1 day | Mon 01/06/20 | Mon 01/06/20
HANNAHSTOWN MAIN INTERBUS T3 (275/110) (BUSHING REPAIRS ) - | 275 | 3 days | Mon 13/01/20 | Wed 15/01/20
HAN - BYC (OHL WORK) - TROLLEY WORK AND TOWER PAINTING | 275 | 1 wk | Mon 01/06/20 | Fri 05/06/20
275KV DISCONNECTOR REPLACEMENT (PROJECTS) - 6 TO BE COMPLETE 2020 | 275 | 2 wks | Fri 01/01/21 | Thu 14/01/21
KEL | 275 | 224 days | Mon 18/05/20 | Thu 25/03/21
KELLS - BPS CVT (KELLS & BUS COUPLER ISOLATOR ) - CVT MAINTENANCE & TESTING PLUS EG118 | 275 | 3 days | Mon 18/05/20 | Wed 20/05/20
CIRCUIT BREAKER FAILS (PROJECTS) - PROTECTION CHANGE | 275 | 1 day | Thu 31/12/20 | Thu 31/12/20
MESH CORNER PROTECTION (PROJECTS) - KELLS - BUSZONE | 275 | 5 wks | Fri 01/01/21 | Thu 04/02/21
IBTX1 (PROJECTS) - MESH CORNER PROTECTION WORKS | 275 | 12 wks | Fri 01/01/21 | Thu 25/03/21
KEL INTERBUS TRANSFORMER 1 (PROJECTS) - PROTECTION CHANGE (WITH REACTOR) | 275 | 6 wks | Mon 03/08/20 | Fri 11/09/20
KEL INTERBUS TRANSFORMER 2 (PROJECTS) - PROTECTION CHANGE | 275 | 6 wks | Mon 14/09/20 | Fri 23/10/20
KEL REACTOR '1' (PROJECTS) - PROTECTION CHANGE | 275 | 6 wks | Mon 03/08/20 | Fri 11/09/20
KEL REACTOR '2' (PROJECTS) - PROTECTION CHANGE | 275 | 6 wks | Mon 14/09/20 | Fri 23/10/20
KPS | 275 | 273 days | Mon 13/01/20 | Wed 27/01/21
CIRCUIT BREAKER FAILS (PROJECTS) - PROTECTION CHANGE | 275 | 1 day | Thu 31/12/20 | Thu 31/12/20
BUS-ZONE (BEFORE C/B FAIL) - BUS-ZONE | 275 | 4 wks | Thu 31/12/20 | Wed 27/01/21
KPS - CAS (LINES) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Mon 05/10/20 | Fri 16/10/20
KPS - TAN (LINES) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Mon 13/01/20 | Fri 24/01/20
KILROOT GENERATOR T1 (LINES) - PLANT MAINT. (INCL. S/E & OIL TEST) | 275 | 1 day | Thu 31/12/20 | Thu 31/12/20
KILROOT GENERATOR T1 (LINES) - PLANT MAINT. | 275 | 5 days | Thu 31/12/20 | Wed 06/01/21
KILROOT GENERATOR T2 (LINES) - PLANT MAINT. | 275 | 5 days | Thu 31/12/20 | Wed 06/01/21
KILROOT CCGT (LINES) - PLANT MAINT. | 275 | 5 days | Thu 31/12/20 | Wed 06/01/21
KILROOT SPARE BAY (LINES) - PLANT MAINT. | 275 | 5 days | Thu 31/12/20 | Wed 06/01/21
(PROJECTS) - CT CHANGES | 275 |  | Thu 31/12/20
CT CHANGE BAY TBC 3 CT'S (PROJECTS) - CT REPLACEMENT | 275 | 3 wks | Mon 13/01/20 | Fri 31/01/20
CT CHANGE BAY TBC 3 CT'S (PROJECTS) - CT REPLACEMENT | 275 | 3 wks | Mon 03/02/20 | Fri 21/02/20
KPS CT CHANGE BAY TBC 3 CT'S (PROJECTS) - CT REPLACEMENT | 275 | 2 wks | Mon 24/02/20 | Fri 06/03/20
KPS CT CHANGE BAY 3 CT'S (PROJECTS) - CT REPLACEMENT BAY | 275 | 2 wks | Mon 09/03/20 | Fri 20/03/20
MAG | 275 | 229 days | Mon 17/02/20 | Thu 31/12/20
CIRCUIT BREAKER FAILS (PROJECTS) - PROTECTION CHANGE | 275 | 1 day | Thu 31/12/20 | Thu 31/12/20
GH5 BUSCOUPLER PROTECTION (PROJECTS) - PROTECTION CHANGE | 275 | 5 wks | Sun 01/11/20 | Thu 03/12/20
(CONTROL PANEL REFURBISHMENT) - | 275 | 3 mins | Thu 31/12/20 | Thu 31/12/20
TMN- MAG 'A' (OHL WORK) - SINGLE TENSION TOWER | 275 | 2.5 days | Mon 17/02/20 | Wed 19/02/20
TMN - MAG 'B' (OHL WORK) - SINGLE TENSION TOWER | 275 | 2.5 days | Wed 19/02/20 | Fri 21/02/20
TAN | 275 | 253 days | Mon 09/03/20 | Wed 24/02/21
TANDRAGEE MAIN INTERBUS 1 (PROJECTS) - CAPACITOR BANK REPAIRS AND OVERHAUL? (WITH REACTOR) | 275 | 8 wks | Thu 31/12/20 | Wed 24/02/21
TAN - KPS (OHL WORK) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Thu 31/12/20 | Wed 13/01/21
RESTRING CATENARIES - | 275 | 2 days | Thu 31/12/20 | Fri 01/01/21
TANDRAGEE REACTOR '1' (REPLACEMENT) - | 275 | 10 wks | Mon 07/09/20 | Fri 13/11/20
TAN - CAS (OHL WORK) - SUSPENSION/TENSION INSULATORS, SPACERS AND TOWER PAINTING | 275 | 2 wks | Mon 24/08/20 | Fri 04/09/20
TANDRAGEE MAIN SECTION A1 BUSBAR (BUSBAR) - GB93 MAINT. | 275 | 3 days | Mon 09/03/20 | Wed 11/03/20
TANDRAGEE MAIN SECTION A2 BUSBAR (BUSBAR) - GB94 MAINT | 275 | 2 days | Thu 12/03/20 | Fri 13/03/20
TANDRAGEE ISOLATOR (TAMNAMORE A ) - GB16 MAINT | 275 | 2 days | Wed 18/03/20 | Thu 19/03/20
BUS ZONE (PROJECTS) - PROTECTION CHANGE | 275 | 26 days | Thu 01/10/20 | Thu 05/11/20
TANDRAGEE MAIN INTERBUS 1 (WTI MEASUREMENTS) - MEASURE WTI FOR JAMIE MC HENDRY (WITH REACTOR) | 275 | 1 day | Fri 01/01/21 | Fri 01/01/21
110kV WORKS | 110 | 408 days? | Wed 01/01/20 | Fri 23/07/21
BPS | 110 | 86 days | Thu 11/06/20 | Thu 08/10/20
DISCONNECT STATION TX1 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 110 | 3 days | Thu 01/10/20 | Mon 05/10/20
DISCONNECT STATION TX3 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 110 | 3 days | Tue 06/10/20 | Thu 08/10/20
DISCONNECT STATION TX2 (STATION DISCONNECTION) - REMOVE BUSBARS AT STATION TX | 110 | 3 days | Thu 11/06/20 | Mon 15/06/20
BALLYLUMFORD GTTX1 110KV CABLE (BALLYLUMFORD GTTX1 110KV CABLE) - SHEATH TEST | 110 | 1 day | Thu 01/10/20 | Thu 01/10/20
BALLYLUMFORD GTTX2 110KV CABLE (BALLYLUMFORD GTTX2 110KV CABLE) - SHEATH TEST | 110 | 2 days | Thu 11/06/20 | Fri 12/06/20
BNM | 110 | 5 days | Wed 01/04/20 | Tue 07/04/20
DONEGALL - BELFAST NORTH MAIN CABLE WORKS - CSE REPLACEMENTS | 110 | 1 wk | Wed 01/04/20 | Tue 07/04/20
CAR | 110 | 6 days | Mon 04/05/20 | Mon 11/05/20
CAR 3C4 (ISOL ESW ONLY) - MAINTENANCE | 110 | 3 days | Mon 04/05/20 | Wed 06/05/20
CAR 4C4,6C2,2C4 (ISOL ESW ONLY) - MAINTENANCE | 110 | 3 days | Thu 07/05/20 | Mon 11/05/20
CAS | 110 | 61 days | Fri 01/05/20 | Fri 24/07/20
CAS - BNH A (OHL WORK) - OHL WORK | 110 | 2 wks | Fri 01/05/20 | Thu 14/05/20
CAS - RAT B (OHL WORK) - OHL WORK | 110 | 3 days | Mon 08/06/20 | Wed 10/06/20
CASTLEREAGH MCXX POLE REPLACEMENT - POLE REPLACEMENT | 110 | 5 days | Fri 01/05/20 | Thu 07/05/20
CAS-KNO A (PROJECTS) - CABLE DIVERSION WORK | 110 | 4 wks | Mon 01/06/20 | Fri 26/06/20
CAS-KNO B (PROJECTS) - CABLE DIVERSION WORK | 110 | 4 wks | Mon 29/06/20 | Fri 24/07/20
CAR MC15 (CAR B) - MINOR AND ASSOCIATED PLANT | 110 | 5 days | Mon 11/05/20 | Fri 15/05/20
CAR MC25 (CAR A) - MINOR AND ASSOCIATED PLANT | 110 | 5 days | Mon 04/05/20 | Fri 08/05/20
COL | 110 | 27 days | Mon 01/06/20 | Tue 07/07/20
COL- LOG B (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Wed 01/07/20 | Tue 07/07/20
COL- LOG A (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 08/06/20 | Fri 12/06/20
(OHL WORK) - COL-CPS | 110 | 2 wks | Mon 01/06/20 | Fri 12/06/20
(OHL WORK) - COL-LIM | 110 | 2 wks | Mon 15/06/20 | Fri 26/06/20
CPS 110 | 110 | 189 days? | Mon 13/04/20 | Thu 31/12/20
COOLKEERAGH MAIN SECTION BUSBAR (BUSBAR) - | 110 |  | Thu 31/12/20
CPS - SPR 'A' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 13/04/20 | Fri 17/04/20
CPS - SPR 'B' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | Mon 20/04/20 | Fri 24/04/20
CPS - STR 'B' (OHL WORK) - TOWER PAINTING | 110 | 2 wks | Mon 29/06/20 | Fri 10/07/20
CPS CIRCUIT BREAKER LEAKING (1,10,12 AND 13HO GAS GUAGES) - DEFECT REPAIRS | 110 | 1 wk | Fri 01/05/20 | Thu 07/05/20
COOLKEERAGH MAIN SECTION 1 (BUSBAR) - 1H1,3H1,7H1,9H1,16H1 | 110 | 5 days | Fri 08/05/20 | Thu 14/05/20
COOLKEERAGH MAIN SECTION 2L (BUSBAR) - 6H2 REPAIR FAULTY MOTOR 110V | 110 | 2 days | Fri 15/05/20 | Mon 18/05/20
CRG | 110 | 10 days | Fri 01/05/20 | Thu 14/05/20
CRG (MN15 CREAGH MAIN CB) - MINOR (INCL. E/SW(2) | 110 | 3 days | Fri 01/05/20 | Tue 05/05/20
CRE TX B DEFECTS GASSING ON TRANSFORMER (INVESTIGATION WORKS) - WORK FOR LEONARD TAGGART | 110 | 1 wk | Fri 01/05/20 | Thu 07/05/20
TX A DEFECTS OIL LEAKS AND GASSING ON TRANSFORMER (INVESTIGATION WORKS) - WORK FOR LEONARD TAGGART | 110 | 1 wk | Fri 08/05/20 | Thu 14/05/20
DON | 110 | 85 days | Fri 01/05/20 | Thu 27/08/20
DONEGALL TX B ISOLATORS (ISOL ESW ONLY) - MAINTENANCE | 110 | 2 days | Fri 01/05/20 | Mon 04/05/20
DON CABLE OIL FLUSHING WORKS (A' CIRCUIT OIL LEAK REPAIRS) - OIL WORKS | 110 | 7 days | Tue 05/05/20 | Wed 13/05/20
DONEGALL TX A (MAJOR 1ST MAINTENANCE) - MAINTENANCE | 110 | 2 wks | Tue 05/05/20 | Mon 18/05/20
DONEGALL TX C (PROJECTS) - TRANSFORMER PAINTING | 110 | 2 wks | Tue 19/05/20 | Mon 01/06/20
FIN - DON 'A' (OHL WORK) - RESTRINGING | 110 | 2 wks | Sat 01/08/20 | Thu 13/08/20
FIN - DON 'B' (OHL WORK) - RESTRINGING | 110 | 2 wks | Fri 14/08/20 | Thu 27/08/20
CABLE OIL FLUSHING WORKS (B' CIRCUIT OIL LEAK REPAIRS) - OIL WORKS & SHEATH TESTS, ISOLATOR MAINT REQUIRES TX OUT AT DONEGALL | 110 | 7 days | Fri 14/08/20 | Mon 24/08/20
DRU | 110 | 10 days | Mon 04/05/20 | Fri 15/05/20
DRU (TX1 & TX3 TAPCHANGER PANELS) - PROJECTS | 110 | 2 wks | Mon 04/05/20 | Fri 15/05/20
DRQ | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
TX (MAINT) - INSTALL NEW BUSHING SPACES TO NEUTRAL | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
DUN | 110 | 188 days | Mon 04/05/20 | Wed 20/01/21
DUNGANNON MAIN T1 ( 110/33KV) (COOLER UPGRADES) - | 110 | 3 wks | Mon 15/06/20 | Fri 03/07/20
DUNGANNON MAIN T2 ( 110/33KV) (COOLER UPGRADES) - | 110 | 3 wks | Mon 06/07/20 | Fri 24/07/20
DUN - TAM C (OHL WORKS) - | 110 | 1 day | Mon 01/06/20 | Mon 01/06/20
DUN - OMA A (OHL WORKS) - | 110 | 1 day | Mon 04/05/20 | Mon 04/05/20
DUNGANNON MAIN T1 ( 110/33KV) (COOLER REPAIRS, TC CHECKS) - | 110 | 3 wks | Thu 31/12/20 | Wed 20/01/21
DUNGANNON MAIN T2 ( 110/33KV) (COOLER REPAIRS, TC CHECKS) - | 110 | 3 wks | Thu 31/12/20 | Wed 20/01/21
EDE | 110 | 20 days | Mon 20/07/20 | Fri 14/08/20
TRANSFORMER '1' (110KV BUSHING REPLACEMENT) - | 110 | 1 wk | Mon 20/07/20 | Fri 24/07/20
TRANSFORMER '2' (110KV BUSHING REPLACEMENT) - | 110 | 1 wk | Mon 27/07/20 | Fri 31/07/20
CVT AND ISOLS BPS A (LINE PLANT) - ISOALTOR MAINTENANCE | 110 | 1 wk | Mon 03/08/20 | Fri 07/08/20
CVT AND ISOLS BPS B (LINE PLANT) - ISOALTOR MAINTENANCE | 110 | 1 wk | Mon 10/08/20 | Fri 14/08/20
ENN | 110 | 168 days | Mon 01/06/20 | Wed 20/01/21
ENN PST ISOLATORS (ISOLATOR MAINTENANCE) - MAINTENANCE | 110 | 1 wk | Mon 01/06/20 | Fri 05/06/20
ENNISKILLEN MAIN T1 (110/33) (TX1 COOLER REPAIRS) - OIL LEAK REPAIRS | 110 | 2 wks | Mon 08/06/20 | Fri 19/06/20
ENN (3PO & 7P0 ENNISKILLEN MAIN CB) - SF6 LEAKS | 110 | 2 days | Mon 01/06/20 | Tue 02/06/20
ENN - DRO B (OHL WORK) - OHL WORK | 110 | 1 wk | Mon 27/07/20 | Fri 31/07/20
ENN - AGY (OHL WORK) - | 110 | 3 days | Mon 03/08/20 | Wed 05/08/20
PST - ISOLATORS ONLY | 110 | 3 wks | Thu 31/12/20 | Wed 20/01/21
GLE | 110 | 1 day | Mon 03/02/20 | Mon 03/02/20
EM171 AND CSE'S (STEEL REPAIRS) - | 110 | 1 day | Mon 03/02/20 | Mon 03/02/20
GRT | 110 | 2 days | Wed 06/05/20 | Thu 07/05/20
GRT TX (MAINT) - INSTALL NEW BUSHING SPACES TO NEUTRAL | 110 | 2 days | Wed 06/05/20 | Thu 07/05/20
HAN | 110 | 233 days? | Mon 06/04/20 | Wed 24/02/21
MG15 ARCING HORNS (MG15 HANNAHSTOWN MAIN CB (FINAGHY A)) - ARCING HORNS | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
HANNAHSTOWN MAIN SECTION 2R BUSBAR (MULTIPLE ISOLATORS TO CHANGE) - | 110 | 2 days | Thu 31/12/20 | Fri 01/01/21
HANNAHSTOWN MAIN SECTION 1R BUSBAR (MULTIPLE ISOLATORS TO CHANGE) - | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
HAN - DON A CABLE FAULT (OIL WORKS) - REPAIRS | 110 |  | Thu 31/12/20
MGXX POLE CHANGE - POLE REPLACEMENT | 110 |  | Thu 31/12/20
ROAD POLE DIVERSIONS (HAN - LIS 'A') - POLE CHANGES | 110 | 2 days | Mon 06/04/20 | Tue 07/04/20
HOUSING DEVELOPMENT POLES (HAN - LIS 'B') - POLE CHANGES | 110 | 5 days | Wed 08/04/20 | Tue 14/04/20
REACTOR 2 REPLACEMENT (CTS AND CB) - | 110 | 8 wks | Thu 31/12/20 | Wed 24/02/21
HANNAHSTOWN MAIN SECTION 2L/2R BUSBAR (PROJECTS) - | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
HANNAHSTOWN MAIN SECTION 2L/2R BUSBAR (PROJECTS) - | 110 | 21 days | Thu 31/12/20 | Thu 28/01/21
HANNAHSTOWN MAIN SECTION 1L/1R BUSBAR (PROJECTS) - MG43,MG33 REPLACEMENT | 110 | 4 wks | Thu 31/12/20 | Wed 27/01/21
HANNAHSTOWN MAIN SECTION 2L/2R BUSBAR (PROJECTS) - MG48,MG33 REPLACEMENT | 110 | 5 wks | Thu 31/12/20 | Wed 03/02/21
HAN- DON - BNM B (PROJECTS) - CABLE OIL FILTERING /PUMPING | 110 | 6 wks | Thu 31/12/20 | Wed 10/02/21
HANNAHSTOWN - DONEGALL 'A' 110KV CABLE (HANNAHSTOWN - DONEGALL 'A' 110KV CABLE) - SHEATH TEST | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
KEL | 110 | 223 days? | Mon 06/04/20 | Wed 10/02/21
KEL - CRE (OHL WORK) - OHL WORK SPAN 69 -150 POLES ONLY | 110 | 10 days | Mon 06/04/20 | Fri 17/04/20
KEL - ANT A (OHL WORK) - LINE RAISING & UNDERCROSSING | 110 | 1 day | Mon 04/05/20 | Mon 04/05/20
KEL - CRE (OHL WORK) - | 110 | 1 day | Mon 06/04/20 | Mon 06/04/20
KEL - BVG A (OHL WORK) - OHL WORK | 110 |  | Thu 31/12/20
INTERLOCKING OUTAGES (PROJECTS) - | 110 | 6 wks | Thu 31/12/20 | Wed 10/02/21
KNO | 110 | 20 days | Mon 08/06/20 | Fri 03/07/20
TX A MAJOR 1ST MAINT (MAJOR) - MAINTENANCE | 110 | 2 wks | Mon 08/06/20 | Fri 19/06/20
TX B MAJOR 1ST MAINT (MAJOR) - MAINTENANCE | 110 | 2 wks | Mon 22/06/20 | Fri 03/07/20
LIM | 110 | 10 days | Mon 15/06/20 | Fri 26/06/20
LIM - CPS (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 15/06/20 | Fri 26/06/20
LIS | 110 | 30 days | Mon 01/06/20 | Fri 10/07/20
LISBURN MAIN T1 (LISBURN MAIN T1) - 33KV BUSHINGS & COOLERS | 110 | 3 wks | Mon 01/06/20 | Fri 19/06/20
LISBURN MAIN T2 ( 110/33KV) (LISBURN MAIN T2) - 33KV BUSHINGS & COOLERS | 110 | 3 wks | Mon 22/06/20 | Fri 10/07/20
NEW | 110 | 50 days | Mon 30/03/20 | Fri 05/06/20
TX1 PAINTING (PROJECTS) - PROJECT WORK | 110 | 5 wks | Mon 30/03/20 | Fri 01/05/20
NEW TX2 PAINTING (PROJECTS) - PROJECT WORK | 110 | 5 wks | Mon 04/05/20 | Fri 05/06/20
OMA | 110 | 191 days | Wed 06/05/20 | Wed 27/01/21
(OHL WORK) - OMA-GRT | 110 | 2 days | Wed 06/05/20 | Thu 07/05/20
OMA - STR A (OHL WORK) - POLE CHANGES AND TOWER WORK | 110 | 1 wk | Mon 17/08/20 | Fri 21/08/20
OMA - DRO B (OHL WORK) - RESTRINGING | 110 | 4 wks | Thu 31/12/20 | Wed 27/01/21
OMA - DRO A (OHL WORK) - RESTRINGING | 110 | 4 wks | Thu 31/12/20 | Wed 27/01/21
OMA - DRO 'A' & 'B' (OHL WORK) - DUAL OUTAGE EARTH WIRE RESTRINGING | 110 | 2 wks | Thu 31/12/20 | Wed 13/01/21
TRE - OMA B ( TREMOGE ) (LINES) - | 110 | 2 wks | Mon 29/06/20 | Fri 10/07/20
STR | 110 | 163 days | Mon 08/06/20 | Wed 20/01/21
STR- OMA B (OHL WORK) - OHL WORK | 110 | 2 wks | Mon 08/06/20 | Fri 19/06/20
PST REFURBISHMENT - ISOLATORS ONLY | 110 | 3 wks | Thu 31/12/20 | Wed 20/01/21
TMN | 110 | 248 days | Sat 01/02/20 | Wed 13/01/21
TMN - TMG FREQUECNY ISSUES CUST (TOWER 180 CLIP ON WIRES) - OHL MAINTENANCE | 110 | 1 day | Sat 01/02/20 | Sat 01/02/20
OHL WORK (POLE REPLACEMENT) - POLES | 110 | 2 wks | Thu 31/12/20 | Wed 13/01/21
TMN - DRU 'B' (POLE REPLACEMENT AND TOWER PAINTING) - POLE REPLACEMENT AND TOWER PAINTING | 110 | 1 wk | Mon 30/03/20 | Fri 03/04/20
TAN | 110 | 199 days | Mon 30/03/20 | Thu 31/12/20
TAN - LIS A (OHL WORK) - OHL WORK | 110 | 1 wk | Mon 27/04/20 | Fri 01/05/20
TAN - LIS B (OHL WORK) - OHL WORK | 110 | 1 wk | Mon 04/05/20 | Fri 08/05/20
SECTION '1R' ISOLATORS (MB39,MB91 AND EM23) - MAINTENANCE | 110 | 3 days | Mon 30/03/20 | Wed 01/04/20
SECTION '1R' ISOLATORS (MB83) - MAINTENANCE | 110 | 1 day | Thu 31/12/20 | Thu 31/12/20
TAN - NRY A (OHL WORK) - | 110 | 2 wks | Mon 30/03/20 | Fri 10/04/20
LINES | 110 | 1 day | Tue 05/05/20 | Tue 05/05/20
KEL - ANT 'B' (OHL WORK) - RAISE CONDUCTORS AT TOWER 404 ( UNDERCROSSING ) | 110 | 1 day | Tue 05/05/20 | Tue 05/05/20
TAN | 110 | 96 days | Mon 04/05/20 | Mon 14/09/20
TAN - NRY B (TOWER PAINTING ) - TOWER PAINTING | 110 | 2 wks | Mon 04/05/20 | Fri 15/05/20
TAN - DRU A (OHL WORK) - | 110 | 2 wks | Tue 01/09/20 | Mon 14/09/20
KEL | 110 | 7 days | Mon 31/08/20 | Tue 08/09/20
KEL BVG B (OHL WORK) - OHL WORK | 110 | 7 days | Mon 31/08/20 | Tue 08/09/20
TAN | 110 | 266 days | Wed 01/01/20 | Wed 06/01/21
TAN - NRY A (PROJECTS) - TELEPROTECTION CHANGE AND DISTANCE PROTECTION | 110 | 5 wks | Mon 30/03/20 | Fri 01/05/20
TAN - NRY B (PROJECTS) - TELEPROTECTION CHANGE AND DISTANCE PROTECTION | 110 | 5 wks | Mon 04/05/20 | Fri 05/06/20
TAN - WAR B (OHL WORK) - | 110 | 5 wks | Wed 01/01/20 | Tue 04/02/20
TAN - BAN A (LINES) - POLE REPLACEMENT | 110 | 1 wk | Mon 03/08/20 | Fri 07/08/20
MB25 (DRU C) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Mon 03/08/20 | Thu 06/08/20
MB35 (WAR A) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Fri 07/08/20 | Wed 12/08/20
MB45 (WAR B) - MINOR (INCL. CT & VT + E/SW, DISC (3) & VT) | 110 | 4 days | Thu 13/08/20 | Tue 18/08/20
(PROJECTS) - POLE CHANGES | 110 | 1 wk | Thu 31/12/20 | Wed 06/01/21
SECTION '1R' ISOLATORS - MAINTENANCE | 110 | 8 days | Wed 01/07/20 | Fri 10/07/20
SECTION '2R' ISOLATORS - MAINTENANCE | 110 | 8 days | Mon 13/07/20 | Wed 22/07/20
SECTION '1L' ISOLATORS - MAINTENANCE | 110 | 8 days | Thu 23/07/20 | Mon 03/08/20
SECTION '2L' ISOLATORS - MAINTENANCE | 110 | 8 days | Tue 04/08/20 | Thu 13/08/20
TMG | 110 | 41 days | Sat 01/08/20 | Mon 28/09/20
TX2 (STAND OFF BUSHINGS) - ALSO REPAIR ISOLATORS??? | 110 | 1 wk | Sat 01/08/20 | Thu 06/08/20
TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION | 110 | 20 days | Tue 01/09/20 | Mon 28/09/20
TRE - OMA (LINES) - POLE CHANGES | 110 | 2 wks | Tue 01/09/20 | Mon 14/09/20
CAS | 110 | 0.01 days | Thu 31/12/20 | Thu 31/12/20
BUSZONE (PROJECTS) - PROTECTION CHANGE | 110 | 3 mins | Thu 31/12/20 | Thu 31/12/20
RSK | 110 | 20 days | Mon 29/06/20 | Fri 24/07/20
RKN - KEL (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 29/06/20 | Fri 10/07/20
RKN - COL (LINES) - POLE REPLACEMENT | 110 | 2 wks | Mon 13/07/20 | Fri 24/07/20
TMN | 110 | 1 day | Mon 27/04/20 | Mon 27/04/20
CONNECT NEW BATTERY STORAGE FACILITIES (DRUMKEE CONNECTION) - PROJECT WORK | 110 | 1 day | Mon 27/04/20 | Mon 27/04/20
TAN | 110 | 0.01 days | Mon 27/04/20 | Mon 27/04/20
CONNECT NEW BATTERY STORAGE FACILITIES (MULLAVILLY CONNECTION) - | 110 | 3 mins | Mon 27/04/20 | Mon 27/04/20
BMA | 110 | 50 days | Mon 04/05/20 | Fri 10/07/20
BALLYMENA TX4 CHANGE (TRANSFORMER CHANGE) - | 110 | 10 wks | Mon 04/05/20 | Fri 10/07/20
CAS | 110 | 50 days | Mon 04/05/20 | Fri 10/07/20
CAS - RAT A (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 04/05/20 | Fri 05/06/20
CAS - RAT B (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 08/06/20 | Fri 10/07/20
COL | 110 | 20 days | Mon 01/06/20 | Fri 26/06/20
COLERAINE T1 (ETX CHANGE) - PROJECT WORK | 110 | 1 wk | Mon 01/06/20 | Fri 05/06/20
COLERAINE T1 (TRANSFORMER '1') - EARTHJNG TRANSFORMER INSTALLATION | 110 | 2 wks | Mon 01/06/20 | Fri 12/06/20
COLERAINE T2 (ETX CHANGE) - PROJECT WORK | 110 | 1 wk | Mon 15/06/20 | Fri 19/06/20
COLERAINE T2 (TRANSFORMER '2') - EARTHJNG TRANSFORMER INSTALLATION | 110 | 2 wks | Mon 15/06/20 | Fri 26/06/20
LMR | 110 | 50 days | Wed 01/07/20 | Tue 08/09/20
TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES/TCHANGE CONTROLS AND PROTECTION PANELS | 110 | 5 wks | Wed 01/07/20 | Tue 04/08/20
TX2 BUSHINGS (PROJECTS) - BUSHING CHANGES/TCHANGE CONTROLS AND PROTECTION PANELS | 110 | 5 wks | Wed 05/08/20 | Tue 08/09/20
CAS-BNH PROTECTION WORK | 110 | 50 days | Mon 20/07/20 | Fri 25/09/20
CAS - BNH A (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 20/07/20 | Fri 21/08/20
CAS - BNH B (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | Mon 24/08/20 | Fri 25/09/20
CAS-CRG-BCM | 110 | 60 days | Mon 03/05/21 | Fri 23/07/21
CAS-CRG-BCM A (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | Mon 03/05/21 | Fri 11/06/21
CAS-CRG-BCM B (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | Mon 14/06/21 | Fri 23/07/21
DON | 110 | 50 days | Fri 01/01/21 | Thu 11/03/21
TX 'B' REPALCEMENT WITH NEW 33BOARD (PROJECTS ) - INSTALL NEW TX B FROM PSW | 110 | 10 wks | Fri 01/01/21 | Thu 11/03/21
HAN | 110 | 1 day | Fri 01/01/21 | Fri 01/01/21
RESTRING CATENARIES - | 110 | 1 day | Fri 01/01/21 | Fri 01/01/21
LAR | 110 | 20 days | Mon 01/06/20 | Fri 26/06/20
LARNE TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES AND TAPCHANGER REPAIR | 110 | 2 wks | Mon 01/06/20 | Fri 12/06/20
LARNE TX2 BUSHINGS (PROJECTS) - BUSHING CHANGES | 110 | 2 wks | Mon 15/06/20 | Fri 26/06/20
NAR | 110 | 2 days | Wed 01/04/20 | Thu 02/04/20
FIT SWAN DIVERTIERS ON CAS-NAR B (BIRD DIVERTER AT BILLY NEIL PLAYING FIELD T242-244) - OHL WORK | 110 | 1 day | Wed 01/04/20 | Wed 01/04/20
FIT SWAN DIVERTIERS ON CAS-NAR A (BIRD DIVERTER AT BILLY NEIL PLAYING FIELD T242-244) - OHL WORK | 110 | 1 day | Thu 02/04/20 | Thu 02/04/20
RSK | 110 | 16 days | Mon 03/08/20 | Mon 24/08/20
(AGIVEY TIE IN) - PROJECTS | 110 | 1 day | Mon 03/08/20 | Mon 03/08/20
RKN - BKY (AGIVEY TIE IN) - OHL PROJECTS | 110 | 3 wks | Tue 04/08/20 | Mon 24/08/20
HAN-DON-BNM | 110 | 30 days | Fri 01/01/21 | Thu 11/02/21
HAN - DON - BNM A (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | Fri 01/01/21 | Thu 11/02/21
HAN - DON - BNM B (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | Fri 01/01/21 | Thu 11/02/21