## Sheet1
SUB 1 | SUB 2 | Task Name | TYPE | kV | Duration | Start | Finish
HANNAHSTOWN |  | IBTX2 MINOR AND MG55 MAINT | MAINT | 275 | 3 wks | Wed 03/01/24 | Tue 23/01/24
TANDRAGEE | BANBRIDGE B | defect repairs pole 87 | OHL | 110 | 3.6 wks | Wed 03/01/24 | Fri 26/01/24
Kilroot | NIKGT4 |  | GEN |  | 1 day | Wed 03/01/24 | Thu 04/01/24
Kilroot | NIKGT3 |  | GEN |  | 1.06 days? | Thu 04/01/24 | Thu 04/01/24
COOLKEERAGH | MAGHERAFELT | SPS SCHEME COMMSSIONING | PROJ | 275 | 6 wks | Thu 04/01/24 | Wed 14/02/24
MAGHERAFELT |  | CIRCUIT BREAKER FAILS SCHEME ( 7 SETS ) | PROJ | 275 | 1 min | Thu 04/01/24 | Thu 04/01/24
MAGHERAFELT |  | RUNBACK SCHEME TESTING AND COMMISSIONING | PROJ | 275 | 6 wks | Thu 04/01/24 | Wed 14/02/24
Kilroot | NIKGT4 |  | GEN |  | 0.44 days | Thu 04/01/24 | Thu 04/01/24
Ballylumford | NIB10 |  | GEN |  | 3.5 days | Fri 05/01/24 | Wed 10/01/24
Lisahally | NILPS |  | GEN |  | 5.44 days | Sun 07/01/24 | Fri 12/01/24
COOLKEERAGH |  | LOADSHEDDING (RUNBACK SCHEME) - 3 LOADSHEDDING RELAYS | PROJ | 275 | TBC | Mon 08/01/24
KELLS |  | MF5 MAINT BUCSOUPLER | MAINT | 110 | 1 wk | Mon 08/01/24 | Fri 12/01/24
TAMNAMORE |  | REACTOR 1 commissiong and agile WORKS (IBTx outage one week at end) | PROJ | 275 | 8 wks | Mon 08/01/24 | Fri 01/03/24
GLENGORMLEY |  | TRANSFORMER TX B 2nd stage replacement | PROJ | 110 | 6 wks | Mon 08/01/24 | Fri 16/02/24
KELLS |  | MF95 MAINT BUS COUPLER | MAINT | 110 | 1 wk | Wed 10/01/24 | Tue 16/01/24
TANDRAGEE | NEWRY A | TOWER PAINTING 1 ARM OVER HOUSE, ARCING HORN DEFECT REPAIRS | OHL | 110 | 3 days | Wed 10/01/24 | Fri 12/01/24
Kilroot | NIKGT3 |  | GEN |  | 8.38 days | Wed 10/01/24 | Fri 19/01/24
DROMORE |  | MW5 MAINT BUS-COUPLER | MAINT | 110 | 1 wk | Mon 15/01/24 | Fri 19/01/24
COOLKEERAGH |  | GA5 MAINT | MAINT | 275 | 5 days | Mon 15/01/24 | Fri 19/01/24
TAMNAMORE | CREAGH | MP40 BAY PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 110 | 3 wks | Mon 15/01/24 | Fri 02/02/24
TAMNAMORE |  | MP40 MAINT CREAGH | MAINT | 110 | 1 wk | Mon 15/01/24 | Fri 19/01/24
TAMNAMORE | CREAGH | POLE REPLACEMENTS WORKS | OHL | 110 | 1 wk | Thu 18/01/24 | Wed 24/01/24
CREAGH |  | MN5 MAINT | MAINT | 110 | 2 days | Thu 18/01/24 | Fri 19/01/24
CASTLEREAGH |  | GC10 MAINT | MAINT | 275 | 5 days | Mon 22/01/24 | Fri 26/01/24
COLERAINE |  | 6L0 MAINT | MAINT | 110 | 2 days | Mon 22/01/24 | Tue 23/01/24
BALLYLUMFORD |  | SECTION A3 ISOLATOR GD18 & Earth Switch EG69 | MAINT | 275 | 2 days | Mon 22/01/24 | Tue 23/01/24
OMAGH |  | 7M0 MAINT | MAINT | 110 | 2 days | Tue 23/01/24 | Wed 24/01/24
LISAGHMORE |  | TX2 33 KV CIRCUIT BREAKER DISCHARGE REPAIRS | MAINT | 110 | 3 days | Wed 24/01/24 | Fri 26/01/24
BALLYLUMFORD |  | SECTION A3 ISOLATOR GD36 | MAINT | 275 | 2 days | Wed 24/01/24 | Thu 25/01/24
OMAGH |  | 8M0 MAINT | MAINT | 110 | 2 days | Thu 25/01/24 | Fri 26/01/24
KILROOT |  | NEW GENERATOR 7 BAY connect to section A2 | PROJ | 275 | 2 days | Thu 25/01/24 | Fri 26/01/24
KILROOT |  | NEW GENERATOR 7 BAY connect to section A1 & scaffolding for final connection | PROJ | 275 | 5 days | Fri 26/01/24 | Thu 01/02/24
TANDRAGEE |  | TANDRAGEE IBTX1 MINOR INC GB45 & MB40 | MAINT | 275 | 2 wks | Fri 26/01/24 | Thu 08/02/24
CASTLEREAGH |  | GC25 MAINT | MAINT | 275 | 5 days | Mon 29/01/24 | Fri 02/02/24
TAMNAMORE |  | MP35 MAINT BUSCOUPLER | MAINT | 110 | 1 wk | Mon 29/01/24 | Fri 02/02/24
TANDRAGEE |  | TANDRAGEE IBTX2 MINOR INC GB75 & MB60 | MAINT | 275 | 2 wks | Mon 29/01/24 | Fri 09/02/24
COLERAINE |  | 8L0 MAINT | MAINT | 110 | 2 days | Mon 29/01/24 | Tue 30/01/24
BALLYLUMFORD |  | SECTION A1 ISOLATOR GD19 & Earth Switch EG70 | MAINT | 275 | 2 days | Mon 29/01/24 | Tue 30/01/24
COOLKEERAGH | COLERAINE | OHL Pole changes AND TOWER PAINTING | OHL | 110 | 2 days | Wed 31/01/24 | Thu 01/02/24
BALLYLUMFORD |  | SECTION A1 ISOLATOR GD38 & Earth Switch EG78 | MAINT | 275 | 2 days | Wed 31/01/24 | Thu 01/02/24
KELLS | Glengormley 'B' | cable sheath tests | MAINT | 110 | 2 days | Fri 02/02/24 | Sun 04/02/24
KELLS | Glengormley 'A' | cable sheath tests | MAINT | 110 | 2 days | Fri 02/02/24 | Sun 04/02/24
KILROOT |  | NEW GENERATOR 7 BAY connect CSE's to CVT & scaffolding removal . Final connection | PROJ | 275 | 5 days | Fri 02/02/24 | Thu 08/02/24
CASTLEREAGH |  | GC5 MAINT | MAINT | 275 | 5 days | Mon 05/02/24 | Fri 09/02/24
DRUMQUIN |  | MX5 MAINT BUSCOUPLER | MAINT | 110 | 5 days | Mon 05/02/24 | Fri 09/02/24
CREAGH |  | MN25 MAINT | MAINT | 110 | 3 days | Mon 05/02/24 | Wed 07/02/24
TANDRAGEE | LISBURN A | POLE REPLACEMENTS WORKS | OHL | 110 | 3 days | Mon 05/02/24 | Wed 07/02/24
BALLYLUMFORD | Magherafelt | GD70 maintenance | MAINT | 275 | 5 days | Mon 05/02/24 | Fri 09/02/24
BALLYLUMFORD | MAGHERAFELT | GD70 PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 1 wk | Mon 05/02/24 | Fri 09/02/24
LIMAVADY |  | 52V0 MAINT | MAINT | 110 | 1 wk | Mon 05/02/24 | Fri 09/02/24
KELLS | CREAGH | D/C TOWERS T39 & T40 | OHL | 110 | 1 day | Mon 05/02/24 | Mon 05/02/24
GORT |  | BUSCOUPLER COMMISSIONING WORKS /WIRING MODIFICATIONS | PROJ | 110 | 3 days | Tue 06/02/24 | Thu 08/02/24
KELLS | RASHARKIN | D/C TOWERS T39 & T40 | OHL | 110 | 3 days | Wed 07/02/24 | Fri 09/02/24
KELLS |  | MF31 maintenance ( bus section isol. assoc with Rasharkin cct ) | OHL | 110 | 2 days | Wed 07/02/24 | Thu 08/02/24
LIMAVADY |  | 51V0 MAINT | MAINT | 110 | 1 wk | Mon 12/02/24 | Fri 16/02/24
CASTLEREAGH |  | GC45 MAINT | MAINT | 275 | 5 days | Mon 12/02/24 | Fri 16/02/24
CASTLEREAGH |  | IBTX4 MINOR | MAINT | 275 | 1 wk | Mon 12/02/24 | Fri 16/02/24
KELLS |  | 110KV GROUP ALARMS T602M | PROJ | 110 | 3 days | Mon 12/02/24 | Wed 14/02/24
HANNAHSTOWN |  | reactor 3 TR3 point of wave breaker testing D shaw | PROJ | 275 | 3 days | Thu 15/02/24 | Mon 19/02/24
HANNAHSTOWN |  | IBTX4 110KV NEW BAY CONSTRUCTION | PROJ | 110 | TBC | Mon 19/02/24 | Fri 05/07/24
CASTLEREAGH |  | MC20 MAINT ( ROSEBANK B) | MAINT | 110 | 5 days | Mon 19/02/24 | Fri 23/02/24
KELLS |  | KEL INTERBUS TRANSFORMER 1 MINOR MAINT INCLUDING TAPCHANGER UPGRADE ( RX COOLER UPGRADES) | MAINT | 275 | 10 wks | Mon 19/02/24 | Fri 26/04/24
KELLS | BPS | MESH CORNER PROTECTION (PROJECTS) - IBTX 1 PROTECTION CHANGE , REACTOR PROTECTION REQUIRES . ( IBTX1 , BPS CIRCUIT GF55 & GF115) |  | 275 | 10 wks | Mon 19/02/24 | Fri 26/04/24
KELLS |  | Kells ibtx1 minor and 275kv isolator refurbs AND MF45 MAINT | MAINT | 275 | 2 wks | Mon 19/02/24 | Fri 01/03/24
KELLS |  | GF115 MAINT | MAINT | 275 | 1 wk | Mon 19/02/24 | Fri 23/02/24
KELLS |  | GF55 MAINT | MAINT | 275 | 1 wk | Mon 19/02/24 | Fri 23/02/24
LIMAVADY |  | 53V0 MAINT | MAINT | 110 | 1 wk | Mon 19/02/24 | Fri 23/02/24
TAMNAMORE | TANDAGREE 'B' | HOTSPOT WORKS ON THE L2 PHASE CVT CONNECTION 22DEGREES | MAINT | 275 | 1 day | Tue 20/02/24 | Tue 20/02/24
CASTLEREAGH |  | GC50 MAINT | MAINT | 275 | 5 days | Mon 26/02/24 | Fri 01/03/24
BALLYLUMFORD | KELLS | TOWER PAINTING & OHL WORKS | OHL | 275 | 2 wks | Mon 26/02/24 | Fri 08/03/24
DONEGALL |  | 1D0 MAINT | MAINT | 110 | 3 days | Mon 26/02/24 | Wed 28/02/24
DONEGALL |  | TX C MINOR NO SFRA | MAINT | 110 | 1 wk | Mon 26/02/24 | Fri 01/03/24
HANNAHSTOWN |  | MG10 MAINT DONEGALL 'A' CIRCUIT | MAINT | 110 | 1 wk | Mon 26/02/24 | Fri 01/03/24
TAMNAMORE |  | INTERBUS 1 MINOR | MAINT | 275 | 1 wk | Mon 26/02/24 | Fri 01/03/24
LIMAVADY |  | 54V0 MAINT | MAINT | 110 | 1 wk | Mon 26/02/24 | Fri 01/03/24
KNOCK |  | TX A MINOR, INC TAPCHANGER FLUSH | MAINT | 110 | 3 wks | Mon 04/03/24 | Fri 22/03/24
BELFAST NORTH MAIN |  | TX A MINOR MAINT | MAINT | 110 | 1 wk | Mon 04/03/24 | Fri 08/03/24
LIMAVADY |  | TX 1 MAJOR NO SFRA | MAINT | 110 | 2 wks | Mon 04/03/24 | Fri 15/03/24
BALLYLUMFORD |  | CONTROL PANEL WIRING | PROJ | 275 | 2 days | Mon 04/03/24 | Tue 05/03/24
BALLYLUMFORD |  | CONTROL PANEL REFURBISHMENT - PROJECT INCLUDING GROUP ALARMS | PROJ | 275 | 4 mons | Mon 04/03/24 | Fri 21/06/24
COLERAINE | LIMAVADY | POLE REPLACEMENTS WORKS | OHL | 110 | 1 wk | Mon 04/03/24 | Fri 08/03/24
GORT |  | TX 1 INSTALLATION | PROJ | 110 | 10 wks | Mon 04/03/24 | Fri 10/05/24
MAGHERAFELT |  | (CONTROL PANEL REFURBISHMENT) - | PROJ | 275 | 3 mins | Mon 04/03/24 | Mon 04/03/24
BELFAST NORTH MAIN |  | TX B MINOR MAINT | MAINT | 110 | 1 wk | Mon 11/03/24 | Fri 15/03/24
COLERAINE | LOGUESTOWN 'A' | tower painting | OHL | 110 | 1 wk | Mon 11/03/24 | Fri 15/03/24
DONEGALL |  | 2D0 MAINT | MAINT | 110 | 3 days | Mon 11/03/24 | Wed 13/03/24
DONEGALL |  | TX B MAJOR MAINT | MAINT | 110 | 3 wks | Mon 11/03/24 | Fri 29/03/24
HANNAHSTOWN |  | MG50 MAINT DONEGALL 'B' CIRCUIT | MAINT | 110 | 1 wk | Mon 11/03/24 | Fri 15/03/24
TAMNAMORE |  | GP5 MAINT MAGHERAFELT 'B' | MAINT | 275 | 1 wk | Mon 11/03/24 | Fri 15/03/24
COLERAINE | COOLKEERAGH | POLE REPLACEMENT WORKS | OHL | 110 | 1 wk | Mon 11/03/24 | Fri 15/03/24
COOLKEERAGH | COLERAINE | OHL Pole changes AND TOWER PAINTING | OHL | 110 | 1 wk | Mon 11/03/24 | Fri 15/03/24
KNOCK |  | TX B MINOR, INC TAPCHANGER FLUSH | MAINT | 110 | 3 wks | Tue 12/03/24 | Mon 01/04/24
BALLYLUMFORD |  | GIS cable works GT1 (only), Includes CT replacements on the both circuits | PROJ | 110 | 7 wks | Mon 18/03/24 | Fri 03/05/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 1 day | Mon 18/03/24 | Mon 18/03/24
BALLYMENA |  | TX4 MAJOR 1ST MAINTENANCE AND COOLER OIL LEAK REPAIRS | MAINT | 110 | 2 wks | Tue 19/03/24 | Mon 01/04/24
BALLYNAHINCH |  | TX1 MAJOR MAINT | MAINT | 110 | 10 days | Tue 19/03/24 | Mon 01/04/24
CASTLEREAGH |  | MC85 MAINT ( BNH A) | MAINT | 110 | 5 days | Tue 19/03/24 | Mon 25/03/24
KELLS | BALLYMENA 'B' | POLE REPLACEMENTS WORKS | OHL | 110 | 1 wk | Tue 19/03/24 | Mon 25/03/24
LIMAVADY |  | TX 2 MAJOR INC SFRA | MAINT | 110 | 2 wks | Tue 19/03/24 | Mon 01/04/24
COOLKEERAGH | LIMAVADY | tower painting AND POLE REPLACEMENTS | OHL | 110 | 2 wks | Tue 19/03/24 | Mon 01/04/24
Ballylumford | NIB31 |  | GEN |  | 2 days | Fri 22/03/24 | Fri 22/03/24
COOLKEERAGH |  | 14H0 MAINT LISAGHMORE A | MAINT | 110 | 1 wk | Mon 25/03/24 | Fri 29/03/24
LISAGHMORE |  | TX1 MAJOR INC SFRA | MAINT | 110 | 10 days | Mon 25/03/24 | Fri 05/04/24
CLOCKCHANGE |  | CLOCKCHANGE | TIME | SPARE | 1 day | Sun 31/03/24 | Sun 31/03/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 2 days | Mon 01/04/24 | Tue 02/04/24
Ballylumford | NIB32 |  | GEN |  | 4 days | Tue 02/04/24 | Thu 04/04/24
Kilroot | NIKGT3 |  | GEN |  | 4 days | Tue 02/04/24 | Thu 04/04/24
BALLYNAHINCH |  | TX2 MAJOR MAINT | MAINT | 110 | 7 days | Wed 03/04/24 | Thu 11/04/24
CASTLEREAGH |  | MC95 MAINT ( BNH B) | MAINT | 110 | 5 days | Wed 03/04/24 | Tue 09/04/24
TANDRAGEE | BANBRIDGE A | POLE REPLACEMENTS WORKS | OHL | 110 | 1 wk | Wed 03/04/24 | Tue 09/04/24
BALLYCRONANMORE | HANNAHSTOWN A | TOWER PAINTING | OHL | 275 | 1.2 wks | Wed 03/04/24 | Wed 10/04/24
Kilroot | NIKGT4 |  | GEN |  | 2 days | Fri 05/04/24 | Fri 05/04/24
Coolkeeragh | NIC30 |  | GEN |  | 2 days | Sat 06/04/24 | Sat 06/04/24
CASTLEREAGH |  | IBTX2 MINOR | MAINT | 275 | 1 wk | Mon 08/04/24 | Fri 12/04/24
TANDRAGEE | BANBRIDGE B | POLE REPLACEMENTS WORKS | OHL | 110 | 1 day | Mon 08/04/24 | Mon 08/04/24
COOLKEERAGH | killymalaght | tower painting AND POLE REPLACEMENTS 272 & 277 | OHL | 110 | 1 wk | Mon 08/04/24 | Fri 12/04/24
COOLKEERAGH | killymalaght | 8H0 BAY PQ MONITOR AND WIRING MODIFCATIONS | PROJ | 110 | 3 wks | Mon 08/04/24 | Fri 26/04/24
ENNISKILLEN |  | PST MAJOR OVERHAUL reschedule | MAINT | 110 | 3 wks | Mon 08/04/24 | Fri 26/04/24
KILLYMALAGHT | SLIEVEKIRK | MR10 MAINT | MAINT | 110 | 1 wk | Mon 08/04/24 | Fri 12/04/24
KILLYMALAGHT |  | MR6, MR7 AND MR9 | MAINT | 110 | 1 wk | Mon 08/04/24 | Fri 12/04/24
COOLKEERAGH |  | IBTX1 MINOR | MAINT | 275 | 1 wk | Mon 08/04/24 | Fri 12/04/24
SLIEVEKIRK |  | Protection testing | MAINT | 110 | 1 day | Mon 08/04/24 | Mon 08/04/24
SLIEVEKIRK |  | MR99 MAINT AND ESW | MAINT | 110 | 1 wk | Mon 08/04/24 | Fri 12/04/24
Ballylumford | NIB10 |  | GEN |  | 2 days | Tue 09/04/24 | Tue 09/04/24
CASTLEREAGH | HAN B | GC33, EG44 AND HANNAHSTOWN 'B' CVT | MAINT | 275 | 1 wk | Thu 11/04/24 | Thu 18/04/24
Kilroot | NIKGT1 |  | GEN |  | 4 days | Mon 15/04/24 | Wed 17/04/24
COOLKEERAGH |  | 12H0 MAINT LISAGHMORE B | MAINT | 110 | 1 wk | Mon 15/04/24 | Fri 19/04/24
LISAGHMORE |  | TX2 MINOR INC DOBLE AND TC FLUSH | MAINT | 110 | 8 days | Mon 15/04/24 | Wed 24/04/24
TANDRAGEE | WARINGSTOWN A | TOWER PAINTING | OHL | 110 | 1 wk | Mon 15/04/24 | Fri 19/04/24
Kilroot | NIKGT2 |  | GEN |  | 3 days | Thu 18/04/24 | Fri 19/04/24
TAMNAMORE |  | INTERBUS 2 MINOR & GP75 & MP60 | MAINT | 275 | 1 wk | Mon 22/04/24 | Fri 26/04/24
TANDRAGEE | WARINGSTOWN B | TOWER PAINTING | OHL | 110 | 1 wk | Mon 22/04/24 | Fri 26/04/24
DRUMNAKELLY |  | 3K0 sf6 repairs | MAINT | 110 | 1 wk | Mon 22/04/24 | Fri 26/04/24
KELLS |  | reactor 1 steps entexol | PROJ | 110 | 1 day | Thu 25/04/24 | Thu 25/04/24
HANNAHSTOWN |  | IBTX4 (275kV mesh closed, Lisburn circuit may need to be returned to service during high Moyle flows) IBTX1 AND liSBURN | PROJ | 110 | 3 wks | Sat 27/04/24 | Thu 16/05/24
GARVAGH |  | GVH TX WIRING MODIFICATIONS, POW adjustments | PROJ | 110 | 3 wks | Mon 29/04/24 | Fri 17/05/24
GARVAGH |  | BUSCOUPLER COMMISSIONING WORKS /WIRING MODIFICATIONS | PROJ | 110 | 3 days | Mon 29/04/24 | Wed 01/05/24
KELLS |  | reactor 2 steps entexol | PROJ | 110 | 1 day | Mon 29/04/24 | Mon 29/04/24
Moyle | MOYLE |  | GEN |  | 7 days | Sun 05/05/24 | Fri 10/05/24
FINAGHY | DONEGALL A | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1 wk | Mon 06/05/24 | Fri 10/05/24
KELLS | ANTIRM A | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1 wk | Mon 06/05/24 | Fri 10/05/24
BALLYLUMFORD |  | IBTX1 MINOR | MAINT | 275 | 1 wk | Mon 06/05/24 | Fri 10/05/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 1 day | Mon 06/05/24 | Mon 06/05/24
COOLKEERAGH |  | 16H0 MAINT SPRINGTOWN B + 16H3 & CVT & CSE's - tower CSE's ?? | MAINT | 110 | 1 wk | Tue 07/05/24 | Mon 13/05/24
SPRINGTOWN |  | TX2 MINOR MAINT | MAINT | 110 | 1 wk | Tue 07/05/24 | Mon 13/05/24
CARMONEY |  | TX A MAJOR MAINT INC SFRA | MAINT | 110 | 2 wks | Tue 07/05/24 | Sat 18/05/24
CARMONEY |  | 5C0 MAINT | MAINT | 110 | 3 days | Tue 07/05/24 | Thu 09/05/24
Moyle | MOYLE |  | GEN |  | 7 days | Sat 11/05/24 | Fri 17/05/24
Coolkeeragh | NICGT8 |  | GEN |  | 9 days | Mon 13/05/24 | Wed 22/05/24
BALLYLUMFORD | BALLYVALLAGH B | OHL WORKS | OHL | 110 | 1 wk | Mon 13/05/24 | Fri 17/05/24
FINAGHY | DONEGALL B | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1 wk | Mon 13/05/24 | Fri 17/05/24
FINAGHY |  | HAN B CSE MAINT | MAINT | 110 | 1 day | Mon 13/05/24 | Mon 13/05/24
KELLS | ANTIRM B | CLIMBING INSPECTIONS / PAINTING | OHL | 110 | 1 wk | Mon 13/05/24 | Fri 17/05/24
CASTLEREAGH |  | GC70 MAINT | MAINT | 275 | 5 days | Mon 13/05/24 | Fri 17/05/24
CASTLEREAGH | TANDRAGEE | OHL AND TOWER PAINTING | OHL | 275 | 2 wks | Mon 13/05/24 | Fri 24/05/24
CASTLEREAGH | TANDRAGEE | GC70/GC75 PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275 | 3 wks | Mon 13/05/24 | Fri 31/05/24
HANNAHSTOWN | BALLYCRONANMORE | OHL AND TOWER PAINTING | OHL | 275 | 1 wk | Mon 13/05/24 | Fri 17/05/24
HANNAHSTOWN | BYC | IBTX4 CORNER AND BYC CIRCUIT | PROJ | 275 | 8 wks | Mon 13/05/24 | Fri 05/07/24
STRABANE | killymalaght | POLE REPLACEMENTS WORKS | OHL | 110 | 1 wk | Mon 13/05/24 | Fri 17/05/24
Ballylumford | NIB10 |  | GEN |  | 65 days | Tue 14/05/24 | Fri 09/08/24
BALLYLUMFORD |  | GIS cable works GT2 (only), Includes CT replacements on the both circuits | PROJ | 110 | 6 wks | Mon 20/05/24 | Fri 28/06/24
NEWTOWNARDS |  | TX1 Major inc MR upgrade | MAINT | 110 | 3 wks | Mon 27/05/24 | Fri 14/06/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 1 day | Mon 27/05/24 | Mon 27/05/24
STRABANE | Omagh A | 6S0 MAINT /REPLACEMENT AND OMAGH A CVT | MAINT | 110 | 7 wks | Mon 27/05/24 | Fri 12/07/24
Coolkeeragh | NIC30 |  | GEN |  | 2 days | Sat 01/06/24 | Sat 01/06/24
DROMORE |  | MW10 MAINT DRUMQUIN CCT | MAINT | 110 | 1 wk | Mon 03/06/24 | Fri 07/06/24
DRUMQUIN |  | TX 1 MAJOR INC SFRA | MAINT | 110 | 1 wk | Mon 03/06/24 | Fri 07/06/24
DRUMQUIN |  | MX10 MAINT TX1 | MAINT | 110 | 1 wk | Mon 03/06/24 | Fri 07/06/24
DRUMQUIN |  | MX15 MAINT DROMORE | MAINT | 110 | 1 wk | Mon 03/06/24 | Fri 07/06/24
CARMONEY |  | TX B MINOR MAINT | MAINT | 110 | 1 wk | Mon 03/06/24 | Fri 07/06/24
CARMONEY |  | 6C0 MAINT | MAINT | 110 | 3 days | Mon 03/06/24 | Wed 05/06/24
OMAGH | DUNGANNON 'A' | 1M0/2M0 BAY PQ MONITOR AND WIRING MODIIFCATIONS | PROJ | 110 | 3 wks | Mon 03/06/24 | Fri 21/06/24
STRABANE |  | ISOLATOR REFURBS | MAINT | 110 | 4 wks | Mon 03/06/24 | Fri 28/06/24
STRABANE | omagh A | POLE REPLACEMENTS WORKS | OHL | 110 | 4 days | Mon 03/06/24 | Thu 06/06/24
COOLKEERAGH |  | TX1 MAJOR AND SHEATH TESTS , NO SFRA | MAINT | 110 | 2 wks | Mon 10/06/24 | Fri 21/06/24
COOLKEERAGH |  | 7H0 MAINT TX1 | MAINT | 110 | 5 days | Mon 10/06/24 | Fri 14/06/24
BALLYLUMFORD |  | IBTX2 MAJOR | MAINT | 275 | 3 wks | Mon 10/06/24 | Fri 28/06/24
BALLYLUMFORD |  | GT2 MD35 and Sheath | MAINT | 110 | 5 days | Mon 17/06/24 | Fri 21/06/24
COOLKEERAGH |  | TX2 MAJOR AND 33KV BUSHINGS AND COOLER DEFECT REPAIRS, NO SFRA | MAINT | 110 | 2 wks | Mon 24/06/24 | Fri 05/07/24
COOLKEERAGH |  | 9H0 MAINT TX2 | MAINT | 110 | 5 days | Mon 24/06/24 | Fri 28/06/24
Kilroot | NIKGT1 |  | GEN |  | 67 days | Mon 01/07/24 | Mon 30/09/24
EDEN | BALLYLUMFORD B | SNAGGING WORKS | OHL | 110 | 5 days | Mon 01/07/24 | Fri 05/07/24
EDEN | BALLYLUMFORD A | SNAGGING WORKS | OHL | 110 | 5 days | Mon 01/07/24 | Fri 05/07/24
LARNE |  | LARNE TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES AND TAPCHANGER REPAIR | PROJ | 110 | 2 wks | Mon 01/07/24 | Fri 12/07/24
LARNE |  | LARNE TX1 MAJOR | MAINT | 110 | 2 wks | Mon 01/07/24 | Fri 12/07/24
COOLKEERAGH | MAGHERAFELT A | A CIRCUIT OUTAGE CLEANING CONDUCTORS 20 SPANS | OHL | 275 | 2 wks | Mon 01/07/24 | Fri 12/07/24
ROSEBANK |  | 33KV CABLE ALTERATIONS ON TX 2 | PROJ | 110 | 2 wks | Wed 03/07/24 | Tue 16/07/24
ROSEBANK |  | 110KV EARTH SWITCH TX2 | PROJ | 110 | 2 wks | Wed 03/07/24 | Tue 16/07/24
ROSEBANK |  | NEW LVAC BOARD | PROJ | 110 | 1 wk | Wed 03/07/24 | Tue 09/07/24
DONEGALL |  | transformer D oil level gauge | MAINT | 110 | 2 days | Fri 12/07/24 | Mon 15/07/24
DRUMNAKELLY | TANDRAGEE 'A' | VT AND ISOLATORS DUE | MAINT | 110 | 2 days | Fri 12/07/24 | Mon 15/07/24
DRUMNAKELLY | TAMNAMORE 'B' | VT AND ISOLATORS DUE | MAINT | 110 | 2 days | Fri 12/07/24 | Mon 15/07/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 2 days | Fri 12/07/24 | Mon 15/07/24
COOLKEERAGH |  | 15H0 MAINT AND CAP BANK ( weeding only ) | MAINT | 110 | 2 days | Mon 15/07/24 | Tue 16/07/24
BELFAST CENTRAL MAIN |  | BCM tx A ETX LV ENCLOSURE | PROJ | 110 | 1 wk | Mon 15/07/24 | Fri 19/07/24
CASTLEREAGH | CREGAGH - BELFAST CENTRAL | CAS-CRG-BCM A & B START | PROJ | 110 | 6 wks | Mon 15/07/24 | Fri 23/08/24
CASTLEREAGH | CREGAGH - BELFAST CENTRAL 'A' | CAS-CRG-BCM A (PROJECTS) - 3 ENDED PROTECTION | PROJ | 110 | 6 wks | Mon 15/07/24 | Fri 23/08/24
STRABANE |  | 8S0 MAINT / REPLACEMENT | MAINT | 110 | 5 wks | Mon 15/07/24 | Fri 16/08/24
LARNE |  | LARNE TX2 BUSHINGS (PROJECTS) - BUSHING CHANGES | PROJ | 110 | 2 wks | Tue 16/07/24 | Mon 29/07/24
LARNE |  | LARNE TX2 MAJOR | MAINT | 110 | 2 wks | Tue 16/07/24 | Mon 29/07/24
BALLYLUMFORD | HANNAHSTOWN B | TOWER PAINTING | OHL | 275 | 2 wks | Tue 16/07/24 | Mon 29/07/24
BALLYLUMFORD | HANNAHSTOWN B | repair joint on Tower 672 Black/Yellow | OHL | 275 | 2 wks | Tue 16/07/24 | Mon 29/07/24
CARMONEY |  | 3C0 MAINT | MAINT | 110 | 3 days | Tue 16/07/24 | Thu 18/07/24
CASTLEREAGH |  | MC26 MAINT | MAINT | 110 | 3 days | Tue 16/07/24 | Thu 18/07/24
CASTLEREAGH | CARNMONEY A | CLIMBING INSPECTIONS / PAINTING/ line raising works | OHL | 110 | 1 wk | Tue 16/07/24 | Mon 22/07/24
COOLKEERAGH | MAGHERAFELT B | B CIRCUIT OUTAGES CLEANING CONDUCTORS 20 SPANS | OHL | 275 | 2 wks | Tue 16/07/24 | Mon 29/07/24
HANNAHSTOWN | BALLYLUMFORD B | OHL AND TOWER PAINTING | OHL | 275 | 1 wk | Tue 16/07/24 | Mon 22/07/24
HANNAHSTOWN | BALLYLUMFORD B | line characteristics | MAINT | 275 | 1 day | Tue 16/07/24 | Tue 16/07/24
HANNAHSTOWN | BPS | 275KV ISOLATORS 3 SETS BPS GG4,GG21,GG22 AND BPS MESH CORNER PROTECTION / DISCONNECT IBTX1 | PROJ | 275 | 15 wks | Tue 16/07/24 | Mon 28/10/24
CARMONEY |  | EDEN 'A' CVT | MAINT | 110 | 2 days | Mon 22/07/24 | Tue 23/07/24
COOLKEERAGH |  | GA55 MAINT MAG B | MAINT | 275 | 1 wk | Mon 22/07/24 | Fri 26/07/24
MAGHERAFELT |  | GH43 MAINT | MAINT | 275 | 5 days | Mon 22/07/24 | Fri 26/07/24
TAMNAMORE |  | MP30 MAINT TREMOGE | MAINT | 110 | 1 wk | Mon 29/07/24 | Fri 02/08/24
Ballylumford | NIBGT1 |  | GEN |  | 5 days | Tue 30/07/24 | Fri 02/08/24
KELLS |  | IBTX2 MINOR | MAINT | 110 | 1 wk | Mon 05/08/24 | Fri 09/08/24
MAGHERAFELT |  | GH5 MAINT BUSCOUPLER | MAINT | 275 | 1 wk | Mon 05/08/24 | Fri 09/08/24
TAMNAMORE |  | MP55 MAINT GORT | MAINT | 110 | 1 wk | Mon 05/08/24 | Fri 09/08/24
BALLYLUMFORD | EDEN A | OHL WORKS | OHL | 110 | 1 wk | Mon 05/08/24 | Fri 09/08/24
EDEN |  | 1T0 MAINT | MAINT | 110 | 5 days | Mon 05/08/24 | Fri 09/08/24
EDEN |  | 3T0 MAINT | MAINT | 110 | 5 days | Mon 05/08/24 | Fri 09/08/24
Ballylumford | NIBGT2 |  | GEN |  | 5 days | Tue 06/08/24 | Fri 09/08/24
NEWRY MAIN |  | TX2 MAJOR INC SFRA | MAINT | 110 | 8 days | Mon 12/08/24 | Wed 21/08/24
TANDRAGEE |  | MB20 MAINT NEWRY B | MAINT | 110 | 1 wk | Mon 12/08/24 | Fri 16/08/24
BALLYLUMFORD | EDEN 'B' | OHL WORKS | OHL | 110 | 1 wk | Mon 12/08/24 | Fri 16/08/24
CARMONEY |  | 2C0 MAINT | MAINT | 110 | 3 days | Mon 12/08/24 | Wed 14/08/24
CARMONEY |  | CAS B CVT MAINT | MAINT | 110 | 2 days | Mon 12/08/24 | Tue 13/08/24
CASTLEREAGH | CARNMONEY B | CLIMBING INSPECTIONS / PAINTING/ line raising works | OHL | 110 | 1 wk | Mon 12/08/24 | Fri 16/08/24
EDEN |  | 4T0 MAINT | MAINT | 110 | 4 days | Mon 12/08/24 | Thu 15/08/24
MAGHERAFELT | TAMNAMORE 'B' | DEFECT REPAIRS T256,T257 & T257A | OHL | 275 | 1 wk | Mon 12/08/24 | Fri 16/08/24
MAGHERAFELT |  | GH65 MAINT TAMANMORE 'B' | MAINT | 275 | 1 wk | Mon 12/08/24 | Fri 16/08/24
MULLAVILLY |  | CT, CVT AND CABLE CHARACTERISTICS TESTS | PROJ | 110 | 2 days | Mon 19/08/24 | Tue 20/08/24
TANDRAGEE |  | MB30 MAINT MULLAVILLY B/STORAGE | MAINT | 110 | 1 wk | Mon 19/08/24 | Fri 23/08/24
STRABANE |  | 7S0 REPLACEMENT AND OMAGH B CVT | PROJ | 110 | 7 wks | Mon 19/08/24 | Fri 04/10/24
BELFAST CENTRAL MAIN |  | BCM tx B ETX LV ENCLOSURE | PROJ | 110 | 1 wk | Mon 26/08/24 | Fri 30/08/24
BANK HOLIDAY/PUBLIC HOLS |  | PUBLIC HOLIDAY | HOL | SPARE | 1 day | Mon 26/08/24 | Mon 26/08/24
CASTLEREAGH | CREGAGH - BELFAST CENTRAL 'B' | CAS-CRG-BCM B (PROJECTS) - 3 ENDED PROTECTION | PROJ | 110 | 6 wks | Mon 26/08/24 | Fri 04/10/24
ENNISKILLEN | Corraclassy | ESB works at corraclassy and on OHL | EIR grid | 110 | 10 days | Mon 26/08/24 | Fri 06/09/24
COOLKEERAGH |  | GA75 MAINT IBTX2 | MAINT | 275 | 5 days | Tue 27/08/24 | Sat 31/08/24
COOLKEERAGH |  | 3H0 MAINT IBTX2 | MAINT | 110 | 5 days | Tue 27/08/24 | Sat 31/08/24
COOLKEERAGH |  | IBTX2 MINOR | MAINT | 275 | 1 wk | Tue 27/08/24 | Mon 02/09/24
TREMOGE | OMAGH B | prep works and measurements for diversion | OHL | 110 | 2 days | Sun 01/09/24 | Mon 02/09/24
Coolkeeragh | NIC30 |  | GEN |  | 21 days | Mon 02/09/24 | Fri 27/09/24
DRUMNAKELLY |  | DRU (TX1 TAPCHANGER PANELS) - PROJECTS | PROJ | 110 | 4 wks | Mon 02/09/24 | Fri 27/09/24
MAGHERAKEEL |  | TX1 MAJOR INC SFRA | MAINT | 110 | 8 days | Mon 02/09/24 | Wed 11/09/24
MAGHERAKEEL |  | MS20 MAINT | MAINT | 110 | 5 days | Mon 02/09/24 | Fri 06/09/24
MAGHERAKEEL |  | MS25 MAINT | MAINT | 110 | 1 wk | Mon 02/09/24 | Fri 06/09/24
OMAGH | MAGHERAKEEL | OHL CONDUCTOR SAMPLES and DLR equipment addition, CVT MAINT | OHL | 110 | 2.5 days | Mon 02/09/24 | Wed 04/09/24
BROCKAGHBOY |  | WINDFARM ANNUAL MAINT . | GEN | 110 |  | Mon 02/09/24
GORT |  | TRANSFORMER 2 OUTAGE TO REPAIR EM356 sticking | MAINT | 110 | 2 wks | Mon 02/09/24
BALLYLUMFORD | BALLYVALLAGH A | OHL WORKS | OHL | 110 | 1 wk | Mon 09/09/24 | Fri 13/09/24
ARVA | GORTAWEE | placeholder | EIR grid | 110 | 10 days | Mon 09/09/24 | Fri 20/09/24
OMAGH |  | 6M0 SF6 LEAK REPAIR | MAINT | 110 | 1 wk | Mon 09/09/24 | Fri 13/09/24
STRABANE | OMAGH B | POLE REPLACEMENT WORKS | OHL | 110 | 1 wk | Mon 09/09/24 | Fri 13/09/24
MAGHERAKEEL |  | TX2 MAJOR INC SFRA | MAINT | 110 | 8 days | Thu 12/09/24 | Mon 23/09/24
MAGHERAKEEL |  | MS45 MAINT | MAINT | 110 | 1 wk | Thu 12/09/24 | Wed 18/09/24
Ballylumford | NIB31 |  | GEN |  | 4 days | Fri 13/09/24 | Tue 17/09/24
Ballylumford | NIB32 |  | GEN |  | 6 days | Fri 13/09/24 | Thu 19/09/24
ENNISKILLEN |  | 110KV CABLE REPLACEMENT TRANSFORMER 2, INSTALL DISCONNECTOR | PROJ | 110 | 4 wks | Mon 16/09/24 | Fri 11/10/24
Ballylumford | NIB31 |  | GEN |  | 8 days | Wed 18/09/24 | Thu 26/09/24
Ballylumford | NIB32 |  | GEN |  | 4 days | Fri 20/09/24 | Tue 24/09/24
DROMORE |  | MW30 MAINT OMAGH 'A' | MAINT | 110 | 1 wk | Mon 23/09/24 | Fri 27/09/24
Ballylumford | NIB32 |  | GEN |  | 3 days | Wed 25/09/24 | Thu 26/09/24
DRUMNAKELLY |  | DRU (TX3 TAPCHANGER PANELS) - PROJECTS | PROJ | 110 | 4 wks | Mon 30/09/24 | Fri 25/10/24
Kilroot | NIKGT2 |  | GEN |  | 24 days | Tue 01/10/24 | Thu 31/10/24
TREMOGE | OMAGH B | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION/ EARTH WIRE COMPLETION LAST SPAN OVER UNDERCOSSING | OHL | 110 | 2 wks | Tue 01/10/24 | Sat 12/10/24
CASTLEREAGH |  | MC35 MAINT ( IBTX3) | MAINT | 110 | 5 days | Mon 07/10/24 | Fri 11/10/24
CASTLEREAGH |  | IBTX3 MINOR | MAINT | 275 | 1 wk | Mon 07/10/24 | Fri 11/10/24
COOLKEERAGH | Strabane | tower painting | OHL | 110 | 2 wks | Mon 07/10/24 | Fri 18/10/24
CLOCKCHANGE |  | CLOCKCHANGE | TIME | SPARE | 1 day | Sun 27/10/24 | Sun 27/10/24
BALLYMENA |  | TX2 BUSHING REPLACEMENT AND BUSBAR COVER REPLACEMENT | MAINT | 110 | 2.2 wks | Fri 01/11/24 | Fri 15/11/24
KELLS |  | CIRCUIT BREAKER FAILS | PROJ | 275
KILROOT |  | CIRCUIT BREAKER FAILS SCHEME ( 13 SETS ) | PROJ | 275
KELLS |  | MF100 MAINT BALLYVALLAGH B | MAINT | 110
BALLYLUMFORD |  | GD5 MAINT | MAINT | 275
BALLYLUMFORD |  | MD50 MAINT (BUS-COUPLER ) | MAINT | 110
BALLYMENA |  | Transformer '3' cable duct sealing at 33kv letterbox | PROJ | 110
BALLYVALLAGH |  | SECTION 1 BUSBAR | MAINT | 110
BALLYVALLAGH |  | SECTION 2 BUSBAR | MAINT | 110
CASTLEREAGH |  | SECTION 1R BUSBAR ( ISOLATORS) | MAINT | 110
CASTLEREAGH |  | SECTION 1L BUSBAR (ISOLATORS ) | MAINT | 110
CASTLEREAGH |  | SECTION 2R BUSBAR ( ISOLATORS ) | MAINT | 110
CASTLEREAGH |  | SECTION 2L BUSBAR ( ISOLATORS ) | MAINT | 110
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION A2 BUSBAR (BUSBAR) - | MAINT | 275
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2L BUSBAR (BUSBAR) - | MAINT | 110
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 2R BUSBAR (BUSBAR) - | MAINT | 110
HANNAHSTOWN |  | 110KV ISOLATORS SECTION 1L | MAINT | 110
HANNAHSTOWN |  | 110KV ISOLATORS SECTION 1R | MAINT | 110
KELLS |  | SECTION 1L BUSBAR ( 3 ISOLATORS) | MAINT | 110
KELLS |  | SECTION 1R BUSBAR ( 4 ISOLATORS ) | MAINT | 110
KELLS |  | SECTION 2R BUSBAR ( 4 ISOLATORS) | MAINT | 110
KILROOT |  | GJ50 MAINT | MAINT | 275
KILROOT |  | GJ50 MAINT | MAINT | 275
OMAGH |  | 10M0 MAINT | MAINT | 110
OMAGH |  | 3M0 MAINT | MAINT | 110
OMAGH |  | 9M0 MAINT | MAINT | 110
TANDRAGEE |  | SECTION '1L' ISOLATORS - MAINTENANCE | MAINT | 275
TANDRAGEE |  | SECTION '2R' ISOLATOR | MAINT | 110
TANDRAGEE |  | SECTION '2L' ISOLATORS - MAINTENANCE | MAINT | 110
TANDRAGEE |  | SECTION '1R' ISOLATORS - MAINTENANCE | MAINT | 110
DRUMNAKELLY |  | 5K0 MAINT | MAINT | 110
DRUMNAKELLY |  | 7K0 MAINT | MAINT | 110
COOLKEERAGH |  | 1H0 MAINT BUS-COUPLER INC 1H2 MAINT | MAINT | 110
TANDRAGEE | NEWRY B | ARCING HORN DEFECT REPAIRS | OHL | 110
KILROOT |  | NEW GENERATOR 7 BAY proximity to test cable on gen 7 | PROJ | 275 | TBC
KILROOT |  | NEW GENERATOR 7 BAY cable retest | PROJ | 275 | TBC
HANNAHSTOWN |  | IBTX4 110KV NEW GANTRY CONSTRUCTION AT GG8 | PROJ | 275 | TBC
HANNAHSTOWN | BALLYLUMFORD B (and BYC) | line characteristics | MAINT | 275 | TBC
HANNAHSTOWN | CASTLEREAGH A & B | earth wire conductor sampling dual circuit outage | OHL | 275 | TBC
BALLYLUMFORD | HANNAHSTOWN B | CVT REPLACEMENT | PROJ | 275
BALLYCRONANMORE |  | MOYLES ANNUAL MAINTENANCE | GEN | 275
KILROOT |  | 275kv CT BAY TBC | PROJ | 275 | TBC
KILROOT |  | 275kv CT BAY TBC | PROJ | 275 | TBC
OMAGH | DROMORE 'A' | OMA - DRO A (OHL WORK) - SNAGGING | OHL | 110 | TBC
OMAGH | DROMORE 'B' | OMA - DRO B (OHL WORK) - SNAGGING | OHL | 110 | TBC
TREMOGE |  | SECTION 2 BUSBAR | MAINT | 110
BALLYCRONANMORE |  | LINE TRAP REPLACE tuning UNITS AT BYC END OF HAN CIRCUIT | PROJ | 275
COOLKEERAGH |  | 110KV CABLE REPLACMEMENT IBTX1 CABLE | PROJ | 275 | TBC
KILROOT | TANDRAGEE | GJ70/GJ75 BAY PQ MONITOR AND WIRING MODIFCATIONS | PROJ | 275
TAMNAMORE |  | GP85 MAINT TAN B | MAINT | 275
MAGHERAFELT | TAMNAMORE 'A' | TMN- MAG 'A' (OHL WORK) - SINGLE TENSION TOWER 228 & 253 | OHL | 275
MAGHERAFELT | TAMNAMORE 'A' | GH55 BAY PQ MONITOR AND WIRING MODIFICATIONS | PROJ | 275
STRABANE |  | 5S0 REPLACEMENT AND CPS B CVT | PROJ | 110 | TBC
TANDRAGEE |  | TANDRAGEE MBXX CIRCUIT BREAKER AND CT REPLACEMENT | PROJ | 110
HANNAHSTOWN | BALLYCRONANMORE | CVT maintaince & test | OHL | 275
HANNAHSTOWN |  | 275KV ISOLATORS BYC CORNER INSTALL BUSBARS FINISH CVT AND LINE TRAPS | PROJ | 275
STRABANE | COOLKEERAGH 'B' | OHL WORKS | PROJ | 110
LISBURN MAIN |  | TX2 LNER | MAINT | 110
LISBURN MAIN |  | TX1 LNER | MAINT | 110
RATHGAEL |  | TX1 LNER | MAINT | 110
TANDRAGEE |  | TANDRAGEE IBTX3 MINOR AND REPLACE RX3 BUCHOLZ & PRD'S | MAINT | 275
COOLKEERAGH |  | COOLKEERAGH MAIN SECTION 1 (BUSBAR) | MAINT | 110
Coolkeeragh | NICGT8 |  | GEN